# Development Research in Practice

Kristoffer Bjarkefur, Luiza Cardoso de Andrade, Benjamin Daniels, Maria Ruth Jones

# oi

# Acknowledgments and notes

We want to thank all the people who helped us get here, especially Arianna Legovini, for her leadership at DIME, unending support of our work, and detailed comments on this book; and Florence Kondylis, for her leadership in founding and growing DIME Analytics and supporting this project from the very first. We also thank the following members of DIME Analytics for their contributions to the ideas in this book and their help organizing them: Roshni Khincha, Avnish Singh, Patricia Paskov, Radhika Kaul, Mizuhiro Suzuki, Yifan Powers, and Maria Arnal Canudo. This work has been financially supported by the United Kingdom Foreign, Commonwealth & Development Office (FCDO) through the DIME i2i Umbrella Facility for Impact Evaluation at the World Bank.

Our graditude to the many people who read and offered feedback as the book took shape: Stephanie Annijas, Maria Camila Ayala Guerrero, Kaustubh Chahande, Thomas Escande, Aram Gassama, Steven Glover, Nausheen Khan, Robert Norling, Michael Orevba, Caio Piza, Francesco Raffaelli, Daniel Rogger, Ankriti Singh, Ravi Somani, and Leonardo Viotti. Although they number far too many to name individually, we also thank all the members of DIME and its teams across all the years for the innovative work they have done, the lessons learned, and the team spirit that makes our work so fruitful and rewarding.

This published version of the book has been revised repeatedly since its internal release in June 2019, with extensive feedback from readers and experts. We would additionally like to thank Vincenzo di Maro (Manager, DIME3) for his support throughout this process, as well as peer reviewers David McKenzie (Lead Economist, DECFP), Holly Krambeck (Program Manager, DECAT), Alaka Holla (Program Manager, HEDGE), Jim Shen (Senior Manager, Abdul Latif Jameel Poverty Action Lab), Federica di Battista (Trialling Lead, UK FCDO), and Gabriel Vicente, Rajee Kanagavel, and Maksim Pecherskiy from the Development Data Partnership team.

This book is a living product that is written and maintained publicly. The code and edit history are at: . You can get a PDF copy at: . The website includes updated instructions for providing feedback, as well as notes on updates to the content. Whether you work with DIME, the World Bank, or another organization or university, we ask that you read the contents of this book critically. We welcome feedback and corrections to improve the book. Please visit  to provide feedback. You can also email us at dimeanalytics@worldbank.org, and we will be very thankful. We hope you enjoy Development Research in Practice!

# Abbreviations

2SLS – Two-Stage Least Squares

AEA – American Economic Association

CAPI – Computer-Assisted Personal Interviewing

DD or DiD – Differences-in-Differences

DDI - Data Documentation Initiative

DIME – Development Impact Evaluation

DOI – Digital object identifier

eGAP – Evidence in Governance and Politics

EU – European Union

FDE - Full Disk Encryption

FSE - Full System Encryption

GDPR – Global Data Protection Regulation

HFC – High-Frequency Checks

IPA – Innovations for Poverty Action

IRB – Institutional Review Board

IV – Instrumental Variables

J-PAL – The Abdul Latif Jameel Poverty Action Lab

MD – Minimum Detectable Effect

NGO – Non-Governmental Organization

ODK – Open Data Kit

OLS – Ordinary Least Squares

OSF – Open Science Foundation

PI – Principal Investigator

PII – Personally-Identifying Information

RA – Research Assistant

RD – Regression Discontinuity

RCT – Randomized Control Trial

SSC – Statistical Software Components

VPN - Virtual Private Network

# Preface

Welcome to Development Research in Practice: The DIME Analytics Data Handbook. This book is intended to teach all users of development data how to handle data effectively, efficiently, and ethically. An empirical revolution has changed the face of development research rapidly over the last decade. Increasingly, researchers are working not just with complex data, but with original data: datasets collected by the research team themselves or acquired through a unique agreement with a project partner. Research teams must carefully document how original data is created, handled, and analyzed. These tasks now contribute as much weight to the quality of the evidence as the research design and the statistical approaches do. At the same time, the scope and scale of empirical research projects is expanding: more people are working on the same data over longer timeframes. For that reason, the central premise of this book is that data work is a “social process”. This means that the many different people on a team need to have the same ideas about what is to be done, and when and where and by whom, so that they can collaborate effectively on a large, long-term research project.

Despite the growing importance of managing data work, little practical guidance is available for practitioners. There are few guides to the conventions, standards, and best practices that are fast becoming a necessity for empirical research. Development Research in Practice aims to fill that gap. It covers the full data workflow for a complex research project using original data. We share the lessons, tools, and processes developed within the World Bank’s Development Impact Evaluation (DIME) department, and compile them into a single narrative of best practices for data work. This book is not sector-specific; it will not teach you econometrics, or how to design an impact evaluation. There are many excellent existing resources on those topics. Instead, it will teach you how to think about all aspects of your research from a data perspective, how to structure research projects to ensure data quality, and how to institute transparent and reproducible workflows. We realize that adopting these workflows may have significant upfront learning costs, but we are convinced that these investments pay off quickly, as you will both save time and improve the quality of your research going forward.

## How to read this book

This book aims to be a highly practical resource so the reader can immediately begin to collaborate more effectively on large, long-term research projects that use the methods and tools discussed. This introduction outlines the basic philosophies that motivate this book and our approach to research data. We want all readers to understand at the outset our mindset that research data work is primarily about communicating effectively within a team and that standardization and simplification of data tasks is a major enabler of effective collaboration. The main chapters of this book will walk you through the data workflow at each stage of an empirical research project, from design to publication. The figure in this introduction visualizes the data workflow. Chapters 1 and 2 contextualize the workflow, and set the stage for the hands-on data tasks which are described in detail in Chapters 3 to 7.

Chapter 1 This book aims to be a highly practical resource so the reader can immediately begin to collaborate more effectively on large, long-term research projects that use the methods and tools discussed. This introduction outlines the basic philosophies that motivate this book and our approach to research data. We want all readers to understand at the outset our mindset that research data work is primarily about communicating effectively within a team and that standardization and simplification of data tasks is a major enabler of effective collaboration. The main chapters of this book will walk you through the data workflow at each stage of an empirical research project, from design to publication. The figure in this introduction visualizes the data workflow. Chapters 1 and 2 contextualize the workflow, and set the stage for the hands-on data tasks which are described in detail in Chapters 3 to 7.

Chapter 2 teaches you to structure your data work for collaborative research, while ensuring the privacy and security of research participants. It discusses the importance of planning data work and associated tools in advance, long before any data is acquired. It also describes ethical concerns common to development data, common pitfalls in legal and practical management of data, and how to respect the rights of research participants at all stages of data work

Chapter 3 turns to the measurement framework, and how to translate research design to a data work plan. It details DIME’s data map template, a set of tools to communicate the project’s data requirements both across the team and across time. It also discusses how to implement random sampling and random assignment in a reproducible and credible manner.

Chapter 4 covers data acquisition. It starts with the legal and institutional frameworks for data ownership and licensing, to ensure that you are aware of the rights and responsibilities of using data collected by the research team or by others. It provides a deep dive on collecting high-quality primary electronic survey data, including developing and deploying survey instruments. Finally, it discusses secure data handling during transfer, sharing, and storage, which is essential in protecting the privacy of respondents in any data.

Chapter 5 describes data processing tasks. It details how to construct “tidy” data at the appropriate units of analysis, how to ensure uniquely identified datasets, and how to routinely incorporate data quality checks into the workflow. It also provides guidance on de-identification and cleaning of personally-identified data, focusing on how to understand and structure data so that it is ready for indicator construction and analytical work.

Chapter 6 discusses data analysis tasks. It begins with data construction, or the creation of new variables from the raw data acquired or collected in the field. It introduces core principles for writing analytical code and creating, exporting, and storing research outputs such as figures and tables reproducibly using dynamic documents.

Chapter 7 outlines the publication of research outputs, including manuscripts, code, and data. This chapter discusses how to effectively collaborate on technical writing using dynamic documents. It also covers how and why to publish datasets in an accessible, citable, and safe fashion. Finally, it provides guidelines for preparing functional and informative reproducibility packages that contain all the code, data, and meta-information needed for others to evaluate and reproduce your work.

Each chapter starts with a box which provides a summary of the most important points, takeaways for different types of readers, and a list of key tools and resources for implementing the recommended practices. After reading each chapter, you should understand what tasks will be performed at every stage of the workflow, and how to implement them according to best practices. You should also understand how the various stages of the workflow tie together, and what inputs and outputs are required and produced from each. The references and links contained in each chapter will lead you to detailed descriptions of individual ideas, tools, and processes to refer to when you need to implement the tasks yourself.

### Demand for Safe Spaces Case Study

Throughout this Handbook, we will refer to a completed DIME project, Demand for Safe Spaces: Avoiding Harassment and Stigma, to provide a case study of the empirical research tasks described in this book. You will find boxes in each chapter with examples of how the practices and workflows described in that chapter were applied in this real-life example. All the code examples and diagrams referenced in the case study can be accessed directly through this book’s GitHub repository. We have made minor adaptations to the original study materials presented for function and clarity. All original materials can be found in the project’s reproducibility package.

The Demand for Safe Spaces study is summarized in its abstract as follows. What are the costs to women of harassment on public transit? This study randomizes the price of a women-reserved “safe space” in Rio de Janeiro and crowdsource information on 22,000 rides. Women in the public space experience harassment once a week. A fifth of riders are willing to forgo 20 percent of the fare to ride in the “safe space”. Randomly assigning riders to the “safe space” reduces physical harassment by 50 percent, implying a cost of $1.45 per incident. Implicit Association Tests show that women face a stigma for riding in the public space that may outweigh the benefits of the safe space.

The Demand for Safe Spaces study used novel original data from three sources. It collected information on 22,000 metro rides from a crowdsourcing app (referred to as crowdsourced ride data in the case study examples), a survey of randomly-sampled commuters on the platform (referred to as the platform survey), and data from an implicit association test. The research team first elicited revealed preferences for the women-reserved cars, and then randomly assigned riders across the reserved and non-reserved cars to measure differences in the incidence of harassment. The use of a customized app allowed the researchers to assign data collection tasks and vary assigned ride spaces (women-reserved car vs public cars) and associated payout across rides. In addition, the team administered social norm surveys and implicit associations tests on a random sample of men and women commuters to document a potential side eﬀect of reserved spaces: stigma against women who choose to ride in the public space.

For the purposes of the Handbook, we focus on the protocols, methods, and data used in the Demand for Safe Spaces study, rather than the results. To learn more about the findings from this study, and more details on how it was conducted, we encourage readers to download the working paper. The material from all the examples in the book and be found at https://github.com/worldbank/dime-data-handbook/tree/master/examples.

The Demand for Safe Spaces study repository can be accessed at https://github.com/worldbank/rio-safe-space.

The working paper Demand for Safe Spaces: Avoiding Harassment and Stigma is available at https://openknowledge.worldbank.org/handle/10986/33853.

## The DIME Wiki: A complementary resource

Throughout the book, you will find many references to the DIME Wiki. The DIME Wiki is a free online collection of impact evaluation resources and best practices. This handbook and the DIME Wiki are meant to go hand-in-hand: the handbook provides the narrative structure and workflow, and the Wiki dives into specific implementation details, offers detailed code examples, and provides a more exhaustive set of references for each topic. Importantly, the DIME Wiki is a living resource that is continuously updated and improved, by the authors of this book and external contributors. We welcome all readers to register as Wiki users and contribute directly.

Overview of development research data work tasks

## Standardizing data work

In the past, data work was often treated as a “black box” in research. A published manuscript might exhaustively detail research designs, estimation strategies, and theoretical frameworks, but typically reserved very little space for detailed descriptions of how data was actually collected and handled. It is almost impossible to assess the quality of the data in such a paper, and whether the results could be reproduced. In the past decade, this has started to change, in part due to increasing requirements by publishers and funders to release code and data.

Data handling and documentation is a key skill for researchers and research staff. Standard processes and documentation practices are important throughout the research process to accurately convey and implement the intended research design, and to minimizes security risks: better protocols and processes lower the probability of data leakages, security breaches, and loss of personal information. When data work is done in an ad-hoc manner, it is very difficult for others to understand what is being done – a reader has to simply trust that the researchers did these things right. Most importantly, if any part of the data pipeline breaks down, research results become unreliable and cannot be faithfully interpreted as being an accurate picture of the intended research design. Because we almost never have “laboratory” settings in this type of research, such a failure has a very high cost: we will have wasted the investments that were made into knowledge generation, and the research opportunity itself, where we intended to conduct the study.

Accurate and reproducible data management and analysis is essential to the success and credibility of modern research. Standardizing and documenting data handling processes is essential to be able to evaluate and understand the data work alongside any final research outputs. An important component of this is process standardization. Process standardization means that there is little ambiguity about how something ought to be done, and therefore the tools to do it can be set in advance. Standard processes help other people understand your work, and they also make your work easier to document. Process standardization and documentation should allow readers of your code to: (1) quickly understand what a particular process or output is supposed to be doing; (2) evaluate whether or not it does that thing correctly; and (3) modify it either to test alternative hypotheses or to adapt into their own work. This book will discuss specific standards recommended by DIME Analytics, but we are more interested in convincing the reader to discuss the adoption of a standard within research teams than to necessarily use the particular standards that we recommend.

## Standardizing coding practices

Modern quantitative research relies heavily on standardized statistical software tools, written with various coding languages, to standardize analytical work. Outputs like regression tables and data visualizations are created using code in statistical software for two primary reasons. The first is that using a standard command or package ensures that the work is done right, and the second is that it ensures the same procedure can be confirmed or checked at a later date or using different data. Keeping a clear, human-readable record of these code and data structures is critical. While it is often possible to perform nearly all the relevant tasks through an interactive user interface or even through software such as Excel, this practice is strongly advised against. In the context of statistical analysis, the practice of writing all work using standard code is widely accepted. To support this practice, DIME now maintains portfolio-wide standards about how analytical code should be maintained and made accessible before, during, and after release or publication.

Over the last few years, DIME has extended the same principles to preparing data for analysis, which often comprises just as much (or more) of the manipulation done to the data over the life cycle of a research project. A major aim of this book is to encourage research teams to think of the tools and processes they use for designing, collecting, and handling data just as they do for analytical tasks. Correspondingly, a major contribution of DIME Analytics has been tools and standard practices for implementing these tasks using statistical software.

While we assume that you are going to do nearly all data work using code, many development researchers come from economics and statistics backgrounds and often understand code to be a means to an end rather than an output itself. We believe that this must change somewhat: in particular, we think that development practitioners must think about their code and programming workflows just as methodologically as they think about their research workflows, and think of code and data as research outputs, just as manuscripts and briefs are.

This approach arises because we see the code as the “recipe” for the analysis. The code tells others exactly what was done, how they can do it again in the future, and provides a roadmap and knowledge base for further original work. Performing every task through written code creates a record of every task you performed. It also prevents direct interaction with the data files that could lead to non-reproducible processes. Finally, DIME Analytics has invested a lot of time in developing code as a learning tool: the examples we have written and the commands we provide are designed to provide a framework for common practice across the entire DIME team, so that everyone is able to read, review, and provide feedback on the work of others starting from the same basic ideas about how various tasks are done.

Most specific code tools have a learning and adaptation process, meaning you will become most comfortable with each tool only by using it in real-world work. To support your process of learning reproducible tools and workflows, we reference free and open-source tools wherever possible, and point to more detailed instructions when relevant. Stata, as a proprietary software, is the notable exception here due to its persistent popularity in development economics and econometrics. This book also includes, in an appendix, the DIME Analytics Coding Guide which includes instructions for how to write good code, instructions on how to use the code examples in this book, as well as our Stata Style Guide. DIME projects are strongly encouraged to explicitly adopt and follow coding style guides in their work. Style guides harmonize code within and across teams making it easier to understand and reuse code, which ultimately helps teams to build on each other’s best practices. Some of the programming languages used at DIME already have well-established and commonly used style guides, such as the Tidyverse style guide for R and PEP-8 for Python.. Stata has relatively few resources of this type available, which is why we have created and included one here that we hope will be an asset to all Stata users.

## The team behind this book

DIME is the Development Impact Evaluation department of the World Bank. Its mission is to generate high-quality and operationally relevant data and research to transform development policy, help reduce extreme poverty, and secure shared prosperity. DIME develops customized data and evidence ecosystems to produce actionable information and recommend specific policy pathways to maximize impact. The department conduct research in 60 countries with 200 agencies, leveraging a US$180 million research budget to shape the design and implementation of US$18 billion in development finance. DIME also provides advisory services to 30 multilateral and bilateral development agencies. DIME research is organized into four primary topic pillars: Economic Transformation and Growth; Gender, Economic Opportunity, and Fragility; Governance and Institution Building; and Infrastructure and Climate Change. Over the years, DIME has employed dozens of research economists, and hundreds of full-time research assistants, field coordinators, and other staff. The team has conducted over 325 impact evaluations. Development Research in Practice exists to take advantage of that concentration and scale of research, to synthesize many resources for data collection and research, and to make DIME tools available to the larger community of development researchers.

As part of its broader mission, DIME invests in public goods to improve the quality and reproducibility of development research around the world. One key early innovation at DIME was the creation of DIME Analytics, the team responsible for writing and maintaining this book. DIME Analytics is a centralized unit that develops and ensures adoption of high quality research practices across the department’s portfolio. This is done through an intensive, collaborative innovation cycle: DIME Analytics onboards and supports research assistants and field coordinators, provides standard tools and workflows to all teams, delivers hands-on support when new tasks or challenges arise, and then develops and integrates lessons from those engagements to bring to the full team. Resources developed and tested in DIME are converted into public goods for the global research community, through open-access trainings and open-source tools. The DIME Analytics Resource Directory appendix provides an introduction to public materials.

DIME Analytics has invested many hours over the past years learning from data work across DIME’s portfolio, identifying inefficiencies and barriers to success, developing tools and trainings, and standardizing best-practice workflows adopted in DIME projects. It has also invested significant energy in the language and materials used to teach these workflows to new team members, and, in many cases, in software tools that support these workflows explicitly. DIME team members often work on diverse portfolios of projects with a wide range of teammates, and we have found that standardizing core processes across all projects results in higher-quality work with fewer opportunities to make mistakes. In that way, the Analytics team is DIME’s method of institutionalizing tools and practices, developed and refined over time, that give the department a common base of knowledge and practice. In 2018, for example, DIME adopted universal reproducibility checks conducted by the Analytics team; the lessons from this practice helped move the DIME team from where 50% of submitted papers in 2018 required significant revision to pass to where 64% of papers passed in 2019 without revision required.

## Looking ahead

While adopting the workflows and mindsets described in this book requires an up-front cost, it will save you (and your collaborators) a lot of time and hassle very quickly. In part this is because you will learn how to implement essential practices directly; in part because you will find tools for the more advanced practices; and most importantly because you will acquire the mindset of doing research with a high-quality data focus.

For some readers, the amount of new tools and practices recommended in this book may seem daunting. We know from experience at DIME that full-scale adoption is possible; in the last few years, the full DIME portfolio has transitioned to transparent and reproducible workflows, with a fair share of hiccups along the way. The authors of this book supported that at-scale transition, and we hope that by sharing our lessons learned and resources, the learning curve for readers will be less steep. In the summary boxes at the beginning of each chapter, we provide a list of the key tools and resources to help readers prioritize. We will also offer “second-best” practices in many cases, suggesting easy-to-implement suggestions to increase transparency and reproducibility, in cases where full-scale adoption of the recommended workflows is not immediately feasible. In fact, we encourage teams to adopt one new practice at a time rather than rebuild their whole workflow from scratch right away. We hope that by the end of the book, all readers will have learned how to handle data more efficiently, effectively and ethically at all stages of the research process.

# Conducting reproducible, transparent, and credible research

Policy decisions are made every day using the results of development research, and these have wide-reaching effects on the lives of millions. As the emphasis on evidence-based policy grows, so too does the scrutiny under which research methods and results are placed. Three major components make up this scrutiny: credibility, transparency, and reproducibility. These three components contribute to one simple idea: research should be high quality and well-documented. Research consumers, including the policy makers who will use the evidence to make decisions, should be able to easily examine and recreate such evidence. In this framework, it is useful to think of research as a public service that requires researchers as a group to be accountable for their methods. This means acting to collectively protect the credibility of development research by following modern practices for research planning and documentation. Across the social sciences, the open science movement has been fueled by concerns about the proliferation of low-quality research practices, data and code that are inaccessible to the public, analytical errors in major research papers, and in some cases even outright fraud. While the development research community has not yet experienced major scandals, it has become clear that there are necessary improvements to make in the way that code and data are handled as part of research. Moreover, having common standards and practices for creating and sharing materials, code, and data with others will improve the value of the work we do.

In this chapter, we outline principles and practices that help to ensure research consumers can be confident in the conclusions reached. We discuss each of the three components – credibility, transparency, and reproducibility – in turn. The first section covers research credibility. It presents three popular methods to commit to particular research questions or methods, and avoid potential criticisms of cherry-picking results: registration, pre-analysis plans, and registered reports. The second section discusses how to apply principles of transparency to all research processes, which allows research teams to be more efficient, and research consumers to fully understand and evaluate research quality. The final section provides guidance on how to make your research fully reproducible, and explains why publishing replication materials is an important research contribution in its own right.

### Summary: Conducting reproducible, transparent, and credible research

This chapter describes three pillars of a high-quality empirical research project: credibility, transparency and reproducibility. These steps and outputs discussed in this chapter should be prepared at the beginning of a project and revisited through the publication process.

1. Credibility: to enhance credibility, you should pre-commit research decisions as much as feasible

- Register research studies to provide a record of every project, so all evidence about a topic can be maintained; pre-register studies to protect design choices from later criticism.

- Write pre-analysis plans for data collection and analysis to both strengthen the conclusions drawn from those analyses and increase efficiency by creating a road map for project data work.

- Publish a registered report to combines the benefits of the two steps above with a formal peer review process and a conditional acceptance of the final results of the specified research.

2. Transparency: you should document all data acquisition and analysis decisions during the project lifecycle, with a clear understanding of what will be released publicly and plan for how those will be published

- Develop and publish comprehensive project documentation, especially instruments for data collection or acquisition that may be needed to prove ownership rights and facilitate re-use of the data.

- Retain all original data in an unaltered form and archive it appropriately, in preparation for it to be de-identified and published at the appropriate time.

- Write all data processing and analysis code with public release in mind.

3. Reproducibility: Prepare analytical work that can be verified and reproduced by others. This means

- Understanding what archives and repositories are appropriate for your various materials

- Preparing for legal documentation and licensing of data, code, and research products

- Initiating reproducible workflows that will easily transfer within and outside of your research team and the necessary documentation for others to understand and use your materials

#### Takeaways

TTLs/PIs will:

- Develop and document the research design and the corresponding data required to execute it

- Guide the research team in structuring and completing project registration

- Understand the team’s future rights and responsibilities regarding data, code, and research publication

- Determine what methods of pre-commitment are appropriate and lead the team in preparing them

RAs will:

- Rework outputs and documentation to meet specific technical requirements of registries, funders, publishers, or other governing bodies

- Inform the team leadership whenever methodologies, data strategies, or their planned executions are not sufficiently clear or are not appropriately documented or communicated

- Familiarize themselves with best practices for carrying out reproducible and transparent research, and initiate those practices within the research team

#### Key Resources

- Register your research study: https://dimewiki.worldbank.org/Study_Registration

- Create a pre-analysis plan: https://dimewiki.worldbank.org/Pre-Analysis_Plan

- Prepare to document research decisions: https://dimewiki.worldbank.org/Data_Documentation

- Publish data in a trusted repository: https://dimewiki.worldbank.org/Publishing_Data

- Prepare and publish a reproducibility package: https://dimewiki.worldbank.org/Reproducible_Research

## Developing a credible research project

The evidentiary value of research is traditionally a function of design choices, such as powered through sampling and randomization, and robustness to alternative specifications and definitions. One frequent target for critics of such research is the fact that most researchers have a lot of leeway in selecting their projects, results, or outcomes after already having had the experience of implementing a project or collecting data in the field, which increases the likelihood of finding “false positive” results that are not true outside carefully-selected data. Credible research design methods are key to maintaining credibility in these choices and avoiding serious errors. This is especially relevant for research that relies on original data sources, from innovative big data sources to unique surveys. Development researchers should take these concerns seriously. Such flexibility can be a significant issue for the quality of evidence overall, particularly if researchers believe that certain types of results are substantially better for their careers or their publication chances.

This section presents three popular methods for researchers to commit to particular research questions or methods, and to avoid potential criticisms of cherry-picking results for publication: registration, pre-analysis plans, and registered reports. Each of these methods involves documenting specific research design components, ideally before carrying out the analytical component or extensively exploring the data. Study registration provides formal notice that a study is being attempted and creates a hub for materials and updates about the study results. Pre-analysis plans are a more formal commitment to use specific methods on particular questions. Writing and releasing a pre-analysis plan in advance of working with data is used to protect the credibility of approaches that have a high likelihood of producing false results. Finally, registered reports allow researchers to approach research planning itself as a process at the level of a full peer review. Registered reports enable close scrutiny of a research design, a feedback and improvement process, and a commitment from a publisher to publish the study based on the credibility of the design, rather than the specific results.

### Registering research studies

Registration of research studies is an increasingly common practice, and more journals are beginning to require the registration of studies they publish. Study registration intended to ensure that a complete record of research inquiry is easily available. Registering research studies ensures that future scholars can quickly find out what work has been carried out on a given question, even if some or all of the work done never results in formal publication. Registration of studies is increasingly required by publishers and can be done before, during, or after the study with essential information about the study purpose. Some currently popular registries are operated by the AEA, 3ie, eGAP, and OSF. They all have different target audiences and features, so select one that is appropriate to your work. Study registration should be feasible for all projects, as registries are typically free to access and can be initially submitted with minimal information about the project. A generally-acceptable practice will be to gradually revise and expand the level of detail in a registration over time, adding more information as the planning for the project progresses.

Pre-registering studies before they begin is an extension of this principle. Registration of a study before it goes to implementation or data acquisition, particularly when specific hypotheses are included in the registration, provides a simple and low-effort way for researchers to conclusively demonstrate that a particular line of inquiry was not generated by the process of data collection or analysis itself. Pre-registrations need not provide exhaustive details about how a particular hypothesis will be approached; only that it will be. Pre-registering specific individual elements of research design or analysis can be highly valuable for the credibility of the research and requires only minor time investment or administrative effort. For this reason, the DIME team requires pre-registration of all studies in a public database with at least some primary hypotheses prespecified, prior to providing funding for impact evaluation research.

### Demand for Safe Spaces Case Study: Registering Research Studies

The experimental component of the Demand for Safe Spaces study was registered at the Registry for International Development Impact Evaluations (RIDIE) under ID 5a125fecae423.

Highlights from the Registry:

- Indicated evaluation method: both primary method (randomized control trial) and additional methods (difference-in-difference/fixed effects).

- Listed key outcome variables: take-up of rides in women-only car (binary), occurrence of harassment or crime during ride (binary), self-reported well-being after each ride, overall subjective well-being, Implicit Association Test D-Score

- Specified primary hypotheses to be tested: The women-only car reduces harassment experienced by women who ride it; Riding the women’s-only car improves psychological well-being of those who ride it; Women are willing to forego income to ride the women’s-only car

- Specified secondary research question and methods: supplementary research methods (implicit association test and platform survey) to help address an additional hypothesis: The women’s-only car is associated with a social norm that assigns responsibility to women for avoiding harassment.

- Provided sample size for each study arm: number of individual participants, number of baseline rides, number of rides during price experiment, number of car-assigned rides, number of expected participants in implicit association test

- *Described data sources: the study relied on data previously collected (through the mobile app) and data to-be-collected (through platform surveys and implicit association tests)

- Registration status: categorized as a non-prospective registry, as the crowdsourced data had already been received and processed. It was important to the team to ensure the credibility of additional data collection and secondary research questions by registering the study.

The RIDIE registry can be accessed at https://ridie.3ieimpact.org/index.php?r=search/detailView&id=588

### Writing pre-analysis plans

If a research team has a large amount of flexibility to define how they approach a particular hypothesis, study registration may not be sufficient to avoid the criticism of “hypothesizing after the results are known”, or HARKing. Examples of such flexibility include a broad range of concrete measures that could be argued to measure to an abstract concept; future choices about sample inclusion or exclusion; or decisions about how to construct derived indicators. There are a variety of templates and checklists of details to include. When the researcher is collecting a large amount of information and has leverage over even a moderate number of these options, it is almost guaranteed that they can come up with any result they like.

Pre-analysis plans (PAPs) can be used to assuage these concerns by specifying some set of analyses the researchers intend to conduct. The pre-analysis plan should be written up in detail for areas that are known to provide a large amount of leeway for researchers to make later decisions, particularly for things like interaction effects or subgroup analysis. Pre-analysis plans shoud not, however, be viewed as binding the researcher’s hands. Depending on what is known about the study at the time of writing, pre-analysis plans can vary widely in the amount of detail they should include. The core function of a PAP is to carefully and explicitly describe one or more specific data-driven inquiries, as specific formulations are often very hard to justify in retrospect with data or projects that potentially provide many avenues to approach a single theoretical question. Anything outside the original plan is just as interesting and valuable as it would have been if the plan was never published; but having pre-committed to the details of a particular inquiry makes its results immune to a wide range of criticisms of specification searching or multiple testing.

### Demand for Safe Spaces Case Study: Writing Pre-Analysis Plans

Although the Demand for Safe Spaces study did not publish a formal pre-analysis plan, the team published a concept note in 2015, which includes much of the same information as a typical pre-analysis plan. The Concept Note was updated in May 2017 to include new secondary research questions. The Concept Note, prepared before fieldwork began, was subject to review and approval within the World Bank and from a technical committee including blinded feedback from external academics. The Concept Note specified the planned study along the following dimensions:

- Theory of change: the main elements of the intervention, and the hypothesized causal chain from inputs, through activities and outputs, to outcomes.

- Hypotheses derived from the theory of change

- Main evaluation question(s) to be addressed by the study

- List of main outcomes of interest, including outcome name, definition, level of measurement

- Evaluation design, including a precise description of the identification strategy for each research questions and description of treatment and control groups

- Sampling strategy and sample size calculation, detailing the assumptions made

- Description of all quantitative data collection instruments

- Data processing and analysis: the statistical methods to be used, the exact specification(s) to be run, including clustering of standard errors; key groups for heterogeneity analysis; adjustments for multiple hypothesis testing; strategy to test (and correct) for bias.

A version of the study’s Concept Note is available at https://github.com/worldbank/rio-safe-space/blob/master/Online%20Appendices/Supplemental%20Material/Project%20Concept%20Note.pdf

### Publishing registered reports

Registered reports take the process of pre-specifying a complex research design to the level of a formal publication. In a registered report, a journal or other publisher will peer review and conditionally accept a specific study for publication, typically then guaranteeing the acceptance of a later publication that carries out the analysis described in the registered report. While far stricter and more complex to carry out than ordinary study registration or pre-analysis planning, the registered report has the added benefit of peer review and expert feedback on the design and structure of the proposed study. Registered reports are never required, but they are designed to reward researchers who are able to provide a large amount of advance detail for their projects, researchers who want to secure publication interest regardless of results, or researchers who want to use methods that may be novel or unusual.

This process is in part meant to combat the “file-drawer problem” and ensure that researchers are transparent in the sense that all promised results obtained from registered-report studies are actually published. This approach has the advantage of pre-specifying in great detail a complete research and analytical design, and securing a commitment for publication regardless of the outcome. This may be of special interest for researchers studying events or programs where either there is a substantial risk that they would either not be able to publish a null or negative result, or where they may wish to avoid any pressure toward finding a particular result, for example when the program or event is the subject of substantial social or political pressures. As with pre-registration and pre-analysis, nothing in a registered report should be understood to prevent a researcher from pursuing additional avenues of inquiry once the study is complete, either in the same or separate research outputs.

## Conducting research transparently

Transparent research exposes not only the code, but all research processes involved in developing the analytical approach. This means that readers are able to judge for themselves whether the research was done well and the decision-making process was sound. If the research is well-structured, and all of the relevant documentation is shared, it is easy for the reader to understand the analysis fully. Researchers that expect process transparency also have an incentive to make better decisions, be skeptical and thorough about their assumptions, and save themselves time, because transparent research methods are labor-saving over the complete course of a project.

Clearly documenting research work is necessary to allow others to evaluate exactly what data was acquired and how it was used to obtain a particular result. Many development research projects are purpose-built to address specific questions, and often use unique data, novel methods, or small samples. These approaches can yield new insights into essential academic questions, but need to be transparently documented so they can be reviewed or replicated by others in the future. Unlike disciplines where data is more standardized or where research is more oriented around secondary data, the exact data used in a development project has often not been observed by anyone else in the past and may not be able to be re-collected by others in the future. Regardless of the novelty of study data, transparent documentation methods help ensure that data was collected and handled appropriately and that studies and interventions were implemented correctly. As with study registrations, project and data documentation should be released on external archival repositories so they can always be accessed and verified.

### Documenting data acquisition and analysis

Documenting a project in detail greatly increases transparency. Many disciplines have a tradition of keeping a “lab notebook”, and adapting and expanding this process to create a lab-style workflow in the development field is a critical step towards more transparent practices. This means explicitly noting decisions as they are made, and explaining the process behind the decision-making. Careful documentation will also save the research team a lot of time during a project, as it prevents you from having the same discussion twice (or more!), since you have a record of why something was done in a particular way. There are a number of available tools that will contribute to producing documentation, but project documentation should always be an active and ongoing process, not a one-time requirement or retrospective task. New decisions are always being made as the plan begins contact with reality, and there is nothing wrong with sensible adaptation so long as it is recorded and disclosed.

Email, however, is not a documentation service, because communications are rarely well-ordered, can be easily deleted, and are not available for future team members. At the very least, emails and other decision-making communications need to be archived and preserved (as, say, PDFs) in an organized manner so that they can be easily accessed and read by others in the future. There are also various software solutions for building proper documentation over time. Some work better for field records such as implementation decisions, research design, and survey development; others work better for recording data work and code development. The Open Science Framework provides one such solution, with integrated file storage, version histories, and collaborative wiki pages. GitHub provides a transparent documentation system through commit messages, issues, README files, and pull requests, in addition to version histories and wiki pages. Such services offer multiple different ways to record the decision process leading to changes and additions, track and register discussions, and manage tasks. These are flexible tools that can be adapted to different team and project dynamics. Services that log your research process can show things like modifications made in response to referee comments, by having tagged version histories at each major revision. They also allow you to use issue trackers to document the research paths and questions you may have tried to answer as a resource to others who have similar questions. Each project has specific requirements for data, code, and documentation management, and the exact transparency tools to use will depend on the team’s needs, but they should be agreed upon prior to project launch. This way, you can start building a project’s documentation as soon as you start making decisions.

### Cataloging and archiving data

Data and data collection methods should be fully cataloged, archived, and documented, whether you are collecting data yourself or receiving it from an outside partner. In some cases this is as simple as uploading a survey instrument or an index of datasets and a codebook to an archive. In other cases this will be more complex. Proper documentation of data collection will often require a detailed description of the overall sampling procedure. For example, settings with many overlapping strata, treatment arms, excluded observations, or resampling protocols might require extensive additional field work documentation. This documentation should be continuously updated and kept with the other study materials; it is often necessary to collate these materials for an appendix for publication in any case.

When data is received from partners or collected in the field, the original data (including corrections) should be immediately placed in a secure permanent storage system. Before analytical work begins, you should create a “for-publication” copy of the original dataset by removing potentially identifying information. This will become the raw data, and must be placed in an archival repository where it can be cited. This can initially be done under embargo or with limited release, in order to protect your data and future work. This type of data depositing or archiving precedes publishing or releasing any data: data at this stage may still need to be embargoed or have other, potentially permanent, access restrictions, so you can instruct the archive to formally release the data later. If your planned analysis requires the use of unpublishable data, that data should always remain encrypted and be stored separately so it is clear what portions of the code will work with and without obtaining a license to the needed restricted-access data.

Some project funders provide specific repositories in which they require the deposit of data they funded, and you should take advantage of these when possible. If this is not provided, you must be aware of privacy issues with directly identifying data and questions of data ownership before uploading raw data to any third-party server, whether public or not; this is a legal question for your home organization. If data that is required for analysis must be placed under restricted use or restricted access, including data that can never be distributed directly by you to third parties, develop a plan for storing that data separately from publishable information. This will allow you to maximize transparency by having a clear release package as well as providing instructions or developing a protocol for allowing access in the future for replicators or reviewers under appropriate access agreements. Regardless of these consideration, all data repositories, such as DIME’s standard, the World Bank Microdata Library and the World Bank Data Catalog, should create a record of the data’s existence and provide instructions on how access might be obtained by another researcher. For more on the steps required to prepare and publish a de-identified dataset, you can refer to Chapter 6 and Chapter 7 of this book. Data publication should create a data citation and a digital object identifier (DOI), or some other persistent index that you can use in your future work to unambiguously indicate the location of your data. This data publication should also include the methodological documentation as well as complete human-readable codebooks for all the variables there.

## Analyzing data reproducibly

Reproducible research makes it easy for others to apply your techniques to new data or to implement a similar research design in a different context. Development research is rapidly moving in the direction of requiring adherence to specific reproducibility guidelines. Major publishers and funders, most notably the American Economic Association, have taken steps to require that code and data are accurately reported, cited, and preserved as research outputs that can be accessed and verified by others. Making research reproducible in this way is a public good. It enables other researchers to re-use code and processes to do their own work more easily and effectively in the future. Regardless of what is formally required, your code should be written neatly with clear instructions. It should be easy to read and understand. The corresponding analysis data should also be made accessible to the greatest legal and ethical extent that it can be.

Common research standards from journals and funders feature both regulation and verification policies. Regulation policies require that authors provide reproducibility packages before publication which are then reviewed by the journal for completeness. Verification policies require that authors make certain materials available to the public, but their completeness is not a precondition for publication. Other journals have adopted guidance that offer checklists for reporting on whether and how various practices were implemented, without specifically requiring any. If you are personally or professionally motivated by citations, producing these kinds of resources can lead to that as well. Even if privacy considerations mean you will not be publishing some or all data or results, these practices are still valuable for project organization.

Our recommendation, regardless of external requirements, is that your should prepare to release all data that can be published When data cannot be published, you should try to publish as much metadata as allowed, including information on how the data was obtained, what fields the data contains and aggregations or descriptive statistics. Even if the data cannot be published, it is rare for code files to contain restricted information, so the code should still be made available with clear instructions for obtaining usable data. Additionally, we recommend that reproducibility efforts be considered when designing the IRB and data licensing agreement for sensitive data, to establish acceptable conditions (such as a secure transfer or cold room) under which representatives from journals or other academics could access data may access the data for the purpose of independently reproducing results.

### Preparing a reproducibility package

At DIME, all research outputs are required to satisfy computational reproducibility, which is an increasingly common requirement for publication. Before releasing a working paper, the research team submits a reproducibility package with de-identified data, and DIME Analytics verifies that the package produces exactly the same results that appear in the paper. The team also comments on whether the package includes sufficient documentation. The Analytics team organizes frequent peer code review for works in progress, and our general recommendation is to ensure that projects are always externally reproducible instead of waiting until the final stages to prepare this material. Once the computational reproducibility check is complete, the team receives a completed reproducibility certificate that also lists any publicly available materials to accompany the package, for use as an appendix to the publication. The team also organizes regular peer code review for works in progress, and our general recommendation is to ensure that projects are always externally reproducible instead of waiting until the final stages to prepare this material. In this way, code is continuously maintained with clear documentation, and should be easy to read and understand in terms of structure, style, and syntax.

For research to be reproducible, all code files for data cleaning, construction and analysis should be public, unless they contain confidential information. Nobody should have to guess what exactly comprises a given index, or what controls are included in your main regression, or whether or not you clustered standard errors correctly. That is, as a purely technical matter, nobody should have to “just trust you”, nor should they have to bother you to find out what would happen if any or all of these things were to be done slightly differently. Letting people play around with your data and code is a great way to have new questions asked and answered based on the valuable work you have already done.

A reproducibility package should include the complete materials needed to exactly re-create your final analysis, and be accessible and well-documented so that others can identify and adjust potential decision points that they are interested in. They should be able to easily identify: what data was used and how that data can be accessed; what code generates each table, figure and in-text number; how key outcomes are constructed; and how all project results can be reproduced. This is important to plan ahead for, so that you can make sure you obtain the proper documentations and permissions for all data, code, and materials you use throughout the project. A well-organized reproducibility package usually takes the form of a complete directory structure, including documentation and a master script, that leads the reader through the process and rationale for the code behind each of the outputs when considered in combination with the corresponding publication.

### Demand for Safe Spaces Case Study: Preparing a Reproducibility Package

The Demand for Safe Spaces team published all final study materials to a repository on the World Bank’s GitHub account. The repository holds the abstract of the paper, ungated access to the most recent version of the full paper, an online appendix including robustness checks and supplemental material, and the project’s reproducibility package.

The data for this project is published in the Microdata Catalog, under the survey ID number BRA_2015-2016_DSS_v01_M. The Microdata catalog entry includes metadata on the study, documentation such as survey instruments and technical reports, terms of use for the data, and access to downloadable data files. Both the crowdsourced data and the platform survey data are accessible through the Microdata Catalog.

The “Reproducibility Package” folder on GitHub contains all the instructions for executing the code. Among other things, it provides licensing information for the materials, software and hardware requirements including time needed to run, and instructions for replicators (which are included below). Finally, it has a detailed list of the code files that will run, their data inputs, and the outputs of each process.

The Demand for Safe Space GitHub repository can be viewed at : https://github.com/worldbank/rio-safe-space

The Microdata Catalog entry for the study is available at https://microdata.worldbank.org/index.php/catalog/3745

## Looking ahead

With the ongoing rise of empirical research and increased public scrutiny of scientific evidence, making analysis code and data available is necessary but not sufficient to guarantee that findings will be credible. Even if your methods are highly precise, your evidence is only as good as your data – and there are plenty of mistakes that can be made between establishing a design and generating final results that would compromise its conclusions. That is why transparency is key for research credibility. It allows other researchers, and research consumers, to verify the steps to a conclusion by themselves, and decide whether their standards for accepting a finding as evidence are met. Every investment you make in documentation and transparency up front protects your project down the line, particularly as these standards continue to tighten. With these principles in mind, the approach we take to the development, structure, and documentation of data work provides a system to implementing these ideas in everyday work. In the next chapter, we will discuss the workspace you need in order to work reproducibly in an efficient, organized, and secure manner.

# Setting the stage for effective and efficient collaboration

In order to do effective data work in a team environment, you need to structure your workflow in advance. Preparation for collaborative data work begins long before you acquire any data, and involves planning both software tools and collaboration platforms for your team. This means knowing what types of data you’ll acquire, whether the data will require special handling due to size or privacy considerations, which datasets and outputs you will need at the end of the process, and how all data files and versions will stay organized throughout. It’s important to plan data workflows in advance because changing software or protocols halfway through a project is costly and time-consuming. Seemingly small decisions such as file-sharing services, folder structures, and filenames can be extremely painful to alter down the line in any project.

This chapter will guide you in setting up an effective environment for collaborative data work, structuring your data work to be well-organized and clearly documented, and setting up processes to handle confidential data securely. The first section outlines how to set up your working environment to effectively collaborate on technical tasks with others, and how to document tasks and decisions. The second section discusses how to organize your code and data so that others will be able to understand and interact with it easily. The third section provides guidelines for ensuring privacy and security when working with confidential data.

### Summary: Setting the stage for effective and efficient collaboration Summary

The technical environment for your data work needs to be established at the start of a research project. Agreeing with the team on software choices, standard code and data structure, and clear data security protocols will prepare you to successfully, safely, and efficiently implement technical tasks throughout the project lifecycle. Consider:

1. Technical collaboration environment. No matter the hardware and software your team plans to use, you should ensure now that it is standardized or interoperable across the team. This includes:

- Secure all physical computing hardware through encryption and password-protection. If specialized or more powerful hardware is required, initiate access requests, purchase orders, or other processes now

- Agree on tools for collaboration and documentation, such that key conversations and decisions are archived and organized outside of instant-message and email conversation

- Decide the programming languages and environments the team will use. Take time to set up a comfortable and modern digital work environment

2. Organization of code and data. The team should agree on where and how code files and databases will be stored, down to the level of the folder structure. This involves setting up:

- A standardized and scalable folder structure so all documents have an unambiguous location, and the location and naming of files describes their purpose and function and is intuitive to all team members

- A backup and version control system appropriate for each file type, to ensure information cannot be lost and that all team members understand how to interoperate and collaborate

- Master script files that will structure and execute the code base of the

3. Information security measures and ethical frameworks. These include:

- Formally request and obtain approval from legal entities governing research in all relevant jurisdictions

- Understand how to respect the rights and dignity of research subjects and plan for how to establish informed consent from individuals or groups participating in the research

- Adopt standardized digital security practices including proper encryption of all confidential information, at rest and in transit, both among your team and with external partners

#### Takeaways

TTLs/PIs will:

- Support the acquisition and maintenance of required computing hardware and software, liaising with procurement, information security and information technology teams as necessary

- Make final decisions regarding code languages and environments

- Discuss and agree upon an appropriate project-wide digital organization strategy

- Institute and communicate best practices in accordance with legal, ethical, and security obligations

RAs will:

- Communicate technical needs clearly with TTLs/PIs and relevant service providers

- Consistently implement digital organization strategy and flag issues with task management, documentation, or materials storage if they arise

- Support project compliance with ethical, legal, and security obligations and flag concerns to TTLs/PIs

#### Key Resources

- DIME Research Ethics Standards: Pillar 1 of the DIME Research Standards https://github.com/worldbank/dime-standards

- DIME GitHub Resources: https://github.com/worldbank/dime-github-trainings

- DIME Data Security Standards: Pillar 4 of the DIME Research Standards https://github.com/worldbank/dime-standards

- DIME Data Publication Standards: Pillar 5 of the DIME Research Standards https://github.com/worldbank/dime-standards

## Preparing a collaborative work environment

This section introduces core concepts and tools for organizing data work in an efficient, collaborative and reproducible manner. Some of these skills may seem elementary, but thinking about simple things from a workflow perspective can help you make marginal improvements every day you work; those add up to substantial gains over the course of multiple years and projects. Together, these processes form a collaborative workflow that will greatly accelerate your team’s ability to get tasks done on all your projects.

Teams often develop workflows in an ad hoc fashion, solving new challenges as they arise. Adaptation is good, of course. But it is important to recognize that there are a number of tasks that exist in common for every project, and it is more efficient to agree on the corresponding workflows in advance. For example, every project requires research documentation, organized file naming, directory organization, coding standards, version control, and code review. These tasks are common to almost every project, and their solutions translate well between projects. Therefore, there are large efficiency gains to thinking in advance about the best way to do these tasks, instead of throwing together a solution when the task arises. This section outlines the main points to discuss within the team, and suggests best practice solutions for these tasks.

### Demand for Safe Spaces Case Study: Preparing a Collaborative Work Environment

Here are a few highlights of how the Demand for Safe Spaces team chose to organize their work environment for effective collaboration:

- The data work for the project was done through a private GitHub repository housed in the World Bank organization account.

- GitHub issues were used to document research decisions and to provide feedback. Even the PIs for the study, who did not directly participate in coding, used Github issues to review code and outputs and to create a record of broader discussions.

- Stata was adopted as the primary software for data analysis, as that is the software all team members had in common at the start of the project. At a later stage of the project, R code was developed specifically to create maps. The R portion of the code was developed independently, as it used different datasets and created separate outputs. The team used two separate master scripts, one for the Stata code base and one for the R code.

- The team members shared a synchronized folder (using Dropbox), which included the de-identified data and project documentation such as survey instruments and enumerator training manuals.

### Setting up your computer

First things first: almost all your data work will be done on your computer, so make sure it’s set up for success. The operating system should be fully updated, it should be in good working order, and you should have a password-protected login. However, password-protection is not sufficient if your computer stores data that is not public. You would need to use encryption for sufficient protection, which will be covered later in this chapter. Make sure your computer is backed up to prevent information loss. Follow the 3-2-1 rule: maintain 3 copies of all original or irreplaceable data, on at least 2 different hardware devices you have access to, with 1 offsite storage method. Chapter 4 provides a protocol for implementing this.

Ensure you know how to get the absolute file path for any given file. On MacOS this will be something like “/users/username/git/project/...” and “C:/users/username/git/project/...” on Windows. Absolute file paths will be an obstacle to collaboration unless they are dynamic absolute file paths. In a dynamic absolute file path the relative project path, “/git/project/...” in the examples above, is added to the user-specific root path for each user, “/users/username” or “C:/users/username” in the examples above, generating an absolute file path unique to each user. Master scripts introduced later in this chapter will show how this can be seamlessly implemented. Dynamic absolute file paths, starting from the file system root, is the best way to ensure that files are read and written correctly when multiple users work on the same project across many different platforms, operative systems and devices. There are contexts, for example some cloud environments, where relative file paths must be used, but in all other contexts we recommend you to always use dynamic absolute file paths.

Use forward slashes (/) in file paths for folders, and whenever possible use only the 26 English characters, numbers, dashes (-), and underscores (_) in folder names and filenames. For emphasis: always use forward slashes (/) in file paths in code, just like in internet addresses. Do this even if you are using a Windows machine where both forward and backward slashes are allowed, as your code will otherwise break if anyone tries to run it on a Mac or Linux machine. Making the structure of your directories a core part of your workflow is very important, since otherwise you will not be able to reliably transfer the instructions for replicating or carrying out your analytical work.

When you are working with others, you will most likely be using some kind of file sharing software.  The exact services you use will depend on your tasks, but in general, there are several approaches to file sharing, and the three discussed here are the most common. File syncing is the most familiar method, and is implemented by software like OneDrive, Dropbox, or Box. Sync forces everyone to have the same version of every file at the same time, which makes simultaneous editing difficult but other tasks easier. Distributed version control is another method, commonly implemented through systems like GitHub, GitLab, and Bitbucket that interact with Git.  Distributed version control allows everyone to access different versions of files at the same time. It is only optimized for specific types of files (for example, any type of code files). Finally, server storage is the least-common method, because there is only one version of the materials, and simultaneous access must be carefully regulated.  Server storage ensures that everyone has access to exactly the same files and environment, and it also enables high-powered computing processes for large and complex data.

All three file sharing methods are used for collaborative workflows, and you should review the types of data work that you will be doing, and plan which types of files will live in which types of sharing services. It is important to note that they are, in general, not interoperable, meaning you should not have version-controlled files inside a syncing service, or vice versa, without setting up complex workarounds, and you cannot shift files between them without losing historical information. Therefore, choosing the correct sharing service for each of your team’s needs at the outset is essential. At DIME we typically use file syncing for all project administrative files and data, version control in Git for code, and server storage for backup and/or large scale computations when needed.

### Establishing effective documentation practices

Once your technical and sharing workspace is set up, you need to decide how you are going to communicate with your team. The first habit that many teams need to break is using instant communication for management and documentation. Email is, simply put, not a system. It is not a system for anything. Neither is instant messaging apps like WhatsApp. Instant messaging tools are developed for communicating “now” and that is what they do well. They are not structured to manage group membership or to present the same information across a group of people, or to remind you when old information becomes relevant. They are not structured to allow people to collaborate over a long time or to review old discussions. It is therefore easy to miss or lose communications from the past when they have relevance in the present. Everything with future relevance that is communicated over email or any other instant medium – such as, for example, decisions about research design – should immediately be recorded in a system that is designed to keep permanent records. We call these systems collaboration tools, and there are several that are very useful.

Good collaboration tools are workflow-oriented systems that allow the team to create and assign tasks, carry out discussions related to single tasks, track task progress across time, and quickly see the overall project status. They are web-based so that everyone on your team can access them simultaneously and have ongoing discussions about tasks and processes. Such systems link communications to specific tasks so that related decisions are permanently recorded and easy to find in the future when questions about that task come up. Choosing the right tool for your team’s needs is essential to designing an effective workflow. What is important is that your team chooses a system and commits to using it, so that decisions, discussions, and tasks are easily reviewable long after they are completed.

Some popular and free collaboration tools that meet these criteria are GitHub and Dropbox Paper. Any specific list of software will quickly be outdated; we mention these as examples that have worked for our team. Different collaboration tools can be used different types of tasks. Our team, for example, uses GitHub for code-related tasks, and Dropbox Paper for more managerial tasks. GitHub creates incentives for writing down why changes were made in response to specific discussions as they are completed, creating naturally documented code. It is useful also because tasks in GitHub Issues can clearly be tied to file versions. On the other hand, Dropbox Paper provides a clean interface with task notifications, assignments, and deadlines, and is very intuitive for people with non-technical backgrounds. Therefore, it is a useful tool for managing non-code-related tasks.

### Setting up your code environment

Taking time early in your project to choose a programming language to work in and setting up a productive code environment for that language will make your work significantly easier.  Setting up a productive code environment means to make sure that the programming language and all other software your code requires will run smoothly on all the hardware you need it to run on. It also means that you have a productive way of interacting with code, and that the code has a seamless method to access your data.

It is difficult and costly to switch programming languages halfway through a project, so think ahead about the various software your team will use. Take into account the technical abilities of team members, what type of internet access the software will need, the type of data you will need to access, and the level of security required. Big datasets require additional infrastructure and may overburden the tools commonly used for small datasets. Also consider the cost of licenses, the time to learn new tools, and the stability of the tools. There are few strictly right or wrong choices for software, but what is important is that you plan in advance and understand how the chosen tools will interact with your workflows.

One option is to hold your code environment constant over the lifecycle of a single project. While this means you will inevitably have different projects with different code environments, each successive project will be better than the last, and you will avoid the costly process of migrating an ongoing project into a new code environment. Code environments should be documented as precisely as possible. The specific version number of the programming languages and the individual packages you use should be referenced or maintained so that they can be reproduced going forward, even if different releases contain changes that would break your code or change your results.  DIME Analytics developed the command ieboilstart in the ietoolkit package to support version and settings stability in Stata. If your project requires more than one programming language, for example if you analyze your data in one language but visualize your results in another, then make sure to make an as clear division between the two as possible. This means that you first complete all tasks done in one language, before the completing the rest of the tasks in the other language. Frequently swapping back and forth between languages is a reproducibility nightmare.

Next, think about how and where you write and execute code. This book is intended to be agnostic to the size or origin of your data, but we are going to broadly assume that you are using one of the two most popular statistical software packages: R or Stata. (If you are using another language, like Python, many of the same principles apply but the specifics will be different.) Most of your code work will be done in a code editor. If you are working in R, RStudio is the typical choice. For Stata, the built-in do-file editor is the most widely adopted code editor. You might also consider using an external editor for your R or Stata code. These editors offer great accessibility and quality features. For example, they can access an entire directory – rather than a single file – which gives you directory-level views and file management actions, such as folder management, Git integration, and simultaneous work with other types of files, without leaving the editor. Using an external editor can also be preferable since your editor will not crash if the execution of your code causes your statistical software to crash. Finally, you can often use the same editor for all programming languages you use, so any customization you do in your code editor of choice will improve your productivity across all your coding work.

## Organizing code and data for replicable research

We assume you are going to do your analytical work through code, and that you want all your processes to be documented and replicable. Though it is possible to interact with some statistical software through the user interface without writing any code, we strongly advise against it. Writing code creates a record of every task you performed. It also prevents direct interaction with the data files that could lead to non-reproducible steps. You may do some exploratory tasks by point-and-click or typing directly into the console, but anything that is included in a research output must be coded in an organized fashion so that you can release the exact code that produces your final results – up to and including individual statistics in text. Still, organizing code and data into files and folders is not a trivial task. What is intuitive to one person rarely comes naturally to another, and searching for files and folders is everybody’s least favorite task. As often as not, you come up with the wrong one, and then it becomes very easy to create problems that require complex resolutions later. This section provides basic tips on managing the folder that stores your project’s data work.

Maintaining an organized file structure for data work is the best way to ensure that you, your teammates, and others are able to easily edit and replicate your work in the future. It also ensures that automated processes from code and scripting tools are able to interact well with your work, whether they are yours or those of others. File organization makes data work easier as well as more transparent, and facilitates integration with tools like version control systems that aim to cut down on the amount of repeated tasks you have to perform. It is worth thinking in advance about how to store, name, and organize the different types of files you will be working with, so that there is no confusion down the line and everyone has the same expectations.

### Organizing files and folders

Once you start a research project, the number of scripts, datasets, and outputs that you have to manage will grow very quickly. This can get out of hand just as quickly, so it’s important to organize your data work and follow best practices from the beginning. You should agree with your team on a specific directory structure, and set it up at the beginning of the project. You should also agree on a file naming convention. This will help you to easily find project files and ensure that all team members can easily run the same code.

To support consistent folder organization at DIME, DIME Analytics created iefolder as a part of our ietoolkit package. This Stata command sets up a pre-standardized folder structure for what we call the DataWork folder. The DataWork folder includes folders for all the steps of a typical project.  Since each project will always have unique needs, we have tried to make the structure easy to adapt. Having a universally standardized folder structure across the entire portfolio of projects means that everyone can easily move between projects without having to reorient on file and folder organization.

If you do not already have a standard file structure across projects, iefolder is an easy template to start from. The command creates a DataWork folder at the project level, and within that folder, creates standardized directory structures for each data source or survey round. Within each subdirectory, iefolder creates folders for raw encrypted data, raw deidentified data, cleaned data, final data, outputs, and documentation. It creates a parallel folder structure for the code files that move the data through this progression, and for the final analytical outputs. The ietoolkit package also includes the iegitaddmd command, which can place README.md placeholder files in your folders so that your folder structure can be shared using Git. Since these placeholder files are written in a plaintext language called Markdown, they also provide an easy way to document the contents of every folder in the structure.

The DataWork folder may be created either inside an existing project folder, or it may be created as a separate root folder. We advise keeping project management materials (such as contracts, terms of reference, briefs and other administrative or management work) separate from the DataWork folder structure. It is useful to maintain project management materials in a sync system like Dropbox, whereas the code folder should be maintained in a version-control system like Git. However, a version-controlled folder should never be stored in a synced folder that is shared with other people. Combining these two types of collaboration tools almost always creates undesired functionalities.

### Demand for Safe Spaces Case Study: Organizing Files and Folders

The diagram below illustrates the folder structure for the Demand for Safe Spaces data work. Note that this project started before the iefolder structured was created, and so differs from the current guidelines. Changing folder organization midway through a project is never recommended. The key feature of folder organization is planning ahead and agreeing with the whole team on the best structure to follow.

The root folder for the study’s data work included two master scripts (one for Stata and one R, that can be run independently), a readme, and 4 subfolders: data, code, documentation and outputs. The folder structure was identical in GitHub and DropBox, but the files present in each of them differed. All code, raw outputs (such as TeX table fragments and PNG images) and plain text documentation were stored in GitHub. All the datasets, PDF outputs and documentation in Word and Excel were stored in DropBox. When data processing was completed, binary files in the Documentation folder that were accessed by the code, such as iecodebook and ieduplicates spreadsheets, were moved to GitHub to ensure completeness of the repository.

### Establishing common file formats

Each task in the research workflow has specific inputs and outputs which feed into one another. It is common, particularly when different tasks are performed by different people inside a team, for incompatibilities to be created. For example, if the Principal Investigators are writing a paper using LaTeX, exporting tables from statistical software into a .csv format will break the workflow. Therefore, it’s important to agree with your team on what tools will be used for what tasks, and where inputs and outputs will be stored, before you start creating them. Take into account ease of use for different team members, and keep in mind that learning how to use a new tool may require some time investment upfront that will be paid off as your project advances.

Knowing how code outputs will be used will help you decide the best format to export them. You can typically use the same software to save figures into various formats, such as .eps},.png,.pdfor.jpg`. However, the decision between using Office Suite software such as Word and PowerPoint versus LaTeX and other plain text formats may influence how you write your code, as this choice often implicates in the use of a particular format. This decision will also affect the version control systems that your team can use.

### Using version control

We recommend using a version control system to maintain control of file history and functionality. A good version control system tracks who edited each file and when, allows you to revert to previous versions, and provides a protocol for ensuring that conflicting versions are avoided. This is important, for example, for your team to be able to find the version of a presentation that you delivered to a donor, or to understand why the significance level of your estimates has changed. Everyone who has ever encountered a file named something like final_report_v5_LJK_KLE_jun15.docx can appreciate how useful such a system can be.

Most syncing services offer some kind of rudimentary version control; these are usually enough to manage changes to binary files (such as office documents) without needing to rely on dreaded filename-based versioning conventions. For code files, however, a more detailed version control system is usually desirable. We recommend using Git for version-control of all data work. Git documents changes to all plaintext files. Plaintext files include all code files, most raw outputs, and written outputs that use code languages, such as LaTeX files and many dynamic documents. Git tracks all the changes you make to each plaintext file, and allows you to go back to previous versions without losing the information on changes made. It also makes it possible to work on multiple parallel versions of a file, so you don’t risk breaking code for other team members as you try something new.

### Writing code that others can read

Good code is written in a way that is easily understood and run by others. Below we discuss a few crucial steps to code organization. They all come from the principle that code is an output by itself, not just a means to an end, and should be written thinking of how easy it will be for someone to read it later. At the end of this section, we include a template for a master script do-file in Stata, to provide a concrete example of the required elements and structure. Throughout this section, we refer to lines of this example do-file to give concrete examples of the required code elements, organization and structure.

To be readable, code must be well-documented. Start by adding a code header to every file. A code header is a long comment that details the functionality of the entire script; refer to lines 5-10 in the example do-file. This should include simple things such as the purpose of the script and the name of the person who wrote it. If you are using a version control software, the last time a modification was made and the person who made it will be recorded by that software. Otherwise, you should include it in the header. You should always track the inputs and outputs of the script, as well as the uniquely identifying variable; refer to lines 52-54 in the example do-file. When you are trying to track down which code creates which dataset, this will be very helpful. While there are other ways to document decisions related to creating code, the information that is relevant to understand the code should always be written in the code file.

Two types of comments should be included in the script itself. The first type of comment describes what is being done. This might be easy to understand from the code itself if you know the language well enough and the code is clear, but often it is still a great deal of work to reverse-engineer the code’s intent. Describing the task in plain English (or whichever language you use to communicate with your team) will make it easier for everyone to read and understand the code’s purpose. It can also help you organize your own work and ensure you are following logical steps. The second type of comment explains why the code is performing a task in a particular way. As you are writing code, you are making a series of decisions that (hopefully) make perfect sense to you at the time. These are often highly specialized and may exploit a functionality that is not obvious or has not been seen by others before. Well-commented code is in itself a great way to document your data work which someone can follow to understand anything from data cleaning decisions that make the published data differ from the original data to decisions on how indicators are constructed. Even you will probably not remember the exact choices that were made in a couple of weeks. Therefore, you must document your precise processes in your code.

Code files should be stored in an easy-to-find location and named in a meaningful way.  Breaking your code into independently readable “chunks” is good practice for code organization. You should write each functional element as a chunk that can run completely on its own. This ensures that each code component is independent; it does not rely on a complex program state created by other code chunks that are not obvious from the immediate context. One way to do this is by creating sections in your script to identify where a specific task is completed. For example, if you want to find the line in your code where the directory is set, you can go straight to “PART 2: Prepare folder paths and define programs”, instead of reading line by line through the entire code.

RStudio makes it very easy to create sections, and it compiles them into an interactive script index for you. In Stata, you can use comments to create section headers (see line 27 of the example do-file), though they’re just there to make the reading easier and don’t have functionality. Since an index is not automated, create this manually in the code header by copying and pasting section titles (see lines 8-10 in the example do-file). You can then add and navigate through them using the find functionality. Since Stata code is harder to navigate, as you will need to scroll through the document, it’s particularly important to avoid writing very long scripts. Therefore, in Stata at least, we recommend breaking code tasks down into separate do-files, since there is no limit on how many you can have, how detailed their names can be, and no advantage to writing longer files. One reasonable rule of thumb is to not write do-files that have more than 200 lines. This is an arbitrary limit, just like the common practice of limiting code lines to 80 characters: it seems to be “enough but not too much” for most purposes.

### Demand for Safe Spaces Case Study: Writing Code That Others Can Read

To ensure that all team members were able to easily read and understand data work, Demand for Safe Spaces code files were extensively commented. Comments typically took the form of “what – why”: what is this section of code doing, and why is it necessary. The below snippet from a do-file cleaning one of the raw data files illustrates the use of comments:

The full code file is available at https://git.io/Jtgev

### Writing code that others can run

To bring all these smaller code files together, you must maintain a master script.  A master script is the map of all your project’s data work which serves as a table of contents for the instructions that you code. Anyone should be able to follow and reproduce all your work from raw data to all outputs by simply running this single script. By follow, we mean someone external to the project who has the master script and all the input data can (i) run all the code and recreate all outputs, (ii) have a general understanding of what is being done at every step, and (iii) see how codes and outputs are related. The master script is also where all the settings are established, such as versions, folder paths, functions, and constants used throughout the project.

/*******************************************************************************
*                           TEMPLATE MASTER DO-FILE                            *
********************************************************************************
*                                                                              *
*   PURPOSE:     Reproduce all data work, map inputs and outputs,              *
*                facilitate collaboration                                      *
*                                                                              *
*   OUTLINE:     PART 1:  Set standard settings and install packages           *
*                PART 2:  Prepare folder paths and define programs             *
*                PART 3:  Run do-files                                         *
*                                                                              *
********************************************************************************
  PART 1:  Install user-written packages and harmonize settings
********************************************************************************/

    local user_commands ietoolkit iefieldkit //Add required user-written commands
    foreach command of local user_commands {
        cap which `command'
        if _rc == 111 ssc install `command'
    }

    *Harmonize settings across users as much as possible
    ieboilstart, v(13.1)
    `r(version)'

/*******************************************************************************
  PART 2:  Prepare folder paths and define programs
*******************************************************************************/

    * Research Assistant folder paths
    if "`c(username)'" == "ResearchAssistant" {
        global github      "C:/Users/RA/Documents/GitHub/d4di/DataWork"
        global dropbox     "C:/Users/RA/Dropbox/d4di/DataWork"
        global encrypted   "M:/DataWork/EncryptedData"
    }

    * Baseline folder globals
    global bl_encrypt       "${encrypted}/Round Baseline Encrypted"
    global bl_dt            "${dropbox}/Baseline/DataSets"
    global bl_doc           "${dropbox}/Baseline/Documentation"
    global bl_do            "${github}/Baseline/Dofiles"
    global bl_out           "${github}/Baseline/Output"

/*******************************************************************************
  PART 3: Run do-files
*******************************************************************************/

/*------------------------------------------------------------------------------
    PART 3.1:  De-identify baseline data
    REQUIRES:   ${bl_encrypt}/Raw Identified Data/D4DI_baseline_raw_identified.dta
    CREATES:    ${bl_dt}/Raw Deidentified/D4DI_baseline_raw_deidentified.dta
    IDS VAR:    hhid
----------------------------------------------------------------------------- */
    *Change the 0 to 1 to run the baseline de-identification dofile
    if (0) do "${bl_do}/Cleaning/deidentify.do"

/*------------------------------------------------------------------------------
    PART 3.2:  Clean baseline data
    REQUIRES:   ${bl_dt}/Raw Deidentified/D4DI_baseline_raw_deidentified.dta
    CREATES:    ${bl_dt}/Final/D4DI_baseline_clean.dta
                ${bl_doc}/Codebook baseline.xlsx
    IDS VAR:    hhid
----------------------------------------------------------------------------- */
    *Change the 0 to 1 to run the baseline cleaning dofile
    if (0) do "${bl_do}/Cleaning/cleaning.do"

/*-----------------------------------------------------------------------------
    PART 3.3:  Construct income indicators
    REQUIRES:   ${bl_dt}/Final/D4DI_baseline_clean.dta
    CREATES:    ${bl_out}/Raw/D4DI_baseline_income_distribution.png
                ${bl_dt}/Intermediate/D4DI_baseline_constructed_income.dta
    IDS VAR:    hhid
----------------------------------------------------------------------------- */
    *Change the 0 to 1 to run the baseline variable construction dofile
    if (0) do "${bl_do}/Construct/construct_income.do"

Try to create the habit of running your code from the master script. Creating “section switches” using macros or objects to run only the codes related to a certain task should always be preferred to manually open different scripts to run them in a certain order (see the if (0) switches in Part 3 of stata-master-dofile.do for one way of how to do this). Furthermore, running all scripts related to a particular task through the master whenever one of them is edited helps you identify unintended consequences of the changes you made. Say, for example, that you changed the name of a variable created in one script. This may break another script that refers to this variable. But unless you run both of them when the change is made, it may take time for that to happen, and when it does, it may take time for you to understand what’s causing an error. The same applies to changes in datasets and results.

To link code, data and outputs, the master script reflects the structure of the DataWork folder in code through globals (in Stata) or string scalars (in R); refer to lines 38-43 of the example do-file. These coding shortcuts can refer to subfolders, so that those folders can be referenced without repeatedly writing out their absolute file paths. Because the DataWork folder is shared by the whole team, its structure is the same in each team member’s computer. The only difference between machines should be the path to the project root folders, i.e. the highest-level shared folder. Depending on your software environment you may have multiple root folders. In a typical DIME project we have one Git root folder for our code, one sync software root folder for our de-identified data, and a third for our encrypted data. This is reflected in the master script in such a way that the only change necessary to run the entire code for a new team member is to change the path to the project root folders to reflect the file system and username; refer to lines 30-35 of the example do-file. The code in stata-master-dofile.do shows how folder structure is reflected in a master do-file. Because writing and maintaining a master script can be challenging as a project grows, an important feature of the iefolder is to write sub-master do-files and add to them whenever new subfolders are created in the DataWork folder.

In order to maintain well-documented and organized code, you should agree with your team on a plan to review code as it is written.  Reading other people’s code is the best way to improve your coding skills. And having another set of eyes on your code will make you more comfortable with the results you find. It’s normal (and common) to make mistakes as you write your code. Reading it again to organize and comment it as you prepare it to be reviewed will help you identify them. Try to have a code review scheduled frequently, every time you finish writing a piece of code, or complete a small task. If you wait for a long time to have your code reviewed, and it gets too complex, preparation and code review will require more time and work, and that is usually the reason why this step is skipped. One other important advantage of code review is that making sure that the code is running properly on other machines, and that other people can read and understand the code easily, is the easiest way to be prepared in advance for a smooth project handover or for release of the code to the general public.

### Demand for Safe Spaces Case Study: Writing Code That Others Can Run

All code for the Demand for Safe Spaces study was organized to run from two master scripts, one Stata Master and one R Master. The master scripts were written such that any team member could run all project code by simply changing the top-level directory. Below is a snippet of the Stata Master:

The complete Stata master script can be found at https://git.io/JtgeT, and the R master at https://git.io/JtgeY.

## Preparing to handle confidential data ethically

Anytime you are working with original data in a development research project, you are almost certainly handling data that include personally-identifying information (PII). PII is information which can, without any transformation or linkage, be used to identify individual people, households, firms, (or other units) in your data. Some examples of PII variables include names, addresses, and geolocations, email addresses, phone numbers, and bank accounts or other financial details. If you are working in a context or population that is either small, specific, or has extensive linkable data sources available to others, information like someone’s age and gender may be sufficient to disclose their identify, even though those variables would not be considered PII in general.

In a collaborative project, you will sometimes need to transfer and work with PII information, and sometimes you will prefer to remove or mask PII before transferring or working with data. There is no one-size-fits-all solution to determine what is PII, research teams have to use careful judgment in each case to avoid statistical disclosure.  It is important to keep in mind that data privacy principles apply not only for the respondent giving you the information but also for their household members or other individuals who are included in the data.

In all cases where confidential information is involved, you must make sure that you adhere to several core principles. These include ethical approval, participant consent, data security, and participant privacy. If you are a US-based researcher, you will become familiar with a set of governance standards known as “The Common Rule.” If you interact with European institutions or persons, you will also become familiar with the General Data Protection Regulation (GDPR), a set of regulations governing data ownership and privacy standards. No matter who you are or what exact legal requirements you face, the core principles and practices you need to consider will always be similar.

### Seeking ethical approval

Most of the field research done in development involves human subjects.  As a researcher, you are asking people to trust you with personal information about themselves: where they live, how rich they are, whether they have committed or been victims of crimes, their names, their national identity numbers, and all sorts of other data. PII data carries strict expectations about data storage and handling, and it is the responsibility of the research team to satisfy these expectations. Your donor or employer will most likely require you to hold a certification from a respected source.

For almost all such data collection and research activities, you will be required to complete some form of Institutional Review Board (IRB) process.  Most commonly this consists of a formal application for approval of a specific protocol for consent, data collection, and data handling. Which IRB has authority over your project is not always apparent, particularly if some institutions do not have their own. It is customary to obtain an approval from a university IRB where at least one PI is affiliated, and if work is being done in an international setting, approval is often also required from an appropriate local institution subject to the laws of the country where data originates.

IRB approval should be obtained well before any data is acquired. IRBs may have infrequent meeting schedules or require several rounds of review for an application to be approved. If there are any deviations from an approved plan or expected adjustments, report these as early as possible so that you can update or revise the protocol. IRBs have the authority to retroactively deny the right to use data which was not acquired in accordance with an approved plan. This is extremely rare, but shows the seriousness of these considerations since the institution itself may face legal penalties if its IRB is unable to enforce them. As always, as long as you work in good faith, you should not have any issues complying with these regulations.

### Demand for Safe Spaces Example – Seeking Ethical Approval

The Duke University IRB reviewed and approved the protocol for all components of fieldwork for the Demand for Safe Spaces study (IRB number D0190). As one of the PIs was at Duke, and the World Bank does not have an IRB, Duke was the relevant institution in this case. The study was registered with the Duke IRB on September 2015. It was amended 4 times to reflect additions to the study design, such as an implicit association test (IAT) and a new survey. The IRB approval was renewed twice, in 2016 and 2017. Highlights from the study IRB protocols:

- Voluntary study participation: The study intervention was done through a smartphone application. Through the app, users were offered payment to complete a set of tasks while using the metro. The tasks involved answering questions at different moments of the trip (before boarding the train, during the ride, after leaving the train). At the start of each task, participants could review what it comprised and the exact payment value, then decide whether to accept the task or not. There was no obligation to complete any task.

- Survey instruments: translated drafts of all survey instruments were shared with the IRB

- Privacy protection: the intervention was done specialized mobile application developed by a partner technology company, which recruited users through social media. User data from the app was encrypted and stored in AWS. As per the user agreement, access to the raw data was restricted to employees of the tech company, using VPN and encrypted laptops. The tech company processed the raw data and released non-identifying data to the researchers, plus household coordinates (study participants provided informed consent to share this data).

- Risk: Participants were tasked with riding the public transport system in Rio De Janeiro. There is some general risk inherent in travel around Rio de Janeiro. However, the public transport system is widely used, and participants are expected to be those who regularly travel on the train. The assigned task may cause them to travel on a different route or at a different time than usual. Tasks are assigned around rush hour, so stations and trains will be crowded, which is expected to reduce risks. Note that half the riders on the system are women, and only a small fraction of the cars are reserved for women, so the task of riding the regular carriage will not require users to go into an all-male environment.

- Ethical obligation: when completing an assigned task, participants were asked whether they experienced any harassment. If harassment was reported, the app directed the participant to the platform guards to whom she could report harassment incidences (the guards are trained to respond to harassment reports), as well as to other resources available in the Rio area.

Appendix C in the working paper discusses the ethics aspects of the study, including participant recruitment, informed consent and how reports of harassment were addressed: https://openknowledge.worldbank.org/handle/10986/33853

### Obtaining informed consent

One primary consideration of IRBs is the protection of the people about whom information is being collected and whose lives may be affected by the research design. Some jurisdictions (especially those who governed by EU law) view all personal data as intrinsically owned by the persons who they describe. This means that those persons have the right to refuse to participate in data collection before it happens, as it is happening, or after it has already happened. It also means that they must explicitly and affirmatively consent to the collection, storage, and use of their information for any purpose.

The development of appropriate consent processes is of primary importance. All survey instruments must include a module in which the sampled respondent grants informed consent to participate. Research participants must be informed of the purpose of the research, what their participation will entail in terms of duration and any procedures, any foreseeable benefits or risks, and how their identity will be protected. There are special additional protections in place for vulnerable populations, such as minors, prisoners, and people with disabilities, and these should be confirmed with relevant authorities if your research includes them.

### Demand for Safe Spaces Case Study: Obtaining Informed Consent

Participation in both the study intervention (assignments to take a specific Supervia ride) and the platform survey were fully voluntary, and both included informed consent. Per the informed consent protocols for the study intervention, participation in each assigned task was voluntary, and participants were paid for each ride they completed shortly after completion, regardless of the total number of rides they completed. Thus, participants could choose to stop participating at any time if they felt uncomfortable.

The consent statement participants were shown was the following:

“If you choose to do this task, you will have to go to a Supervia station, ride the train, and answer questions about your experience on the train. You will have to ride the train for ___ minutes, and answering the questions will take about ten minutes. You will be paid at least ____ reais for the task, and possibly more. You will be able to review the payment for each task and option before deciding whether to do that task. You can choose during the task whether to ride either the women’s-only or the mixed carriage on the Supervia. Your responses to the task will not be identified in any way with you personally. The anonymous data will be shared with researchers at Duke University in the United States. You can choose to stop the task at any time. To get paid for this task, however, you have to finish the task.”

The sentence in italics was removed for the portion of the data collection in which participants were assigned to ride in a particular type of car; the rest of the consent statement applied to all tasks.

### Ensuring research subject privacy

In order to safeguard PII data and protect respondent privacy, you must set up a data protection protocol from the outset of a project. Secure data storage and transfer are ultimately your personal responsibility. Later chapters will discuss how to properly protect your data depending on which method you are using to acquire, store or share data. This section will only cover the computer setup you will need for any project. There are several components to this.

First, you need a system for managing strong and unique passwords for all accounts – including personal accounts like computer logins and email. This means that all your passwords should be long, not use common words and should not be reused for multiple accounts. The only way to make that practically feasible is to use a password manager. Most password managers also allow you to securely share passwords for shared accounts with your colleagues. Multi-factor authentication (sometimes called 2-step verification) is a secure alternative to passwords when available.

Second, machines that stores confidential data should not be connected to insecure physical or wireless networks, and when it is necessary to do so, they should use a VPN to connect to the internet. Furthermore, USB drives and other devices connecting over USB cables should not be connected to machines storing confidential data unless you know where the USB device came from and who has used it before you. Machines with confidential data should also be stored in a secure location when not in use.

Third, all confidential data must be encrypted at all times.  When files are properly encrypted, the information they contain will be completely unreadable and unusable even if they were to be intercepted by a malicious “intruder” (an information-security term for any unauthorized information access) or accidentally made public. We will discuss implementations of encryption in more detail specific to different stages of data work in Chapter 4, but when setting up a software environment for you and your team, make sure that you have a solution for all parts of your workflow on all team members computers. You can encrypt your data at the disk (hard drive) level, called full disk encryption (FDE), or at the individual file or folder level, called file system encryption (FSE). When possible both should be applied, but our recommendation is that project teams set up data protection protocols using file system encryption as the main type of protection, and require all members that handle confidential data to use it.

Most implementations of FDE use your computer login password to prevent your files from ever being read by anyone but you. It is important to note that password protection alone is not sufficient. Password protection makes it more difficult for someone else to gain access to your files, but only encryption properly protects your data if someone manages to access your files anyway. Whenever FDE is available in your operating system it should always be enabled. FDE protects your data when encrypted just as well as FSE, but we recommend FSE due to the following disadvantages of FDE. First, FDE is implemented differently in different operating systems making it difficult to create useful instructions for all computer set-ups team members may use. Second, when FDE decrypts your disk, then all data on that disk is decrypted, even files you do not need to use at that time. Since most FDE systems automatically decrypt your full disk each time you log in, a malicious intruder that has gained access to your computer would have access to all your files. Third and perhaps most important, FDE cannot be used when sharing confidential data over insecure channels like file syncing services or email. So FDE would anyways have to be complimented with some other type of protection during collaboration.

When using FSE, instead of encrypting a full disk or drive, you create encrypted folders in which you can securely store confidential data. These encrypted folders protect your data when they are stored on your computer but can also be used to securely transfer data over insecure channels like file syncing services and email. Encrypted folders in FSE are only decrypted when you need that specific folder to be decrypted. That means that a malicious intruder that has gained access to your computer only gains access to the folders you have decrypted while your computer was compromised. Folders you rarely or never decrypt therefore remain protected even if someone gains access to your computer. DIME uses VeraCrypt for FSE, and our protocols are available as part of the DIME Research Standards. VeraCrypt is free of charge and available for Windows, MacOS, and Linux. While some details are different across platforms, the encryption will be implemented the same way for all team members.

Regardless of whether you use full disk encryption or file system encryption, it is important to remember that encryption provides no protection when your data is decrypted. Therefore, you should always log out from your computer when you are not using it, and only keep folders with confidential data decrypted when you need exactly those files. The latter is only possible when you are using FSE.

Handling confidential data properly will always add to your workload. The easiest way to reduce that work load is to handle it as rarely as possible. Whenever our research design allows us to, we should not work with confidential data at all, and not collect it or ask for it in the first place. Even when we do need confidential data for some aspect of our research, it is almost never the case that we need it for all aspects of our data. It is often very simple to conduct planning and analytical work using a subset of the data that does not include this type of information.  Therefore we recommend that all projects plan a workflow with a version of the data where confidential data has been removed and always use that dataset when possible.

Note that it is in practice impossible to anonymize data. There is always some statistical chance that an individual’s identity will be re-linked to the data collected about them – even if that data has had all directly identifying information removed – by using some other data that becomes identifying when analyzed together. For this reason, we recommend de-identification in two stages. The initial de-identification process strips the data of direct identifiers as early in the process as possible, to create a working de-identified dataset that can be shared within the research team without the need for encryption. This data set should always be used when possible. The final de-identification process involves making a decision about the trade-off between risk of disclosure and utility of the data before publicly releasing a dataset.

Finally, it is essential to have an end-of-life plan for data even before it is acquired. This includes plans for how to transfer access and control to a new person joining the team, and how to revoke that access when someone is leaving the team. It should also include a plan for how the confidential data should be deleted. Every project should have a clear data retention and destruction plan. After a project is completed and its de-identified data has been made available as a part of data publication, research teams should not retain confidential data indefinitely.

### Demand for Safe Spaces Example: Ensuring Research Subject Privacy

The Demand for Safe Spaces team adopted the following data security protocols:

- All confidential data was stored in a World Bank OneDrive folder The World Bank One Drive has been set up by WB IT to be more secure than regular OneDrive and is the recommended institutional solution for storing confidential data.

- Access to the confidential data was limited to the Research Analyst and the Research Assistant working on the data cleaning.

- All de-identified data used for the analysis was stored in the synchronized folder shared by the full research team (in this case, using Dropbox).

- Indirect identifiers such as demographic variables and labels to train lines and stations were removed from the data before it was published to the Microdata Catalog.

## Looking ahead

With your code environment established, you will have a firm idea about how you are going to handle the data and code that you receive and create throughout the research process. This structure should prepare you to work collaboratively, to share code and data across machines and among team members, and to document your work as a group. With an organization plan and plans to to version-control and back up files, you are ready to handle materials ethically and securely. You should also have secured the approvals needed for any planned work. You are now ready to translate your project’s research design into a measurement framework to answer your research questions. In the next chapter, we will outline how to prepare the essential elements of research data. You will learn how to map out your project’s data needs according to both the research design and the planned creation and use of data across the project timeline.

# Establishing a measurement framework

The first step in the data workflow is to establish a measurement framework. This requires understanding your project’s data requirements and how to structure the required data to answer the research questions. Setting up the measurement framework involves more than simply listing the key outcome variables. You also need to understand how to structure original data, to determine how different data sources connect together, and to create tools to document these decisions and communicate them to the full research team. In this chapter we will show how to develop this framework, and hope to convince you that planning in advance both saves time and increases research quality.

The first section of this chapter introduces the DIME Data Map Template. The template includes a data linkage table, master datasets, and data flowcharts. These tools are used to communicate the project’s data requirements across the team and over time. The second section discusses how to translate your project’s research design into data needs. It provides examples on the specific data required by common impact evaluation research designs, and how to document the linkage between research design and data sources in our data map template. The final section links the measurement framework to the reproducibility and credibility pillars introduced in Chapter 1. It covers how to reproducibly generate research design variables and how to user power calculations and randomization inference to assess credibility.

## Documenting data needs

Most projects require more than one data source to answer a research question. These could be data from multiple survey rounds, data acquired from different partners (such as administrative data, implementation data, sensor data), technological tools like satellite imagery or web scraping, or complex combinations of these and other sources. However your study data is structured, you need to know how to link data from all sources and analyze the relationships between units to answer your research questions. You might think that you are able to keep all the relevant details in your head, but the whole research team is unlikely to have the same understanding, over the whole lifecycle of the project, of the relationship between all required datasets. To make sure that the full team shares the same understanding, we recommend creating a data map. The purpose of the data map is to make sure that you have all data that you need to answer the research questions in your research design, well before starting the analysis process described in Chapter 6. It is also useful documentation for the project. The process of drafting the data map is a useful opportunity for principal investigators to communicate their vision of the data structure and requirements, and for research assistants to communicate their understanding of that vision. Our recommended best practice is that the data map is completed before any data is acquired and that it is made a part of the pre-registration of the study. However, in practice many research projects evolve as new data sources, observations, and research questions arise, and then it is important that each component of the Data Map is continuously maintained and updated.

DIME’s data map template has three components: one data linkage table, one or several master datasets and one or several data flowcharts. The data linkage table lists all the raw datasets that will be used in the project, what data sources they are created from, and how they relate to each other. For each unit of observation in the data linkage table, as well for each unit of analysis you plan to use, you will create and maintain a master dataset, listing all observations of that unit relevant to the project. Finally, using these two resources you will create data flowcharts, describing how the raw datasets and master datasets are to be combined and manipulated to create analysis datasets. Each component will be discussed in more detail below.

In order to map measurement frameworks into data needs, we find it helpful to distinguish between two types of variables: variables that tie your research design to the observations in the data, which we call research design variables; and variables that correspond to observations of the real world, which we call measurement variables. Research design variables map information about your research subjects to the research design. Often, these variables have no meaning outside the research project, for example ID variables and treatment status. Others will be observations from the real world, but only those that determines how each specific research unit should be handled during the analysis, for example treatment uptake and eligibility status. Measurement variables, on the other hand, are real world measures that are not determined by the research team. Examples include characteristics of the research subject, outcomes of interest, and control variables among many others.

### Developing a data linkage table

To create a data map according to DIME’s template, the first step is to create a data linkage table by listing all the data sources you know you will use in a spreadsheet, and the raw datasets that will be created from them. If one source of data will result in two different raw datasets, then list each dataset on its own row. For each dataset, list the unit of observation and the name of the project ID variable for that unit of observation. It is important to include both plain-language terminology as well as technical file and variable names here. For example, the hh_baseline2020_listmap.csv dataset may be called the “Baseline Household Listing” data; it may be identified by the hh_id variable and said to be identified at the “Household” level. Having the plain-language terminology here early in the project allows you to use these titles unambiguously in communication.

The data linkage table will therefore help you plan out how you will identify each unit of observation in your data. When you list a dataset in the data linkage table – which should be done before that data source is acquired – you should make sure that the data will be fully and uniquely identified by the project ID, or make a plan for how the new dataset will be linked to the project ID. It is very labor-intensive to work with a dataset that does not have an unambiguous way to link to the project ID, and it is a major source of error.

The data linkage table should indicate whether datasets can be merged one-to-one (for example, merging baseline and endline datasets that use the same unit of observation), or whether two datasets need to be merged many-to-one (for example, school administrative data merged with student data). Your data map must indicate which ID variables can be used – and how – when merging datasets. The data linkage table is also a great place to list other metadata, such as the source of your data, its backup locations, the nature of the data license, and so on.

### Constructing master datasets

The second step in creating a data map is to create one master dataset for each unit of observation that will be used in any research activity. Examples of such activities are data collection, data analysis, sampling, and treatment assignment. The master dataset is the authoritative source of the project ID and all research design variables for the corresponding unit of observation, such as sample status and treatment assignment. Therefore, the master dataset serves as an unambiguous method of mapping the observations in the data to the research design. A master dataset should not include any measurement variables. Research design variables and measurement variables may come from the same source, but should not be stored in the same way. For example, if you acquire administrative data that both includes information on eligibility for the study (research design variables) and data on the topic of your study (measurement variables), the data should be processed such that research design variables are stored in the master dataset, while measurement variables should be stored separately and prepared for analysis as described in Chapter 5.

Each master dataset is to be the authoritative source for how all observations at that unit of analysis are identified. This means that the master datasets should include identifying information such as names, contact information, and the project ID. The project ID is the ID variable used in the data linkage table, and is therefore how observations are linked across datasets. Your master dataset may list alternative IDs that are used, for example, by a partner organization. However, you must not use such an ID as your project ID, as you would then not be in control over who can re-identify data. The project ID must be created by the project team, and the linkage to direct identifiers should only be known to people listed on the IRB. Your master dataset serves as the linkage between all other identifying information and your project ID. Since your master dataset is full of identifying information, it must always be encrypted. If you receive a dataset with an alternative ID, you should replace it with your project ID as a part of de-identification (see Chapter 5 and Chapter 7 for more on de-identification). The alternative ID should be stored in your master dataset so it may be linked back to your data using the project ID if ever needed. Any dataset that needs to retain an alternative ID for any reason should be treated as confidential data; it should always be encrypted and never published.

The starting point for the master dataset is typically a sampling frame (more on sampling frames later in this chapter). However, you should continuously update the master dataset with all observations ever encountered in your project, even if those observations are not eligible for the study. Examples include new observations listed during monitoring activities or observations that are connected to respondents in the study, for example in a social network module. This is useful because, if you ever need to perform a record linkage such as a fuzzy match on string variables like proper names, the more information you have the fewer errors you are likely to make. If you ever need to do a fuzzy match, you should always do that between the master dataset and the dataset without an unambiguous identifier. You should not begin data cleaning or analysis until you have successfully merged the project IDs from the master dataset. When adding new observations to the master datasets, always convince yourself beyond reasonable doubt that the new observation is indeed a new observation. Sometimes you will encounter different spellings in identifiers and identifiers such as addresses may become outdated.

### Creating data flowcharts

The third and final step in creating the data map is to create data flowcharts. Each analysis dataset (see Chapter 6 for discussion on why you likely need multiple analysis datasets) should have a data flowchart showing how it was created. The flowchart is a diagram where each starting point is either a master dataset or a dataset listed in the data linkage table. The data flowchart should include instructions on how the datasets can be combined to create the analysis dataset. The operations used to combine the data could include: appending, one-to-one merging, many-to-one or one-to-many merging, collapsing, or a broad variety of others. You must list which variable or set of variables should be used in each operation, and note whether the operation creates a new variable or combination of variables to identify the newly linked data. Datasets should be linked by project IDs when possible (exceptions are time variables in longitudinal data, and sub-units like farm plots that belong to farmers with project IDs). Once you have acquired the datasets listed in the flowchart, you can add to the data flowcharts the number of observations that the starting point dataset has and the number of observation each resulting datasets should have after each operation. This is a great method to track attrition and to make sure that the operations used to combine datasets did not create unwanted duplicates or incorrectly drop any observations.

The information that goes into the data flowcharts can be expressed in text, but our experience is that diagrams are the most efficient way to communicate this information across a team. A data flowchart can be created in a flowchart drawing tool (there are many free alternatives online) or by using the shapes or SmartArt tools in, for example, Microsoft Office. You can also do this simply by drawing on a piece of paper and taking a photo, but we recommend a digital tool so that flowcharts can easily be updated over time if needed. As with the data linkage table, you should include both technical information and plain-language interpretations of the operations that are done and the data that is created. These will help readers understand the complex data combinations that often result from merges and appends, such as panel datasets like “person-year” structures and multi-level data like “district-school-teacher-student” structures.

## Translating research design to data needs

An important step in translating the research design to specific data structure is to determine which research design variables you will need in the data analysis to infer what differences in measurement variables are attributable to your research design. These data needs should be expressed in your data map by listing the data source for each variable in the data linkage table, by adding columns for them in your master dataset (the master dataset might not have any observations yet; that is not a problem), and by indicating in your data flowcharts how they will be merged to the analysis data. It is important you do this before acquiring any data, to make sure that the data acquisition activities described in chapter 4 will generate the data needed to answer your research questions.

As DIME primarily works on impact evaluations, we focus our discussion here on research designs that compare a group that received some kind of treatment against a counterfactual. The key assumption is that each person, facility, or village (or whatever the unit of treatment is) had two possible states: their outcome if they did receive the treatment and their outcome if they did not receive that treatment. The average impact of the treatment, is defined as the difference between these two states averaged over all units.

However, we can never observe the same unit in both the treated and untreated state simultaneously, so we cannot calculate these differences directly. Instead, the treatment group is compared to a control group that is statistically indistinguishable, which is often referred to as achieving balance between two or more groups. DIME Analytics maintains a Stata command to standardize and automate the creation of well-formatted balance tables: iebaltab. Each research design has a different method for identifying and balancing the counterfactual group. The rest of this section covers how research data requirements differ between those different methods. What does not differ, however, is that these data requirements are all research design variables. And that the research design variables discussed below should always be included in the master dataset. You will often have to merge the research design variables to other datasets, but that is an easy task if you created a data linkage table.

We assume you have a working familiarity with the research designs mentioned here. You should reference our Research Design Appendix, where you will find more details and specific references for common impact evaluation designs.

### Applying common research designs to data

In experimental research designs, such as randomized control trials (RCTs),  the research team determines which members of the studied population will receive the treatment. This is typically done by a randomized process in which a subset of the eligible population is randomly assigned to receive the treatment (see later in this chapter for how to implement this). The intuition is that if everyone in the eligible population is assigned at random to either the treatment or control group, then the two groups will, on average, be statistically indistinguishable. Randomization makes it generally possible to obtain unbiased estimates of the effects that can be attributed to a specific program or intervention: in a randomized trial, the expected spurious correlation between treatment and outcomes will approach zero as the sample size increases. The randomized assignment should be done using data from the master dataset, and the result should be saved back to the master dataset, before being merged to other datasets.

Quasi-experimental research designs,  by contrast, are based on events not controlled by the research team. Instead, they rely on “experiments of nature”, in which natural variation in exposure to treatment can be argued to approximate deliberate randomization. You must have a way to measure this natural variation, and how the variation is categorized as outcomes of a naturally randomized assignment must be documented in your master dataset. Unlike carefully planned experimental designs, quasi-experimental designs typically require the luck of having access to data collected at the right times and places to exploit events that occurred in the past. Therefore, these methods often use either secondary data, including administrative data or other classes of routinely-collected information, and it is important that your data linkage table documents how this data can be linked to the rest of the data in your project.

No matter the design type, you should be very clear about which data points you observe or collect are research design variables. For example, regression discontinuity (RD)  designs exploit sharp breaks or limits in policy designs. The cutoff determinant, or running variable, should be saved in your master dataset. In instrumental variables (IV)  designs, the instruments influence the probability of treatment. These research design variables should be collected and stored in the master dataset. Both the running variable in RD designs and the instruments in IV designs, are among the rare examples of research design variables that may vary over time. In such cases your research design should ex-ante clearly indicate what point of time they will be recorded, and this should be clearly documented in your master dataset.

In matching designs, observations are often grouped by a strata, grouping, index, or propensity score. Like all research design variables, the matching results should be stored in the master dataset. This is best done by assigning a matching ID to each matched pair or group, and create a variable in the master dataset with the matching ID each unit belongs to. In all these designs, fidelity to the design is important to record as well. A program intended for students that scored under 50% on a test might have some cases where the program is offered to someone that scored 51% at the test, or someone that scored 49% at the might decline to participate in the program. Differences between assignments and realizations should also be recorded in the master datasets.

### Including multiple time periods

Your data map should also take into consideration whether your project uses data from one time period or several. A study that observes data in only one time period is called a cross-sectional study. Observations over multiple time periods, referred to as longitudinal data, can consist of either repeated cross-sections or panel data. In repeated cross-sections, each successive round of data collection uses a new random sample of observations from the treatment and control groups, but in a panel data study the same observations are tracked and included each round. If each round of data collection is a separate activity, then they should be treated as separate sources of data and get their own row in the data linkage table.

If the data is generated continuously, or acquired at frequent intervals, then it can be treated as a single data source. When panel data is acquired in discreet batches, the data linkage table must document how the different rounds will be merged or appended. You must keep track of the attrition rate in panel data, which is the share of observations not observed in follow-up data. It is common that the observations not possible to track can be correlated with the outcome you study. For example, poorer households may live in more informal dwellings, patients with worse health conditions might not survive to follow-up, and so on. If this is the case, then your results might only be an effect of your remaining sample being a subset of the original sample that were better or worse off from the beginning. You should have a variable in your master dataset that indicates attrition. A balance check using the attrition variable can provide insights as to whether the lost observations were systematically different compared to the rest of the sample.

### Incorporating monitoring data

For any study with an ex-ante design, monitoring data^[ More details on monitoring data can be found on the DIME Wiki: https://dimewiki.worldbank.org/Administrative_and_Monitoring_Data#Monitoring_Data}} is very important for understanding if the research design corresponds to reality. The most typical example is to make sure that, in an experimental design, the treatment was implemented according to your treatment assignment. Treatment implementation is often carried out by partners, and field realities may be more complex than foreseen during research design. Furthermore, the field staff of your partner organization, might not be aware that their actions are the implementation of a research design.

Therefore, you must acquire monitoring data that tells you how well the realized treatment implementation in the field corresponds to your intended treatment assignment, for nearly all experimental research designs. While monitoring data has traditionally been collected by sending someone to the field , it is increasingly common to collect monitoring data remotely. Some examples of remote monitoring include: local collaborators uploading geotagged images for visible interventions (such as physical infrastructure), installing sensors to broadcast measurements (such as air pollution or waterflow), distributing wearable devices to track location or physical activity (such as fitbits), or applying image recognition to satellite data. In-person monitoring activities are often preferred but cost and travel dangers, such as conflicts or disease outbreaks, make remote monitoring innovations increasingly appealing. If cost alone is the constraint, consider sampling a subset of the implementation area to monitor in-person. This may not be detailed enough to be used as a control in your analysis, but it will still provide a means to estimate the validity of your research design assumptions.

Linking monitoring data to the rest of the data in your project is often complex and a major source of errors. Monitoring data is rarely received in the same format or structure as your research data. For example, you may receive a list of the names of all people who attended a training, or administrative data from a partner organization without a proper identifier. In both those cases it can be difficult to ensure a one-to-one match between units in the monitoring data and the master datasets. Planning ahead, and collaborating closely with the implementing organization from the outset of the project, is the best way to avoid these difficulties. Often, it is ideal for the research team to prepare forms (paper or electronic) for monitoring, preloading with names of sampled individuals, or ensuring that there is a consistent identifier that is directly linkable to the project ID. If monitoring data is not handled carefully, you risk ending up with poor correlation between treatment uptake and treatment assignment, without a way to tell if the poor correlation is just a result of poor matching of the monitoring data or a meaningful implementation problem.

## Creating research design variables by randomization

Random sampling and random treatment assignment are two core research activities that generate important research design variables. Random sampling and random treatment assignment directly determine the set of individuals who will be observed and what their status will be for the purpose of effect estimation. Randomization is used to ensure that a sample is representative and that treatment groups are statistically indistinguishable.

Randomization in statistical software is non-trivial and its mechanics are unintuitive for the human brain. The principles of randomization we will outline apply not just to random sampling and random assignment, but to all statistical computing processes that have random components such as simulations and bootstrapping. Furthermore, all random processes introduce statistical noise or uncertainty into estimates of effect sizes. Choosing one random sample from all the possibilities produces some probability of choosing a group of units that are not, in fact, representative. Similarly, choosing one random assignment produces some probability of creating groups that are not good counterfactuals. Power calculation and randomization inference are the main methods by which these probabilities of error are assessed. These analyses are particularly important in the initial phases of development research – typically conducted before any data acquisition or field work occurs – and have implications for feasibility, planning, and budgeting.

### Randomizing sampling and treatment assignment

Sampling is the process of randomly selecting observations from a list of individuals to create a representative or statistically similar sub-sample. This process can be used, for example, to select a subset from all eligible units to be included in data collection when the cost of collecting data on everyone is prohibitive. But it can also be used to select a sub-sample of your observations to test a computationally heavy process before running it on the full data. Randomized treatment assignment is the process of assigning observations to different treatment arms. This process is central to experimental research design. Most of the code processes used for randomized assignment are the same as those used for sampling, since it is also a process of randomly splitting a list of observations into groups. Where sampling determines whether a particular individual will be observed at all in the course of data collection, randomized assignment determines if each individual will be observed as a treatment observation or used as a counterfactual.

The list of units to sample or assign from may be called a sampling universe, a listing frame, or something similar. The starting point for randomized sampling or assignment should be a master dataset in almost all cases, and the result of the randomized process should always be saved in the master dataset before it is merged to any other data. Example of exceptions when this cannot start from a master dataset are: sampling done in real time, such as randomly sampling patients as they arrive at a health facility, and treatment assignment done through an in-person lottery. In those cases, it is important that you collect enough data during the real time sampling, or take care to prepare the inputs for the lottery such that you can add these individuals to your master dataset afterwards.

The simplest form of sampling is uniform-probability random sampling. This means that every eligible observation in the master dataset has an equal probability of being selected. The most explicit method of implementing this process is to assign random numbers to all your potential observations, order them by the number they are assigned, and mark as “sampled” those with the lowest numbers, up to the desired proportion. There are a number of shortcuts to doing this process, but they all use this method as the starting point, so you should become familiar with exactly how it works. The do-file below provides an example of how to implement uniform-probability sampling in practice. This code uses a Stata built-in dataset and is fully reproducible (more on reproducible randomization in next section), so anyone that runs this code in any version of Stata later than 13.1 (the version set in this code) will get the exact same, but still random, results.

Sampling typically has only two possible outcomes: observed and unobserved. Similarly, a simple randomized assignment has two outcomes: treatment and control, and the logic in the code would be identical to the sampling code example. However, randomized assignment often involves multiple treatment arms which each represent different varieties of treatments to be delivered; in some cases, multiple treatment arms are intended to overlap in the same sample. Complexity can therefore grow very quickly in randomized assignment and it is doubly important to fully understand the conceptual process that is described in the experimental design, and fill in any gaps before implementing it in code. The do-file below provides an example of how to implement a randomized assignment with multiple treatment arms.

### Programming reproducible random processes

For statistical programming to be reproducible, you must be able to re-obtain its exact outputs in the future. We will focus on what you need to do to produce truly random results for your project, to ensure you can get those results again. This takes a combination of strict rules, solid understanding, and careful programming. This section introduces strict rules: these are non-negotiable (but thankfully simple). Stata, like most statistical software, uses a pseudo-random number generator which, in ordinary research use, produces sequences of number that are as good as random. However, for reproducible randomization, we need two additional properties: we need to be able to fix the sequence of numbers generated and we need to ensure that the first number is independently randomized. In Stata, this is accomplished through three concepts: versioning, sorting, and seeding. We again use Stata in our examples, but the same principles translate to all other programming languages.

Rule 1: Versioning requires using the same version of the software each time you run the random process. If anything is different, the underlying list of random numbers may have changed, and it may be impossible to recover the original result. In Stata, the version command ensures that the list of random numbers is fixed. The ieboilstart command in ietoolkit provides functionality to support this requirement. We recommend you use ieboilstart at the beginning of your master do-file. Note that testing your do-files without running them via the master do-file may produce different results, since Stata’s version setting expires after each time you run your do-files.

Rule 2: Sorting requires that the order of the actual data that the random process is run on is fixed. Because random numbers are assigned to each observation row-by-row starting from the top row, changing their order will change the result of the process. In Stata, we recommend using isid [id_variable], sort to guarantee a unique sorting order. This command does two things. First it tests that all observations have unique values in the sort variable, as duplicates would cause an ambiguous sort order. If all values are unique, then the command sorts on this variable guaranteeing a unique sort order. It is a common misconception that the sort, stable command may also be used, but by itself it cannot guarantee an unambiguous sort order and is therefore not appropriate for this purpose. Since the exact order must be unchanged, the underlying data itself must be unchanged as well between runs. This means that if you expect the number of observations to change (for example to increase during ongoing data collection), your randomization will not be reproducible unless you split your data up into smaller fixed datasets where the number of observations does not change. You can combine all those smaller datasets after your randomization.

Rule 3: Seeding requires manually setting the start point in the list of pseudo-random numbers. A seed is just a single number that specifies one of the possible start points. It should be at least six digits long and you should use exactly one unique, different, and randomly created seed per randomization process. In Stata, set seed [seed] will set the generator to the start point identified by the seed. In R, the set.seed function does the same. To be clear: you should not set a single seed once in the master do-file, but instead you should set a new seed in code right before each random process. The most important thing is that each of these seeds is truly random, so do not use shortcuts such as the current date or a seed you have used before. You should also describe in your code how the seed was selected.

% testing randomization reproducibility You must carefully confirm exactly how your code runs before finalizing it, as other commands may induce randomness in the data, change the sorting order, or alter the place of the random generator without you realizing it. To confirm that a randomization has worked correctly before finalizing its results, save the outputs of the process in a temporary location, re-run the code, and use cf or datasignature to ensure nothing has changed. It is also advisable to let someone else reproduce your randomization results on their machine to remove any doubt that your results are reproducible. Once the result of a randomization is used in the field, there is no way to correct any mistakes. The code below provides an example of a fully reproducible randomization.

As discussed above, at times it will not be possible to use a master dataset for randomized sampling or treatment assignment (examples were sampling patients on arrival or live lotteries). In addition to presenting challenges with matching, these methods typically do not leave a record of the randomization, and as such are never reproducible. However, you can often run your randomization in advance even when you do not have list of eligible units in advance. Let’s say you want to, at various health facilities, randomly select a sub-sample of patients as they arrive. You can then have a pre-generated list with a random order of “in sample” and “not in sample”. Your field staff would then go through this list in order and cross off one randomized result as it is used for a patient.

This is especially beneficial if you are implementing a more complex randomization. For example, a hypothetical research design may call for enumerators to: (1) sample 10% of people observed in a particular location; (2) show a video to 50% of the sample; (3) administer a short questionnaire to 80% of all those sampled and (4) administer a longer questionnaire to the remaining 20%, with the questionnaire mix equal between those who were shown the video and those that were not. In real-time, such a complex randomization is much more likely to be implemented correctly if your field staff simply can follow a list with the randomized categories where you are in control of the pre-determined proportions and the random order. This way, you can also control with precision how these categories are evenly distributed across all the locations where you plan to conduct this research.

Finally, if this real-time randomization implementation is done using survey software, then the pre-generated list of randomized categories can be preloaded into the questionnaire. Then the field team can follow a list of respondent IDs that are randomized into the appropriate categories, and the survey software can show a video and control which version of the questionnaire is asked. This way, you reduce the risk of errors in field randomization.

### Implementing clustered or stratified designs

% the cases discussed so far are the most simple, but not the most common For a variety of reasons, random sampling and random treatment assignment are rarely as straightforward as a uniform-probability draw. The most common variants are clustering and stratification. Clustering occurs when your unit of analysis is different than the unit of sampling or treatment assignment. For example, a policy may be implemented at the village level, or you may only be able to send enumerators to a limited number of villages, or the outcomes of interest for the study are measured at the household level.  The groups in which units are assigned to treatment are called clusters.

Stratification breaks the full set of observations into subgroups before performing randomized assignment within each subgroup.  The subgroups are called strata. This ensures that members of every subgroup are included in all groups of the randomized assignment process, or that members of all groups are observed in the sample. Without stratification, it is possible that the randomization would put all the members of a subgroup into just one of the treatment arms, or fail to select any of them into the sample. For both clustering and stratification, implementation is nearly identical in both random sampling and random assignment.

Clustering is procedurally straightforward in Stata, although it typically needs to be performed manually. To cluster a sampling or randomized assignment, randomize on the master dataset for the unit of observation of the cluster, and then merge the results to the master dataset for the unit of analysis. This is a many-to-one merge and your data map should document how those datasets can be merged correctly. If you do not have a master dataset yet for the unit of observation of the cluster, then you first have to create that and update your data map accordingly. When sampling or randomized assignment is conducted using clusters, the clustering variable should be clearly identified in the master dataset for the unit of analysis since it will need to be used in subsequent statistical analysis. Namely, standard errors for these types of designs must be clustered at the level at which the randomization was clustered. This accounts for the design covariance within the cluster – the information that if one individual was observed or treated there, the other members of the clustering group were as well.

Although procedurally straightforward, implementing stratified designs in statistical software is prone to error. Even for a simple multi-armed design, the basic method of randomly ordering the observations will often create very skewed assignments. The user-written randtreat command properly implements stratification. The options and outputs (including messages) from the command should be carefully reviewed so that you understand exactly what has been implemented. Notably, it is extremely hard to target precise numbers of observations in stratified designs, because exact allocations are rarely round fractions and the process of assigning the leftover “misfit” observations imposes an additional layer of randomization above the specified division.

### Performing power calculations

Random sampling and treatment assignment are noisy processes: it is impossible to predict the result in advance. By design, we know that the exact choice of sample or treatment will be uncorrelated with our key outcomes, but this lack of correlation is only true “in expectation” – that is, the noise component of the correlation between randomization and outcome will only be zero on average across a large number of randomized trials. In any particular randomization, the correlation between the sampling or randomized assignments and the outcome variable is guaranteed to be nonzero: this is called the in-sample or finite-sample correlation.

Since we know that the true correlation (over the “population” of potential samples or randomized assignments) is zero, we think of the observed correlation as an error. In sampling, we call this the sampling error, and it is defined as the difference between a true population parameter and the observed mean due to chance selection of units. In randomized assignment, we call this the randomization noise, and define it as the difference between a true treatment effect and the estimated effect due to placing units in groups. The intuition for both measures is that from any group, you can find some possible subsets that have higher-than-average values of some measure; similarly, you can find some that have lower-than-average values. Your random sample or treatment assignment will fall in one of these categories, and we need to assess the likelihood and magnitude of this occurrence. Power calculation and randomization inference are the two key tools to doing so.

Power calculations report the likelihood that your experimental design  will be able to detect the treatment effects you are interested in given these sources of noise. This measure of power can be described in various different ways, each of which has different practical uses. The purpose of power calculations is to identify where the strengths and weaknesses of your design are located, so you know the relative tradeoffs you will face by changing your randomization scheme for the final design. It is important to consider take-up rates and attrition when doing power calculations; incomplete take-up will significantly reduce power, understanding what minimum level of take-up is required can help guide field operations (for this reason, monitoring take-up in real-time is often critical).

The minimum detectable effect (MDE) is the smallest true effect that a given research design can reliably detect. This is useful as a check on whether a study is worthwhile. If, in your field, a “large” effect is just a few percentage points or a small fraction of a standard deviation, then it is nonsensical to run a study whose MDE is much larger than that. This is because, given the sample size and variation in the population, the effect needs to be much larger to possibly be statistically detected, so such a study would never be able to say anything about the effect size that is practically relevant. Conversely, the minimum sample size pre-specifies expected effect sizes and tells you how large a study’s sample would need to be to detect that effect, which can tell you what resources you would need to implement a useful study.

Randomization inference is used to analyze the likelihood  that the randomized assignment process, by chance, would have created a false treatment effect as large as the one you estimated. Randomization inference is a generalization of placebo tests, because it considers what the estimated results would have been from a randomized assignment that did not in fact happen in reality. Randomization inference is particularly important in quasi-experimental designs and in small samples, where the number of possible randomizations is itself small. Randomization inference can therefore be used proactively during experimental design, to examine the potential spurious treatment effects your exact design is able to produce. If there is significant heaping at particular result levels, or if results seem to depend dramatically on the outcomes for a small number of individuals, randomization inference will flag those issues before the experiment is fielded and allow adjustments to the design to be made.

## Looking ahead

This chapter introduced the DIME Data Map template, a toolkit to documents your data acquisition plan and how each data source relates to the design of your study. The data map contains research design variables and the instructions for using them in combination with measurement variables, which together will form the dataset(s) for your analytical work. We then discussed ways for you to use this planning data to inform and execute research design tasks, such as randomized sampling and assignment, and to produce concrete measures of whether the project design is sufficient to answer the research questions you pose. In the next chapter, we will turn to the first step in actually answering those questions – data acquisition. The next chapter will detail the processes of obtaining original data, whether you are collecting it yourself or receiving it from another entity.

# Acquiring development data

Many research questions require the team to acquire original data, because no source of publicly available data addresses the inputs or outcomes of interest for the relevant population. Data acquisition can take many forms, including: primary data generated through surveys; private sector partnerships granting access to new data sources, such as administrative and sensor data; digitization of paper records, including administrative data; web scraping; primary data capture by unmanned aerial vehicles or other types of remote sensing; or novel integration of various types of datasets, such as combining survey and sensor data. Much of the recent push toward credibility in the social sciences has focused on analytical practices. However, credible development research depends, first and foremost, on the quality of the acquired data. Clear and careful documentation of the data acquisition process is essential for research reproducibility.

This chapter covers reproducible data acquisition, special considerations for generating high-quality survey data, and protocols for safely and securely handling confidential data. The first section discusses reproducible data acquisition: how to establish and document your right to use the data. This applies to all original data, whether collected for the first time through surveys or sensors or acquired through a unique partnership. The second section goes into detail on data acquisition through surveys, as this process is typically more involved than acquisition of secondary data, and has more in-built opportunities for quality control. It provides detailed guidance on the electronic survey workflow, from designing electronic survey instruments to monitoring data quality once fieldwork is ongoing. The final section discusses safe data handling, providing guidance on how to receive, transfer, store, and share confidential data. Secure file management is a basic requirement to comply with the legal and ethical agreements that allow access to personal information for research purposes.

## Acquiring data ethically and reproducibly

Clearly establishing and documenting data access is critical for reproducible research. This section provides guidelines for establishing data ownership, receiving data from development partners, and documenting the research team’s right to use the data. It is the researchers’ responsibility to respect the rights of people who own the data and the people who are described by it; but also to make sure that information is as available and accessible as possible. These twin responsibilities can and do come into tension, so it is important to be fully informed about what other researchers are doing and to fully inform other researchers of what you are doing. Writing down and agreeing to specific details is a good way of doing that.

### Determining data ownership

Before acquiring any data, it is critical to establish data ownership. Data ownership can sometimes be challenging to establish, as various jurisdictions have differing laws regarding data and information, and the research team may have their own information regulations. In some, data is implicitly owned by the people who it is about. In others, it is owned by the people who collected it. In still more, it is highly unclear and there are varying norms. The best approach is always to consult with a local partner, and enter into specific legal agreements establishing ownership, access, and publication rights. This is particularly critical where confidential data is involved – that is, when people are disclosing information to you that you could not obtain simply by observation or through public records.

If the research team is requesting access to existing data, they must enter into data licensing agreements to access the data and publish research outputs based on it. These agreements should make clear from the outset whether and how the research team can make the original data public, or publish any portion or derivative of the data. If the data is publicly accessible, this may be as simple to agreeing to terms of use on the website where the data can be downloaded. If it is original data that is not yet publicly accessible, the process is typically more complex and requires a documented legal agreement or memorandum of understanding.

If the research team is generating data directly, such as survey data, it is important to clarify up front who owns the data, and who will have access to it. These details need to be shared with respondents when they are offered the opportunity to consent to participate in the study. If the research team is not collecting the data directly – for example, if a government, private company, or research partner is doing the data collection – make sure that you have an explicit agreement about who owns the resulting data.

The contract for data collection should include specific terms as to the rights and responsibilities of each stakeholder. It must clearly stipulate which party owns the data produced, and that the research team maintains full intellectual property rights. The contract should also explicitly indicate that the contracted firm is responsible for protecting respondent privacy, that the data collection will not be delegated to any third parties, and that the data will not be used by the firm or subcontractors for any purpose not expressly stated in the contract, before, during or after the assignment. The contract should also stipulate that the vendor is required to comply with ethical standards for social science research, and adhere to the specific terms of agreement with the relevant Institutional Review Board (IRB) or applicable local authority. Finally, it should include policies on reuse, storage, and retention or destruction of data.

Research teams that acquire original data must also consider data ownership downstream, through the terms they will use to release that data to other researchers or to the general public. The team should consider whether they can publish the data in full after removing personal identifiers. For example, the team must consider whether it would be acceptable for their data to be copied and stored on servers anywhere in the world, whether they would prefer to manage permissions on a case-by-case basis, and whether they expect that data users would cite or credit them. Similarly, the team can require users in turn to release their derivative datasets or publications under similar licenses, or offer use without restriction. There are simple license templates for offering many of these permissions, but, at the planning stage, the team should make sure that all licensing agreements, data collection contracts, and informed consent processes used to acquire the data specifically detail those future uses.

### Obtaining data licenses

Data licensing is the formal act of the dataset owner giving some data rights to a specific user, while retaining ownership of the dataset. If you are not the owner of the dataset you want to analyze, you must enter into a licensing agreement to access it for research purposes. Similarly, when you own a dataset, you must consider whether you will make the dataset accessible to other researchers, and what terms-of-use you require.

If the research team requires access to existing data for novel research, terms of use should be agreed on with the data owner, typically through a data licensing agreement. These terms should specify what data elements will be received, what purposes the data will be used for, and who will have access to the data. Keep in mind that the data owner is likely not highly familiar with the research process, and therefore may be surprised at some of the things you want to do if you are not clear up front. You will typically want intellectual property rights to all research outputs developed used the data, a license for all uses of derivative works, including public distribution (unless ethical considerations contraindicate this). This is important to allow the research team to store, catalog, and publish, in whole or in part, either the original licensed dataset or datasets derived from the original. Make sure that the license you obtain from the data owner allows these uses, and that you consult with the owner if you foresee exceptions with specific portions of the data.

The World Bank has a template Data License Agreement which DIME follows. The template specifies the specific objectives of the data sharing, and whether the data can be used only for the established purpose or for other objectives after it is obtained. It classifies the data into one of four access categories, depending on who can access the data by default and whether case-by-case authorization for access is needed. The data provider may impose similar restrictions to sharing derivative data and any or all of the associated metadata. The template also specifies the required citation for the data. While you do not need to use the World Bank’s template or its access categories if you do not work on a World Bank project, we still think it is important that you use this information in two ways. First, make sure to base your Data License Agreement on some template. Hand-written agreements can leave many legal ambiguities or gaps where the permissions given to the research team are unclear or incomplete. Second, we strongly recommend you to categorize data using some variation of this system. Then you should have different standard procedures for each category, so that the intended processes for handling the data are clear.

### Documenting data received from partners

Research teams granted access to existing data may receive that data in a number of different ways. You may receive access to an existing server, physical access to extract certain information, or a one-time data transfer. In all cases, you must take action to ensure that data is transferred through secure channels so that confidentiality is not compromised. See the section Handling data securely later in this chapter for how to do that. Keep in mind that compliance with ethical research standards may in some cases require a stricter level of security than initially proposed by the partner agency. It is also critical at this stage to request any and all available documentation for the data; this could take the form of a data dictionary or codebook, a manual for administrative data collection system, detailed reports or operating procedures, or another format. If no written documentation is available, interview the person(s) responsible for managing the data to learn as much as possible about the data; the interview notes should be archived with data documentation.

At this stage, it is very important to assess documentation and cataloging of the data and associated metadata. It is not always clear what pieces of information will jointly constitute a research dataset, and many of the datasets you receive will not be organized for research. You should always retain the original data exactly as received alongside a copy of the corresponding ownership agreement or license. You should make a simple README document noting the date of receipt, the source and recipient of the data, and a brief description of each file received. All too often data will be provided as vaguely-named spreadsheets, or digital files with non-specific titles, and documentation will be critical for future access and reproducibility.

Eventually, you will want to make sure that you are creating a set of documents that can be properly submitted to a data catalog and given a reference and citation. The metadata – documentation about the data – is critical for future use of the data. Metadata should include documentation of how the data was created, what they measure, and how they are to be used. In the case of survey data, this includes the survey instrument and associated manuals; the sampling protocols and field adherence to those protocols, and any sampling weights; what variable(s) uniquely identify the dataset(s), and how different datasets can be linked; and a description of field procedures and quality controls. DIME uses as a standard the Data Documentation Initiative (DDI), which is supported by the World Bank’s Microdata Catalog.

As soon as the desired pieces of information are stored together, think about which ones are the components of what you would call a dataset. Often, when you are receiving data from a partner, even highly-structured materials such as registers or records are not, as received, equivalent to a research dataset, and require initial cleaning, restructuring, or recombination to reach the stage we would consider a raw research dataset. This is as much an art than a science: you want to keep information together that is best contextualized together, but you also want to information granular as much as possible, particularly when there are varying units of observation. There usually won’t be a single correct way to answer this question, and the research team will need to decide how to organize the materials received. Soon, you will begin to build research datasets from this set of information, and these will become your original clean data, which will be the material published, released, and cited as the starting point of your data. (If funders or publishers request that “raw” data be published or cataloged, for example, this is the dataset that you should provide, unless they specifically require data in the original format you received it.) These first datasets created from the received materials are the objects you need to catalog, release, and license. Now is a good time to begin assessing disclosure risk and/or seek publication licenses in collaboration with data providers, while you are in close contact with them.

## Collecting high-quality data using electronic surveys

In this section, we detail specific considerations for acquiring high-quality data through electronic surveys of study subjects. If your project will not use any survey data, you may want to skip this section. There are many excellent resources on questionnaire design and field supervision, but few that cover the particular challenges and opportunities presented by electronic surveys. There are also many survey software options available to researchers, and the market is rapidly evolving. Therefore, we focus on specific workflow considerations for digitally-collected data, and on basic concepts rather than software-specific tools.

Electronic data collection technologies have greatly accelerated our ability to bring in high-quality data using purpose-built survey instruments, and therefore improved the precision of research. At the same time, electronic surveys create new pitfalls to avoid. Programming electronic surveys efficiently requires a very different mindset than writing paper-based surveys; careful preparation can improve survey efficiency and data quality. This section will outline the major steps and technical considerations you will need to follow whenever you field a custom survey instrument, no matter the scale.

### Designing survey instruments

A well-designed questionnaire results from careful planning, consideration of analysis and indicators, close review of existing questionnaires, survey pilots, and research team and stakeholder review. There are many excellent resources on questionnaire design, such as from the World Bank’s Living Standards Measurement Survey. The focus of this section is the design of electronic field surveys, often referred to as Computer Assisted Personal Interviews (CAPI). Although most surveys are now collected electronically, by tablet, mobile phone or web browser, questionnaire design  (content development) and questionnaire programming (functionality development) should be seen as two strictly separate tasks. Therefore, the research team should agree on all questionnaire content and design a version of the survey on paper before beginning to program the electronic version. This facilitates a focus on content during the design process and ensures teams have a readable, printable version of their questionnaire. Most importantly, it means the research, not the technology, drives the questionnaire design.

We recommend this approach for three reasons. First, an easy-to-read paper questionnaire is very useful for training data collection staff, which we will discuss further in the enumerator training section below. Second, finalizing the paper version of the questionnaire before beginning any programming avoids version control concerns that arise from concurrent work on paper and electronic survey instruments. Third, a readable paper questionnaire is a necessary component of data documentation, since it is difficult to work backwards from the survey program to the intended concepts.

The workflow for designing a questionnaire will feel much like writing an essay: begin from broad concepts and slowly flesh out the specifics. It is essential to start with a clear understanding of the theory of change and research design for your project. The first step of questionnaire design is to list key outcomes of interest, as well as the main covariates to control for and any variables needed for the specific research design. The ideal starting point for this is a pre-analysis plan.

Use the list of key outcomes to create an outline of questionnaire `modules}. Do not number the modules; instead use a short prefix as numbers quickly get outdated when modules are reordered. For each module, determine if the module is applicable to the full sample, or only to specific respondents, and whether or how often the module should be repeated. A few examples: a module on maternal health only applies to households with a woman who has children, a household income module should be answered by the person responsible for household finances, and a module on agricultural production might be repeated for each crop the household cultivated. Each module should then be expanded into specific indicators to observe in the field. Questionnaires for impact evaluation must also include ways to document the reasons for attrition and treatment contamination. These are essential data components for completing CONSORT records, a standardized system for reporting enrollment, intervention allocation, follow-up, and data analysis through the phases of a randomized trial.

### Piloting survey instruments

A survey pilot is critical to finalize survey design. The pilot must be done out-of-sample, but in a context as similar as possible to the study sample. The survey pilot includes three steps: a pre-pilot, a content-focused pilot, and a data-focused pilot.

The first step is a pre-pilot. The pre-pilot is a qualitative exercise, done early in the questionnaire design process. The objective is to answer broad questions about how to measure key outcome variables, and gather qualitative information relevant to any of the planned survey modules. A pre-pilot is particularly important when designing new survey instruments.

The second step is a content-focused pilot. The objectives at this stage are to improve the structure and length of the questionnaire, refine the phrasing and translation of specific questions, check for potential sensitivities and for enumerator/respondent interactions, and confirm coded response options are exhaustive. In addition, it is an opportunity to test and refine all survey protocols, such as how units will be sampled or pre-selected units identified. The content-focused pilot is best done on pen and paper, before the questionnaire is programmed, because changes at this point may be deep and structural, which are hard to adjust in code. It is important at this point to test both the validity and the reliability of the survey questions; for this reason it is important to conduct the content-focused pilot with a sufficiently large sample (the exact requirement will depend on the research sample; a very rough rule of thumb is a minimum of 30 interviews.

The final stage is a data-focused pilot. After the content is finalized, proceed with programming a draft version of the electronic survey instrument. The objective of this pilot is to refine the questionnaire programming; this is discussed in detail in the following section.

### Programming electronic survey instruments

Once the team is satisfied with the content and structure of the survey, it is time to move on to implementing it electronically. Electronic data collection has great potential to simplify survey implementation and improve data quality. But it is critical to ensure that electronic survey instruments flow correctly and produce data that can be used in statistical software, before data collection starts. Electronic questionnaires are typically developed in a spreadsheet (usually using Excel or Google Sheets) or a software-specific form builder, all of which are accessible even to novice users. We will not address software-specific form design in this book; rather, we focus on coding and design conventions that are important to follow for electronic surveys regardless of software choice. Survey software tools provide a wide range of features designed to make implementing even highly complex surveys easy, scalable, and secure. However, these are not fully automatic: you need to actively design and manage the survey. Here, we discuss specific practices that you need to follow to take advantage of electronic survey features and ensure that the exported data is compatible with your statistical software.

From a data perspective, questions with coded response options are always preferable to open-ended questions. The content-based pilot is an excellent time to ask open-ended questions and refine fixed responses for the final version of the questionnaire – do not count on coding up lots of free text after a full survey. Coding responses helps to ensure that the data will be useful for quantitative analysis. Two examples help illustrate the point. First, instead of asking “How do you feel about the proposed policy change?”, use techniques like Likert scales. Second, if collecting data on things like medication use or food supplies, you could collect: the brand name of the product; the generic name of the product; a coded identifier for the item; or the broad category to which each product belongs (“antibiotics” or “staple foods”, for example). All four may be useful for different reasons, but the latter two are likely to be the most useful for rapid data analysis. The coded identifiers require providing a translation dictionary to field staff, but enables automated rapid recoding for analysis with no loss of information. The broad category requires agreement on the groups of interest, but allows for much more comprehensible top-line statistics and data quality checks. Rigorous field testing is required to ensure that answer categories are comprehensive; however, it is best practice to include an other, specify option. Keep track of those responses in the first few weeks of field work. Adding an answer category for a response frequently showing up as other can save time, as it avoids extensive post-coding.

It is essential to name the fields in your questionnaire in a way that will also work in your data analysis software. Most survey programs will not enforce this by default, since limits vary across statistical software, and survey software will encourage you to use long sentences as question labels and detailed descriptions as choice options. This is what you want for the enumerator-respondent interaction, but you should already have analysis-compatible labels programmed in the background so the resulting data can be rapidly imported in analytical software. There is some debate over how exactly individual questions should be identified: formats like hq_1 are hard to remember and unpleasant to reorder, but formats like hq_asked_about_loans quickly become cumbersome. We recommend using descriptive names with clear prefixes so that variables within a module stay together when sorted alphabetically. Variable names should never include spaces or mixed cases (we prefer all-lowercase naming). Take special care with the length: very long names will be cut off in some softwares, which could result in a loss of uniqueness and lots of manual work to restore compatibility. We further discourage explicit question numbering, at least at first, as it discourages re-ordering questions, which is a common recommended change after the pilot. In the case of follow-up surveys, numbering can quickly become convoluted, too often resulting in uninformative variables names like ag_15a, ag_15_new, ag_15_fup2, and so on.

### Using electronic survey features to enhance data quality

Electronic surveys are more than simply a paper questionnaire displayed on a mobile device or web browser. All common survey software allows you to automate survey logic and include hard or soft constraints on survey responses. These features make enumerators’ work easier, and they create the opportunity to identify and resolve data issues in real time, simplifying data cleaning and improving response quality. Well-programmed questionnaires should include most or all of the following features:

- Localization: the survey instrument should display full-text questions and responses in all potential survey languages, and it should also have English and code-compatible versions of all text and labels.

- Survey logic: built-in tests should be included for all logic connections between questions, so that only relevant questions appear, rather than relying on enumerators to follow complex survey logic. This covers simple skip codes, as well as more complex interdependencies (e.g., a child health module is only asked to households that report the presence of a child under 5).

- Range checks: add range checks for all numeric variables to catch data entry mistakes (e.g. age must be less than 120).

- Confirmation of key variables: require double entry of essential information (such as a contact phone number in a survey with planned phone follow-ups), with automatic validation that the two entries match and rejection and re-entry otherwise.

- Multimedia: electronic questionnaires facilitate collection of images, video, and geolocation data directly during the survey, using the camera and GPS built into the tablet or phone.

- Preloaded data: data from previous rounds or related surveys can be used to prepopulate certain sections of the questionnaire, and validated during the survey.

- Filtered response options: filters reduce the number of response options dynamically (e.g. filtering a “cities” choice list based on the state selected).

- Location checks: enumerators submit their actual location using in-built GPS, to confirm they are in the right place for the interview.

- Consistency checks: check that answers to related questions align, and trigger a warning if not so that enumerators can probe further (e.g., if a household reports producing 800 kg of maize, but selling 900 kg of maize from their own production).

- Calculations: make the electronic survey instrument do all math, rather than relying on the enumerator or asking them to carry a calculator.

All established survey software include debugging and test options to correct syntax errors and make sure that the survey instruments will successfully compile. This is not sufficient, however, to ensure that the resulting dataset will load without errors in your data analysis software of choice. DIME Analytics developed the ietestform command, part of the Stata package iefieldkit, to implement a form-checking routine for SurveyCTO, a proprietary implementation of the open source Open Data Kit (ODK) software. Intended for use during questionnaire programming and before field work, ietestform tests for best practices in coding, naming and labeling, and choice lists. Although ietestform is software-specific, many of the tests it runs are general and important to consider regardless of software choice. To give a few examples, ietestform tests that no variable names exceed 32 characters, the limit in Stata (variable names that exceed that limit will be truncated, and as a result may no longer be unique). It checks whether ranges are included for numeric variables. ietestform also removes all leading and trailing blanks from response lists, which could be handled inconsistently across software.

The final stage of survey piloting, the data-focused pilot, should be done at this stage (after the questionnaire is programmed). The objective of this data-focused pilot is to validate the programming and export a sample dataset. Significant desk-testing of the instrument is required to debug the programming as fully as possible before going to the field. It is important to plan for multiple days of piloting, so that any debugging or other revisions to the electronic survey instrument can be made at the end of each day and tested the following, until no further field errors arise. The data-focused pilot should be done in advance of enumerator training.

### Training enumerators

Once a survey instrument is designed, piloted on paper to refine content, programmed, piloted electronically to refine the data, and fully translated to any local languages, it is time to prepare to train the field staff who will be responsible for conducting interviews. The following guidelines for enumerator training apply regardless of whether data will ultimately be collected in person or remotely, with the only significant differences being in terms of survey protocols and the nature of the field practice (which could be in-person or by phone).

The first step is to develop a detailed enumerator manual.  The manual should explain each question in the survey instrument, address any issues that arose during piloting and cover frequently asked questions. The manual must also describe survey protocols and conventions, such as how to select or confirm the identity of respondents, and standardized means for recording responses such as ``Don’t know".  The enumerator manual serves as the basis for the enumerator training.  We recommend the training to be divided into two sessions: first a training-of-trainers, and then the enumerator training. The training-of-trainers should include the field supervisors and any other relevant management staff from the organization responsible for data collection, and should be led by the research team. The objective is to ensure the survey leaders are deeply familiar with the survey instrument and protocols, so that they can support and supervise enumerators going forward. The training-of-trainers typically lasts a few days, though exact length will depend on the complexity of the survey instrument and experience level of the staff.

Enumerator training includes all field staff, and should be jointly led by the research team and the survey managers. This training typically lasts one to two weeks, though exact length will depend on complexity and experience; training for particularly challenging surveys may take a full month. Enumerator training has three components: review of the paper questionnaire, review of the electronic survey instrument, and field practice. The training schedule should allow for significant discussion and feedback after each component. Training with a paper survey instrument is critical, even for surveys that will be deployed electronically. Starting with paper ensures a focus on survey content and structure before diving into the technical components of the survey software. It is much easier for enumerators to understand the overall flow of a survey instrument and the range of possible participant responses on a paper survey than on a tablet, and it is easier to translate that understanding to digital functionality later. The classroom training should be very interactive, using methods such as role plays and mock interviews to test understanding of survey protocols and modules. The field practice should be carefully supervised, so as to provide individualized feedback to each enumerator.

When introducing the digital form of the survey, enumerators should submit data from practice interviews to the server, and the research team should run the standard data quality checks, to familiarize the enumerators with those standards for data quality and how quality issues will be communicated and resolved. It is essential to train more enumerators than will be required for the survey, and to include objective assessments throughout the training. These assessments can take the form of pop quizzes (which we recommend doing daily, using the same software as the survey), points for participation, and score on the field practice. At the end of the training, use the aggregate score to transparently select the final team of enumerators.

### Checking data quality in real time

Once all field staff are trained, it is time to start collecting data. If you have followed all the guidance above, the stage should be set for quality data. To ensure high quality data in practice, the research team should develop a data quality assurance plan. A key advantage of electronic data collection methods, as compared to traditional paper surveys and one-time data dumps, is the ability to access and analyze the data as data collection is ongoing. Data issues can then be identified and resolved in real-time. Designing systematic data checks and running them routinely throughout data collection simplifies field monitoring and improves data quality. There are two important types of checks for data quality monitoring: high frequency quality checks and field validation.

High frequency data quality checks should be scripted in advance of the start of data collection, so that data checks can start as soon as data starts to come in. A research assistant should run the high-frequency checks (HFCs) on a daily basis for the duration of the survey. HFCs should include monitor consistency and range of responses to each question, survey programming validation, tests for enumerator-specific effects, and checks for duplicate entries and completeness of online submissions vis-a-vis the field log.

High-frequency checks will only improve data quality if the issues they catch are communicated to the team collecting the data and corrections are documented and applied to the data. This requires close communication with the field team, so that enumerators are made aware of data quality issues promptly, and a transparent system for document issues and corrections. There are many ways to communicate results of high-frequency checks to the field team. What’s most important is to find a way to create actionable information for your team. ipacheck, for example, generates a spreadsheet with flagged errors; these can be sent directly to the data collection teams. Many teams choose other formats to display results, such as online dashboards created by custom scripts. It is also possible to automate communication of errors to the field team by adding scripts to link the HFCs with a messaging platform. Any of these solutions are possible: what works best for your team will depend on such factors as cellular networks in field work areas, whether field supervisors have access to laptops, internet speed, and coding skills of the team preparing the HFC workflows.

Careful field validation is essential for high-quality survey data. While we cannot control natural measurement error, which comes from variation in the realization of key outcomes, there is often an opportunity to reduce error arising from inaccuracies in the data generation process. Back-checks, spot checks, and other validation audits help ensure that data is not falsified, incomplete, or otherwise suspect. Field validation is also an opportunity to ensure that all field protocols are followed. For back-checks, a random subset of observations is selected, and a subset of information from the full survey is verified through a brief targeted survey with the original respondent. For spot checks, field supervisors (and, if contextually appropriate, research team staff) should do unannounced field visits to each enumerator, to confirm first-hand that they are following survey protocols and understand the survey questions well. Design of the back-checks or validations follows the same survey design principles discussed above: you should use the analysis plan or list of key outcomes to establish which subset of variables to prioritize, and similarly focus on errors that would be major flags for poor quality data.

Real-time access to the data massively increases the potential utility of back-checks, and both simplifies and improves the rigor of the associated workflows. You can use the raw data to draw the back-check or validation sample; this ensures that the validation is correctly apportioned across observations. As soon as high frequency checks are complete, the back-check data can be tested against the original data to identify areas of concern in real time. The bcstats command is a useful tool for analyzing back-check data in Stata. Some electronic surveys software also provide a unique opportunity to do audits through audio recordings of the interview, typically short recordings triggered at random throughout the questionnaire. Audio audits are a useful means to assess whether enumerators are conducting interviews as expected. Do note, however, that audio audits must be included in the informed consent for the respondents, and the recordings will need to be assessed by specially trained staff.

## Handling data securely

All confidential data must be handled in such a way that only people specifically approved by an Institutional Review Board (IRB), or specified in the Data Licensing Agreement (DLA), are able to access the data. Data can be confidential for multiple reasons; two very common reasons are that the data contains personally-identifying information (PII)  or that the data owner has specified restricted access.

### Encrypting data

Data encryption is a group of tools and methods to ensure that confidential files are unreadable and unusable even if laptops are stolen, servers are hacked, or unauthorized access to the data is obtained in any other way. Proper encryption is central to secure data handling, and can rarely be condensed into a single tool or method, as the data will travel through many servers, devices, and computers from the source of the data to the final analysis. Encryption should be seen as a system that is only as secure as its weakest link. This section recommends a streamlined encryption workflow, so that it is easy as possible to make sure the entire chain is easy to manage and is sufficiently secure.

All encryption relies on a password or encryption key for both encrypting and decrypting information. Encryption makes data files completely unusable to anyone who obtains them if they do not have the specific decryption key. This is a higher level of security than most password-protection, because password-protected information is often readable if the password is bypassed or the storage server is compromised. You will need to share and store these keys carefully; if you lose them or cannot match them to encrypted information, the information is permanently lost. Therefore, you should treat access to encryption keys as equivalent to access to the confidential information. It is never secure to share these passwords or keys by email, WhatsApp or other common modes of communication; instead, use a secure password manager built for this purpose.

There are two contexts for encryption you should be aware of. Encryption-in-transit protects your data when it is sent over the internet. This is a standard, passive protection that almost all internet-based services use; you only need to worry about it if you are creating a custom transfer solution. Encryption-at-rest protects your data when it is stored on a server, computer, or drive.

There are two main types of encryption algorithms and they are called symmetric encryption and asymmetric encryption. In symmetric encryption, the same key is used to both encrypt and decrypt the data. In asymmetric encryption, one key is used to encrypt data, and another key from the same “pair” is used to decrypt it. You, as a user, need to keep track of these keys. While encryption keys for asymmetric encryption are often automatically provided to the devices recording or inputting information, only people listed on your IRB should have access to decryption keys or symmetric-encryption keys.

Typically, unless you have access to an approved enterprise version of data sharing software, you will need to set up encryption at rest for your data in two locations – server or web storage during data acquisition and local storage afterwards. You should never trust that this is automatically implemented unless a cybersecurity expert within your organization has specified that a specific service is appropriate to your use case. In all other cases you should follow the steps laid out in this section, where you set up your own encryption where you, and only you, are in full control of who has access to the key.

### Collecting and storing data securely

Most data collection software will automatically encrypt all data in transit (i.e., upload from field or download from server). However, it is necessary to ensure that confidential data are protected when stored on a server owned by the data collection software provider or which can be accessed by people not on your research team (including your local IT or system administrators). In most data collection platforms, encryption-at-rest needs to be explicitly enabled and operated by the user. When collecting data, the tablets or the browsers used for data collection should encrypt all information before submitting it to the server, and you should decrypt it only after downloading to your local machine.

This is a perfect use case for asymmetric encryption where there are two keys, forming a “public/private key pair”. The public key can safely be sent to all tablets or browsers so it can be used for encrypting the data before it is submitted to the server. Only the private key in the same key pair can then be used to decrypt that data so it can be accessed after it has been received. The private key should be kept secret and should not be shared with anyone not listed on the IRB. Again, you must store the key pair in a secure location, such as a secure note in a password manager, as there is no way to access your data if the private key is lost. If your data collection service allows you to browse data in the browser, then the encryption is only implemented correctly if you are asked for the key each time.

The data security standards that apply when receiving confidential data from the field also apply when transferring confidential data to the field, such as sampling or enumeration lists containing PII. In some survey software, you can use the same encryption that allows you to receive data securely from the field, to also send confidential data, such as an identifying list of respondents, to the field. Otherwise, you will need to create a securely stored file, transfer it to the field team using an insecure tool, and have them decrypt the information locally using a key that is transferred using a secure password manager. This process will be more similar to that for securely `storing} data, which we discuss next.

The first thing you need to do before planning how to securely send or receive data, is to plan how to securely store data after it has been transferred. Typically, you want to store your data so that you can decrypt and access it, interact with it and then encrypt it again. (Usually, you will not want to edit this data, but only extract non-sensitive pieces of it to an insecure location.) That is a perfect use case for symmetric encryption where the same key is used to both encrypt and decrypt your files. Think of this type of encryption similarly to a physical safe, where you have one key which is used to both add and access contents.

The equivalent to the safe in secure data storage is an encrypted folder, which you can set up using, for example, VeraCrypt. You can interact with files in an encrypted folder, and modify them like any unencrypted file, if and only if you have the key. This is an implementation of encryption-at-rest. There is absolutely no way to restore the data if you lose your key, so we cannot stress enough the importance of using a password manager, or equally secure solution, to store these encryption keys.

It is becoming more and more common that development research is done on data set that is too big to store on a regular computer, and instead the data is stored and processed in a cloud environment. There are many available cloud storage solutions and you need to understand how the data is encrypted and how the keys are handled. This is likely another case where a regular research team will have to ask a cybersecurity expert. After someone have helped you to set up a secure cloud storage, if you were to download a sample of the data – for example to develop your code on – then you need to remember to encrypt the data when stored on your computer.

### Backing up original data

In addition to encrypting your data, you must protect it from being accidentally overwritten or deleted. This is done through a back-up protocol, which creates additional copies of your original data, exactly as received and finalized, in secure locations that will remain permanently available but are not intended for frequent access. Here is an example of such a protocol:

- Create an encrypted folder in your project folder. This should be on your computer, and could be in a shared folder.

- Download your original data from your data source to that encrypted folder. If your data source is a survey and the data was encrypted during data collection, then you will need both the private key used during data collection to be able to download the data, and the key used when you created the encrypted folder to save it there. This your first copy of your raw data, and the copy you will use for cleaning and analysis.

- Create a second encrypted folder on an external drive that you can keep in a secure location. Copy the data you just downloaded to this second encrypted folder. This is the ``master" backup copy of the raw data. You should never work with this data on a day-to-day basis. You should not use the same encrypted folder or the same key as above, because if you use the same key and lose the key, then you will have lost access to both encrypted folders. If you have a physical safe where you can securely store the external drive, then you do not need to encrypt the data and thereby do not risk losing access by losing an encryption key.

- Finally, create a third encrypted folder. Either you can create this on your computer and upload it to a long-term cloud storage service (not a sync software), or you can create it on another external hard drive or computer that you then store in a second location, for example, at another office of your organization. This is the golden master" backup copy of the raw data. You should never store thegolden master" copy in a synced folder, as it would be deleted in the cloud storage if it is deleted on your computer. You should also never work with this data; it exists only for recovery purposes.

This handling satisfies the 3-2-1 rule: there are two on-site copies of the data and one off-site copy, so the data can never be lost in case of hardware failure. If you remain lucky, you will never have to access your “master” or “golden master” copies – you just want to know it is there, safe, if you one day end up needing it.

## Looking ahead

This chapter provided a road map to the acquisition of original data. It outlined guidelines for ensuring that you have effective ownership or licensing of data that you obtain or collect, and how to make those materials available in the future. It also provided an extensive guide for one of the most common – and challenging – methods of data collection: primary electronic surveys. Finally, it emphasized the secure handling of this potentially sensitive information, giving you a range of tools and a complete workflow for transferring and storing data securely at all times. Once your original data is completely transferred, securely stored, and backed up, the data acquisition stage is complete, as summarized in the figure accompanying this chapter. This is when the heavy lifting with statistical software starts. Before you can proceed to analyze your data and answer your project’s research questions, you first need to check the quality of the data acquired, make sure you have the right information in the right format, and prepare it for analysis. This process, which we call data cleaning and processing, is described in the next chapter.

Data acquisition tasks and outputs

# Cleaning and processing research data

Original data comes in a variety of formats, most of which are not immediately suited for analysis. The process of preparing data for analysis has many different names: data cleaning, data munging, data wrangling. But they all mean the same thing – transforming raw data into a convenient format for your intended use. This is the most time-consuming step of a project’s data work, particularly when primary data is involved; it is also essential for data quality. A structured workflow for preparing newly-acquired data for analysis is essential for efficient, transparent, and reproducible data work. One key point of this chapter is that no changes are made to the contents of data at this point. We consider creating new variables, imputing values and correcting outliers to be research decisions, and will discuss those in the next chapter. Therefore, the clean dataset, which is the main output from the workflow discussed in this chapter, contains the same information as the raw data, but in a format that is ready for use with statistical software.

This chapter describes the various tasks involved in making newly-acquired data ready for analysis. The first section teaches you how to make your data tidy. This means adjusting how the dataset is organized until the relationship between rows and columns is well-defined. The second section describes quality assurance checks, which are necessary to verify data accuracy. The third section covers de-identification, as removing direct identifiers early in the data handling process helps to ensure privacy. The final section discusses how to examine each variable in your dataset and make sure that it is as well documented and as easy to use as possible. Each of these tasks is implemented through code, and resulting datasets can be reproduced exactly by running this code. The raw data files are kept exactly as they were acquired, and no changes are made directly to them.

## Making data “tidy”

The very first step in creating an analysis-friendly dataset is understanding the data acquired, and using this understanding to translate the data into an intuitive format. This section discusses what steps may be needed to make sure that each row in your data tables represents one observation. Getting to such a format may be harder than expected, and the unit of observation may be ambiguous in many raw datasets. This section will present what we call a tidy data format, which is, in our experience, the ideal format to handle tabular data. We will treat tidying data as the first step in data cleaning even though, in practice, both tidying and quality monitoring should be done simultaneously as data is received. This is because quality assurance can only be finalized using tidied data, when it is guaranteed that each observation is uniquely identified.

### Establishing a unique identifier

An important step before starting to tidy a dataset is to understand the unit of observation and find out which variable or set of variables is the unique identifier for each observation. As discussed in Chapter 3, the unique identifier will be used to link observations in this dataset to data in other data sources according to the data linkage table, and the unique identifier for all observations must be listed in the master dataset. Ensuring that observations are uniquely and fully identified is arguably the most important step in data cleaning. It may be the case that the variables expected to uniquely identify the raw data contain either missing or duplicate values.

It is also possible for a raw dataset to not include an unique identifier, or that the identifier is not a suitable project ID. Suitable project IDs should, for example, not involve long strings that are difficult to work with, such as a name, or be an ID that is known outside the research team. In such cases, cleaning begins by adding a project ID to the raw data. If a project ID already exists, for this unit of observation, then you should carefully merge it from the master dataset to the raw data using other identifying information. If a project ID does not exist, then you need to generate one, add it to the master dataset, and then merge it back into the raw data. Note that while digital survey tools create unique identifiers for each data submission, that is not the same as having a unique ID variable for each observation in the sample, as there can be multiple submissions for the same observation.

DIME Analytics created an automated workflow to identify, correct and document occurrences of duplicated entries in the unique identifier using ieduplicates and iecompdup, two Stata commands included in the iefieldkit package. One advantage of using ieduplicates to correct duplicated entries is that it creates duplicates reports which records each corrections made and documents the reason for it. Even if you are not using this command, it is important to keep a record of all cases of duplicated IDs encountered and how they were resolved.

### Tidying raw data

Though raw data can be acquired in all shapes and sizes, it is most commonly received as one or multiple data tables. These data tables can organize information in multiple ways, and not all of them result in easy-to-handle datasets. Fortunately, a vast literature of database management has identified the format that makes interacting with the data as easy as it can be. We call data in such format tidy. A data table is tidy when each column represents one variable, each row represents one observation, and all variables in it have the same unit of observation. Every other format is untidy. This may seem trivial, but raw data, and raw survey data in particular, is rarely received in a tidy format.

The most common case of untidy raw data encountered in development research is a dataset with multiple units of observations stored in the same data table. Take, for example, a household survey that includes household-level questions, as well as a household member roster. Such raw datasets usually consists of a single data table where questions from the household member roster are saved in different columns, one for each member, with a corresponding member suffix, and household-level questions are represented by one column each. When your rows include multiple nested observational units, then the identifying variable does not identify all observations on that row, as there is more than one unit of observation on the same row.

Survey data containing nested units of observation is typically imported from survey platforms in wide format. Wide format data could have, for instance, one column for a household-level variable (for example ownsfridge), and a few columns for household member-level variables (for example sex_1, sex_2). Raw data is often saved in this format because it’s the most efficient way to transfer it: adding different levels of observation into the same data table allows for data to be transferred in a single file. However, this leads to the widespread practice of interacting with data in wide format, although doing so is often inefficient and error-prone.

To understand how dealing with wide data can be complicated, imagine you need to calculate the share of women in each household using the household level data described above. In a wide data table you will either have to first create variables counting the number of women and the total number of household members, and then calculate the share, or you will have to transform the data to a different format. In a tidy data table, however, where each row is a household member, you can easily aggregate the share of women by household, without additional steps, and then merge the result to the household-level data tables. Tidy data tables are also easier to clean, as each attribute only needs to be checked once, and each column corresponds directly to one question in the questionnaire. Finally, as you will see in Chapter 6, summary statistics and distributions are much simpler to generate from tidy data tables.

As mentioned earlier, there are unlimited ways for data to be untidy; wide format is only one of those ways. Another example is a data table containing both information on transactions and on the firms involved in each transaction. In this case, the firm-level information will be repeated for all transactions a given firm was involved in. Analyzing data in this format would give more weight to firms that conducted more transactions, which may not be consistent with the research design.

The basic process behind tidying a data table is simple: first, identify all the variables that were measured at the same level of observation; second, create separate data tables for each level of observation; and third, reshape the data and remove duplicated rows until each data table is uniquely and fully identified by the identifying variable that corresponds to its unit of observation. Reshaping data tables is the most intricate task in data cleaning; you should be very familiar with commands such as reshape in Stata and pivot in R. You must be sure that identifying variables are consistent across data tables, so they can always be linked. Reshaping is the type of transformation we referred to in the example of how you calculate the share of women in a wide data set. The important difference is that in a tidy workflow, instead of transforming the data for each operation, this transformation is done once for all data during cleaning, making all subsequent operations much easier.

In the earlier household survey example, household-level variables will be stored in one tidy data table, and household-member variables are reshaped and stored in a separate, member-level, tidy data table, which also contains the household ID for each individual. The household ID is intentionally duplicated in the household members data table to allow one or several household members to be linked to the same household data. The unique identifier for the household member-level data data will be either a single household member ID or a combination of household ID and household member ID. In the transaction data example, the result of the tidying process would be one transaction-level data table, containing variables indicating the ID of all firms involved; and one firm-level data table with a single entry for each firm. Then, firm-level analysis is easily done by calculating appropriate statistics in the transactions data table (in Stata, often through collapse) and then merging or joining those results to the firms data table.

In a tidy workflow, your clean dataset is a set of one or more tidy data tables. In both examples above, your clean dataset is made up of two tidy data tables. There must be a clear way to connect each tidy data table to a master dataset, and thereby also to all other datasets. To implement this, you need to decide which data table is the main data table; that data table’s unit of observation will be the main unit of observation of your dataset. The main unit of observation must directly correspond to a master dataset, and be listed in the data linkage table. All other data tables in your dataset must have an unambiguous way to merge with the main data table. This way, it will be possible to link all data points in all your project’s datasets to each other. We recommend that you save your datasets as a folder, in which the main data table shares the same name as the folder, and the name of all other data tables start with the same name, but are suffixed with the unit of observation for that data table.

In the household dataset example, the household-level data table would be the main table. This means that there must be a master dataset for households. (You may have a master dataset for household members as well if you think it is important for your research, but it is not strictly required.) The household data set would then be stored in a folder called, for example, baseline-hh-survey/. In that folder you would save both the household-level data table with the same name as the folder, for example baseline-hh-survey.csv, and the household member-level data named in the same format but with a suffix, for example baseline-hh-survey-hhmember.csv.

The tidying process gets more complex as the number of nested groups increases. That means the steps of identifying the unit of observation of each variable and reshaping the separated data tables need to be repeated multiple times. However, the more nested groups a dataset includes, the more efficient it is to deal with tidy data as compared to untidy. Cleaning and analyzing wide datasets, in particular, is a repetitive and error-prone process.

The next step of data cleaning, data quality monitoring, may involve comparing different units of observation. Aggregating sub-units to compare to a higher unit is much easier with tidy data, which is why we suggest tidying data as the first step in the cleaning workflow. If you are conducting primary data collection, you can start preparing or coding the data tidying even before the data is acquired, since you will know in advance the exact format in which the data will be received. In the case of survey data, tidying datasets will guarantee a one-to-one correspondence between questions in the questionnaire and columns in the data. Preparing the data for analysis, the last task in this chapter, is much simpler when that is the case.

## Assuring data quality

Whether you are acquiring data from a partner or collecting it directly, it is important to make sure that data faithfully reflects ground realities. You should carefully examine and clean any data you are about to use. When reviewing raw data, you will inevitably encounter data entry mistakes, such as typos and inconsistent values. Whether your team is conducting a survey or you are receiving administrative data from a partner, the key aspects to have in mind are data completeness, consistency and distribution. Data quality assurance checks should be performed as soon as the data is acquired. When data is being collected and transferred to the team in real-time, this means conducting high-frequency checks. Primary data require extra attention to quality checks, as data entry by humans is more susceptible to errors, and the research team will be the only line of defense between data issues and the data analysis. Survey-specific quality monitoring protocols are discussed in Chaper 4.

### Implementing data quality checks

Data quality checks should carefully inspect key treatment and outcome variables to ensure that the data quality of core study variables is uniformly high, and that additional effort is centered where it is most important. They should be run every time data is received to flag irregularities in the acquisition progress, in sample completeness, or in response quality. The faster issues are identified, the more likely they are to be solved. Once the field team has left a survey area, or high-frequency data has been deleted from a server, it may be impossible to verify whether data points are correct or not. Even if the research team is not receiving data in real-time, the data owners may not be as knowledgeable about the data, or even as responsive to the research team queries, as time goes by. ipacheck is a very useful Stata command that automates some of these tasks, regardless of the data source.

It is important to check continuously that the observations received match the intended sample. In surveys, electronic survey software often provides case management features through which sampled units are directly assigned to individual enumerators. For data received from partners, such as administrative data, this may be harder to validate. In these cases, cross-referencing with other data sources can help to ensure completeness. It is often the case that raw data includes duplicate or missing entries, which may occur due to typos, failed submissions to data servers, or other mistakes. Issues with data transmission often result in missing observations, particularly when large datasets are being transferred, or when data is being collected in locations with limited internet connection. Keeping a record of what data was submitted, and comparing it to the data received as soon as transmission is complete reduces the risk of noticing that data is missing when it is no longer possible to recover it.

Once data completeness is confirmed, observed units must be validated against the expected sample: this is as straightforward as merging the sample list with the data received and checking for mismatches. Reporting errors and duplicate observations in real time allows for efficient corrections. ieduplicates provides a workflow for resolving duplicate entries with the data provider. For surveys, it is also important to track data collection progress to monitor attrition, so that it is clear early on if a change in protocols or additional tracking will be needed. Remember to also check survey completion rates and sample compliance by surveyors and survey teams, and compare data missingness across administrative regions, to identify any clusters that may be providing data of suspect quality.

Quality checks should also include checks of response quality and consistency. For example, whether the values for each variable fall within the expected range, and related variables do not contradict each other. Electronic data collection systems often incorporate many quality control features, such as range restrictions and logical flows. Data received from systems that do not include such controls should be checked more carefully. Consistency checks are project specific, so it is difficult to provide general guidance. A detailed knowledge of the variables in the dataset and a careful examination of the analysis plan is the best way to prepare. Examples of inconsistencies in survey data would include cases where a household reports having cultivated a plot in one module, but does not list any cultivated crops in another. Response consistency should be checked across all datasets, as this is much harder to automate. For example, if two sets of administrative records are received, one with hospital level information and one with data on each medical staff, the number of entries in the second set of entries should match the number of employed personnel in the first one.

Finally, no amount of pre-programmed checks can replace actually looking at the data. Of course that doesn’t mean eye checking each data point, but rather plotting and tabulating distributions for your main variables of interest. This will help you identify outliers and other potentially problematic patterns that you had not foreseen. A common source of outliers values in survey data are typos, but they can also occur in admin data if, for example, the unit reported changed over time, but the data was stored with the same variable name. Identifying unforeseen patterns in the distribution will also help you gather relevant information, for example whether there was no harvest data because of a particular pest in the community or if the unusual call records in a particular area caused by temporary downtime of a tower. Analysis of metadata and paradata can also useful in assessing data quality. For example, electronic survey software generates automatically collected timestamps and trace histories, showing when data was submitted, how long enumerators spent on each question, and how many times answers were changed before or after the data was submitted.

## Processing confidential data

When implementing the steps discussed up to this point, you are likely to be handling confidential data. Effective data quality monitoring frequently requires you to identify the individual observations in your dataset, and the people or other entities who provided the information. Using identified data allows you to quickly follow up on and resolve identified issues. Handling confidential data such as personally-identifying information requires a secure environment and, typically, decryption. De-identifying the data will allow you to simplify that workflow, and will also reduces the risk of harmful leaks. This section describes how to de-identify data in order to share it with a wider audience.

### Protecting research subject privacy

Most development data involves human subjects.  As a researcher, you may have access to personal information about your subjects: where they live, how much income they have, whether they have committed or been victims of crimes, their names, their national identity numbers, and other sensitive data. There are strict requirements for safely storing and handling personally-identifying data, and it is the responsibility of the research team to satisfy these requirements. Everyone working with human subjects research should have completed an ethics certification course. A plan for secure data handling is typically also required for IRB approval.

The best way to avoid risk is to minimize interactions with PII as much as possible. First, only collect personally-identifying information that is strictly necessary for the research. Second, avoid the proliferation of copies of identified data. There should never be more than one copy of the raw identified dataset in the working project folder, and it must always be encrypted. Third, de-identify the data as early as possible in the workflow. Even within the research team, access to the identified data should be limited to team members who require it for their specific tasks. Data analysis that requires identifying information is rare and in most cases can be avoided by properly linking masked identifiers to research information such as treatment statuses and weights, then removing unmasked identifiers.

% De-identification vs anonymization Once data is acquired and the data quality checks described above are completed, the next task is typically to de-identify the data, by removing or masking all personally-identifying variables.  Note that it is in practice impossible to anonymize data. There is always some statistical chance that an individual’s identity will be re-linked to the stored data – even if that data has had all directly identifying information removed – by using some other data that becomes identifying when integrated. For this reason, we typically recommend de-identification in two stages. The initial de-identification process, performed as soon as data is acquired, strips the data of direct identifiers, to create a working de-identified dataset that can be shared within the research team without the need for encryption. The **final de-identification* process, performed before data is publicly released, involves careful consideration of the trade-offs between risk of identifying individuals and the utility of the data, and typically requires the removal of a further level of indirect identifiers. The rest of this section describes how to implement both the initial and the final de-identification processes.

### Implementing de-identification

Initial de-identification reduces risk and simplifies workflows. Once you create a de-identified version of the dataset, you no longer need to interact directly with the encrypted data. Note that if the data tidying resulted in multiple raw data tables, each will need to be de-identified separately, but the workflow will be the same for all of them.

During the initial round of de-identification, datasets must be stripped of personally identifying information. To do so, you will need to identify all variables that contain such information. For data collection, where the research team designs the survey instrument, flagging all potentially identifying variables at questionnaire design stage simplifies the initial de-identification process. If you did not do that, or you received original data by another means, there are a few tools to help flag variables with personally-identifying data. JPAL’s PII-scan and IPA’s PII_detection, scan variable names and labels for common string patterns associated with identifying information. The World Bank’s sdcMicro lists variables that uniquely identify observations, but its more refined method and higher processing capacity requirement makes it better suited for final de-identification. The iefieldkit command iecodebook lists all variables in a dataset and exports an Excel sheet where you can easily select which variables to keep or drop.

Once you have a list of variables that contain confidential information, assess them against the analysis plan and first ask yourself for each variable: will this variable be needed for the analysis? If not, the variable should be dropped. Don’t be afraid to drop too many variables the first time, as you can always go back and extract additional variables from the raw data, but you cannot go back in time and drop a PII variable that was leaked.

For each confidential variable that is needed in the analysis, ask yourself: can I encode or otherwise construct a variable that masks the confidential component, and then drop this variable? For example, it is easy to encode identifiers for small localities like villages and only provide a meaningless numerical indicator showing which observations are in the same village without revealing which villages are included in the data. This is typically the case for most identifying information. If the answer to either of the two questions above is yes, all you need to do is write a script to drop the variables that are not required for analysis, encode or otherwise mask those that are required, and save a working version of the data. For example: after constructing measures of distance or area, drop the specific geolocations in the data; after constructing and verifying numeric identifiers in a social network module, drop all names. If confidential information is strictly required for the analysis and cannot be masked or encoded, then at least the confidential part of the data is required to remain encrypted and only be decrypted when used during in the data analysis process. Using confidential data in the analysis process does not justify storing or sharing it in an insecure way.

After initial de-identification is complete, your dataset will consist of one or multiple tidy, de-identified data tables. This is the dataset that you will interact with during the remaining tasks described in this chapter. Initial de-identification should not affect the usability of the data. Note that access to the initially de-identified data should still be restricted to the research team only, as indirect identifiers may still present a high risk if disclosure. It is common, and even desirable, for teams to make data publicly available once the tasks discussed in this chapter are concluded. This will allow other researchers to conduct additional analysis and to reproduce your finding. Before that can be done, however, you should further consider whether your data can be re-identified, in a process we call final de-identification, which will be discussed in more detail in Chapter 7.

## Cleaning and preparing data for analysis

The last step in the data cleaning process involves making the dataset easy to use and understand, and carefully examining each variable to document distributions and identify patterns that may bias the analysis. The resulting dataset will contain only the variables collected in the field, and no modifications to data points will be made, except for corrections of mistaken entries. You may have more data tables in your dataset now then originally received, and they may have a different format, but the information contained is still the same. Apart from the cleaned dataset (or datasets) itself, cleaning will also yield extensive documentation describing it.

Data cleaning yields in-depth understanding of the contents and structure of your data. This knowledge will be key to correctly constructing and analyzing final indicators, which we cover in the next chapter. Do not rush through this step! It is common for data cleaning to be the most time-consuming task in a project. In this section, we introduce some concepts and tools to make it more efficient and productive. The section is separated into three subtopics: exploring the data, making corrections, and recoding and annotating. They are separated here because they are different in nature, and should be kept separated in your code. In practice, however, they may all done at the same point in time.

### Exploring the data

The first time you interact with the data contents is during quality checks. However, these checks are are usually time-sensitive, and there may not be time to explore the data at length. During data cleaning, on the other hand, you will need to inspect each variable closely. Use tabulations, summary statistics, histograms and density plots to understand the structure of data, and look for patterns or irregularities. Think critically about what you see. You should ensure that the numerical values that appear are consistent with the information the variable represents. You should ensure that statistical distributions look realistic and are not highly clumped or skewed. You should confirm that related variables are consistent with each other. You should check for outliers and missing values. Then, you should assess if unusual or unexpected distributional patterns of any of these characteristics could be caused by data entry errors.

At this point, it is more important to document your findings than to directly address any irregularities found. There is a very limited set of changes that should be made to the raw data during cleaning. They are described in the next two sections, and are usually applied to each variable as you examine it. Most of the transformations that result in new variables will be done during data construction, a process discussed in the next chapter. For now, focus on creating a record of what you observe, and extensively documenting the data being explored. You will use this documentation when discussing with your team how to address irregularities once you get to the construction stage. This material will also be valuable during exploratory data analysis.

### Correcting data points

% Correct or not correct As mentioned earlier, corrections to issues identified during data quality monitoring are the only changes done to individual data points during the data cleaning stage. However, there is a lot of discussion about whether one should modify such data points at all. Some argue that follow-ups to the issues identified are costly and add limited value. Since it is not possible to check each and every possible data entry error, doing so can create a false sense of security from issues identified on a few main variables. Additionally, manually-inspected data may suffer from considerable inspector variability. In many cases, the main purpose of data quality checks is to detect fraud and identify problems with data collection protocols. On the other hand, there is also an argument to be made against keeping clear typing errors or not correcting missing values. We recommend correcting any entries that are clearly identified as errors. However, there is some subjectivity involved in deciding which cases fall into this category. A common rule of thumb is to include the set of corrections which are based on information that you have privileged access to and other research teams would not be able to make, and no more. Making this such decisions involve deep knowledge of the data and the particular circumstances or each research project.

Whether you decide to modify your data or not, you must keep a careful record of all issues that you identify. If no data points are modified, it may still be helpful to add flags to observations containing potentially problematic values, so you can verify how they affect results during analysis. If your team decides to follow up on and correct these issues, the follow-up process must also be thoroughly documented. Be very careful not to include confidential information in documentation that is not securely stored, or that you intend to release as part of a replication package or data publication. Finally, remember not to make changes directly to the raw data. Instead, any corrections must be done as part of data cleaning, applied through code, and saved to a new intermediate dataset.

### Recoding and annotating data

% Why recoding and annotating data are important The cleaned dataset is the starting point of data analysis. It will be extensively manipulated to construct analysis indicators, so it is important for it to be easily processed by statistical software. To make the analysis process smoother, anyone opening this dataset for the first time should have all the information needed to interact with it, even if they were not involved in the acquisition or cleaning process. This will save them time going back and forth between the dataset and its accompanying documentation.

% Encoding variables Often times, datasets are not imported into statistical software in the most efficient format. The most common example is string (text) variables: categorical variables and open-ended responses are often read as strings. However, variables in this format cannot be used for quantitative analysis. Therefore, categorical variables must be transformed into other formats, such as factors in R and labeled integers in Stata. Additionally, open-ended responses stored as strings usually have a high risk of including identifying information, so cleaning them requires extra attention. The choice names in categorical variables (called value labels in Stata and levels in R) should be accurate, concise, and directly linked to the data collection instrument. Adding choice names to categorical variables makes it easier to understand your data as you explore it, and thus reduces the risk of small errors making their way through into the analysis stage.

% Recoding missing values In survey data, it is common for non-responses such as “Don’t know” and “Declined to answer” to be represented by arbitrary survey codes. The presence of these values could bias your analysis, since they don’t represent actual observations of an attribute. They need to be turned into missing values. However, the fact that a respondent didn’t know how to answer a question is also useful information that would be lost by simply omitting all information. In Stata, this information can be elegantly conserved using extended missing values.

% Labeling variables We recommend that the cleaned dataset be kept as similar to the raw data as possible. This is particularly important regarding variable names: keeping them consistent with the raw data makes data processing and construction more transparent. Unfortunately, not all variable names are informative. In such cases, one important piece of documentation makes the data easier to handle: the variable dictionary. When a data collection instrument (for example a questionnaire) is available, it is often the best dictionary one could ask for. But even in these cases, going back and forth between files can be inefficient, so annotating variables in a dataset is extremely useful. In Stata, `variable labels} must always be present in a cleaned dataset. They should include a short and clear description of the variable. A lengthier description, that may include, for example, the exact wording of a question, may be added through variable notes. In R, it is less common to use variable labels, and a separate dataset with a variable dictionary is often preferred, but data frame attributes can be used for the same purpose.

Finally, any information that is not relevant for analysis may be removed from the dataset. In primary data, it is common to collect information for quality monitoring purposes, such as notes, duration fields and surveyor IDs. Once you are past the quality monitoring phase, these variables may be removed from your dataset. In fact, to make the data easier to handle, you may choose to start from a minimal set of variables, and add new ones as you clean them. To ensure the cleaned dataset file doesn’t get too big to be handled, use commands such as compress in Stata so the data is always stored in the most efficient format.

% Cleaning tools: iecodebook, tidyverse Although all these tasks are key to making the data easy to use, implementing them can be quite repetitive and create convoluted scripts. The iecodebook command suite, part of the iefieldkit Stata package, is designed to make some of the most tedious components of this process more efficient.  It also creates a self-documenting workflow, so your data cleaning documentation is created alongside that code, with no extra steps. As far as we know, currently there are no similar resources in R. However, the tidyverse packages compose a consistent and useful grammar to perform the same tasks.

### Documenting data cleaning

Throughout the data cleaning process, you will often need extensive inputs from the people responsible for data collection. Sometimes this is your research team, but often it will be someone else. It could be a survey team, the government ministry responsible for administrative data systems, the technology firm that generated remote sensing data, etc. Regardless of who originally collected the data, you should acquire and organize all documentation of how the data was generated. What type of documentation that is available depends on how the data was collected. For original data collection, this should include field protocols, data collection manuals, survey instruments, supervisor notes, and data quality monitoring reports. For secondary data, you should try to get the same type of information, but that is often not possible unless the data source is a well managed data publication. Independently of its exact composition, the data documentation should be stored alongside your data dictionary and codebooks. You will probably need these files during analysis, and they should be published along with the data, so other researchers may use them for their analysis as well.

## Looking ahead

This chapter introduced a workflow of formatting, cleaning, and quality assurance for the data that you obtained from the field or from partners, illustrated in the figure that follows. These tasks create your first research outputs using original data: an analysis-ready dataset. This dataset is well-structured to describe your units of analysis (it is “tidy”), it faithfully represents the measurements it was intended to collect, and it does not expose the identities of the people described by it. You have also now taken the time to fully understand the patterns and structures in your data, and annotated and labeled them for your use and use by others. Combined with the data map, this dataset will be the fundamental starting point for all analysis work. In the next chapter, we will walk through the steps needed to run the analyses originally specified in your analysis plan and answer your research question – or perhaps to find out you now have even more questions.

Data cleaning tasks and outputs

# Constructing and analyzing research data

The process of data analysis is typically a back-and-forth discussion between people with differing skill sets. To effectively do this in a team environment, data, code and outputs must be well-organized and documented, with a clear system for version control, analysis scripts that can be run by all team members, and creation of research outputs fully automated. Putting in time upfront to structure the data analysis workflow in a reproducible manner pays substantial dividends throughout the process. Similarly, documenting research decisions made during data analysis is essential not only for research quality and transparency, but also for the smooth implementation of a project.

In this chapter, we discuss the necessary steps to transform cleaned raw data into informative analysis outputs such as tables and figures. The suggested workflow starts where the last chapter ended: with the outputs of data cleaning. The first section covers variable construction: transforming the raw data into economically meaningful indicators. The second section discusses the analysis code itself. We do not offer instructions on how to conduct specific analyses, as that is determined by research design, and there are many excellent existing guides. Rather, we discuss how to structure and document data analysis that is easy to follow and understand, for both the full research team members and research consumers. The final section discusses ways to automate common outputs so that your work is fully reproducible.

## Creating analysis datasets

For this chapter, we assume you are starting from one or multiple well-documented tidy datasets. We also assume that these datasets have gone through thorough quality checks and incorporate any corrections needed. The next step is to construct the variables that you will use for analysis; that is, to transform the cleaned data into analysis-ready data. It’s possible the data is ready for analysis as acquired, but in most cases it needs to be prepared by integrating different datasets and creating derived variables (dummies, indices, and interactions, to name a few ). The derived indicators you will construct should be planned during research design, with the pre-analysis plan serving as a guide. During construction, data will typically be reshaped, merged, and aggregated to change the level of the data points from the unit of observation  in the raw data to the unit of analysis .

Each analysis dataset is built to answer an analysis question. If the sub-samples and units of observation vary for different pieces of the analysis, you will probably need to create many purpose-built analysis datasets. In such cases, it is not good practice to try to create a single “one-size-fits-all” analysis dataset. For a concrete example of what this means, think of an agricultural intervention that was randomized across villages and only affected certain plots within each village. The research team may want to run household-level regressions on income, test for plot-level productivity gains, and check if village characteristics are balanced. Having three separate datasets for each of these three pieces of analysis will result in cleaner, more efficient, and less error-prone analytical code than if you started from a single analysis dataset and repeatedly transformed it.

### Organizing data analysis workflows

Construction follows data cleaning and should be treated as a separate task for two reasons. First, this helps to clearly differentiate error corrections (necessary for all data uses) from creation of analysis indicators (necessary only for specific analyses). Second, it helps to ensure that variable definitions are consistent across datasets. For example, take a project that has a baseline and an endline survey. Unless the two data collection instruments are exactly the same, which is preferable but often not the case, the data cleaning for each of these rounds will require different steps, and therefore will be done separately. However, the analysis indicators must be constructed in the exact same way, so they are comparable. To do this, you will require at least two separate cleaning scripts, and a unified construction script. Maintaining one construction script guarantees that you will not accidentally make changes to an indicator from one round while forgetting to update the other.

When we visualize the research workflow, variable construction precedes data analysis, as derivative variables need to be created before they are analyzed. In practice, however, as you analyze the data, it is often useful to revisit construction, and explore different subsets and transformations of the data. Even if construction and analysis are done concurrently, you should always code them in separate scripts. If every script that creates a table starts by loading a dataset, subsetting it, and manipulating variables, any edits to construction need to be replicated in all scripts. This increases the chances that at least one of them will have a different sample or variable definition. Coding all variable construction and data transformation in a unified script, separate from the analysis code, prevents such problems and ensures consistency across different outputs.

### Integrating multiple data sources

To create the analysis dataset, it is typically necessary to combine information from different data sources or different datasets with a common source. For the next few paragraphs, we call such operations “merges”, but they are also commonly referred to as “data joins”. As discussed in Chapter 3, this process should be documented using data flowcharts, and different data sources should only be combined in accordance with the data linkage table. For example, you may merge administrative data with survey data in order to include demographic information in your analysis, or you may want to integrate geographic information in order to include location-specific controls. To understand how to perform such operations, you will need to consider the unit of observation for each dataset, and their respective identifying variables. Merges are frequent and complex operations, which makes them a common source of error. Whichever statistical software you are using, take the time to read through the help file of merge commands and make sure you understand their options and outputs.

When writing the code to implement merge operations, a few steps can help avoid mistakes. First, before writing code to combine the datasets, write pseudocode to understand which observations you expect to be matched or not, and why. When possible, determine exactly which and how many matched and unmatched observations should result from the merge. The best tool you have to understand this is the three components of the data map discussed in chapter 3. Second, think carefully about whether you want to keep matched and unmatched observations, or only specific matching outcomes (e.g. to create a balanced panel), and add that to the pseudocode as well. Finally, run the code to merge the datasets, and compare the outcome to your expectations. Add comments to explain any exceptions, and make it so the code will return an error in case unexpected results show up in future runs.

To avoid unintentional changes to your data, pay close attention to merge results. Two that require careful scrutiny are missing values and dropped observations. Make sure to read about how each command treats missing observations: are unmatched observations dropped, or are they kept with missing values? Whenever possible, add automated checks in the script that throw an error message if the result is different than what you expect, or you may not notice changes in the outcome after running large chunks of code. Document changes to the number of observations in your comments, and explain why they are happening. If your are subsetting your data by keeping only matched observations, write down the reason why the observations differ across datasets, as well as why you are only interested in those that matched. The same applies when you are adding new observations from the merged dataset.

Some merges of data with different units of observation are more conceptually complex. Examples include: overlaying road location data with household data, using a spatial match; combining school administrative data, such as attendance records and test scores, with student demographic characteristics from a survey; or linking a dataset of infrastructure access points, such as water pumps or schools, with a dataset of household locations. In these cases, a key part of the research contribution is figuring out a useful way to combine the datasets. Since the conceptual constructs that link observations from the two data sources are important and can take many possible forms, it is especially important for the data integration to not be treated mechanically, and to be extensively documented, separately from other data construction tasks.

### Creating analysis variables

Once you have assembled variables from different sources into a single working dataset with the right raw information and observations, it’s time to create the derived indicators of interest for analysis. Before constructing new indicators, you must check and double-check units, scales, and value assignments of each variable that will be used. This is when you will use the knowledge of the data and the documentation developed during cleaning the most. First, check that all categorical variables have the same value assignment, such that labels and levels have the same correspondence across variables that use the same options. For example, it’s possible that in one question 0 means “no” and 1 means “yes”, while in another one the same answers were coded as 1 and 2. (We recommend coding binary questions as either 1 and 0 or TRUE and FALSE, so they can be used numerically as frequencies in means and as dummies in regressions. This often implies re-expressing categorical variables like gender as binary variables like woman.) Second, make sure that any numeric variables you are comparing are converted to the same scale or unit of measure: you cannot add one hectare and two acres and get a meaningful number. New variables should be assigned functional names, and the dataset ordered such that related variables are together. Adding notes to each variable will make your dataset more user-friendly.

At this point, you will also need to decide how to handle any outliers or unusual values identified during data cleaning. How to treat outliers is a research question. There are multiple possible approaches, and the best choice for a particular case will depend on the objectives of the analysis. Whatever your team decides, make sure to explicitly note what the decision was and how it was made. Results can be sensitive to the treatment of outliers, so keeping the original variable in the dataset will allow you to test how much it affects your outputs. All these points also apply to imputation of missing values and other distributional patterns. As a general rule, never overwrite or delete original data during the construction process. Always create derived indicators with new names.

Two features of data create additional complexities when constructing indicators: research designs comprising multiple units of observation and analysis, and designs with repeated observations of the same units over time. When your research involves different units of observation, creating analysis datasets will probably mean combining variables measured at these different levels. If you followed our recommendations from Chapter 5, this means combining variables that are included in different tidy datasets. To make sure constructed variables are consistent across datasets, we recommend that each indicator be constructed in the dataset corresponding to its unit of observation. Once we have indicators at each unit of observation, they may be aggregated and/or merged to different units of analysis. Take the example of a project that acquired data at both the student and teacher levels. You may want to analyze the performance of students on a test while controlling for teacher characteristics. This can be done by assigning the teacher-level indicators to all the students in the corresponding class. Conversely, you may want to include average student test scores in the analysis dataset containing teacher-level variables. To do so, you would start from the constructed dataset at student level, average (using commands like collapse in Stata and summarise in R) the test scores of all students taught by the same teacher, and merge this teacher-level aggregate measure onto the original teacher dataset. You should be mindful of two aspects while performing such operations: the first is the correspondence between identifying variables at different levels, which should be documented in the data linkage table; the second is that they will necessarily involve merges, so all the steps outlined in the previous section should be applied.

Finally, creating a panel with survey data involves additional timing complexities. It is common to construct indicators soon after receiving data from a new survey round. However, creating indicators for each round separately increases the risk of using different definitions each time. Having a well-established definition for each constructed variable helps prevent that mistake, but the best way to guarantee it won’t happen is to create the indicators for all rounds in the same script. Say you constructed some analysis variables after baseline, and are now receiving midline data. Then the first thing you should do is create a cleaned panel dataset, ignoring the previous constructed version of the baseline data. Our team created iefieldkit’s iecodebook append subcommand to help you reconcile and append data from cleaned survey rounds or similar data collected from different contexts.  This is done by completing an Excel sheet to indicate what changes in names, value assignments, and value labels should be made so the data is consistent across rounds or settings. By doing so, you are also creating helpful documentation about your data work. Once data tables are consistently appended, adapt your construction script so it can be used on the complete panel dataset. In addition to preventing inconsistencies and documenting your work, this process will also save you time and give you an opportunity to review your original code.

### Documenting variable construction

Because data construction involves translating concrete observed data points to measures of abstract concepts, it is important to document exactly how each variable is derived or calculated. Careful documentation is closely linked to the research principles discussed in the first chapter. It makes research decisions transparent, as anyone can read about how you defined each variable in your analysis, and what was the reasoning behind these decisions. By reading the documentation, someone unfamiliar with the project should be able to understand the contents of the analysis datasets, the steps taken to create them, and the decision-making process through your documentation. Ideally, they should also be able reproduce your steps and recreate the constructed variables. Therefore, documentation is an output of construction as relevant as the code and data, and it is good practice for papers to have an accompanying data appendix listing analysis variables and their definitions.

The development of construction documentation is a good opportunity to have a wider discussion with your team about creating protocols for variable definition, which will guarantee that indicators are defined consistently across projects. You must have a detailed account of how variables are created. This will be implemented in your code, but you should still add comments explaining in human language what you are doing and why. This is a crucial step both to prevent mistakes and to guarantee transparency. To make sure that these comments can be more easily navigated, it is wise to start writing a variable dictionary as soon as you begin making changes to the data. The variable dictionary can be saved in an Excel spreadsheet, a Word document, or even a plain text file. Whatever format it takes, it should carefully record how specific variables have been combined, recoded, and scaled. Whenever relevant, the code should point to these files to indicate where the definition are being implemented.

The iecodebook export subcommand is a good way to ensure you have easy-to-read documentation. When all your final indicators have been created, you can use it to list all variables in the dataset in an Excel sheet. You can then add the variable definitions to that file to create a concise metadata document. Take this opportunity to review your notes and make sure that your code is implementing exactly what is described in the documentation.

## Writing analysis code

After data is cleaned and indicators are constructed, you are ready to start analyzing the data.  There are many existing resources for data analysis and statistical methods, such as R for Data Science;(Wickham and Grolemund 2017) A Practical Introduction to Stata;(McGovern 2012) Mostly Harmless Econometrics; and Causal Inference: The Mixtape. We focus on how to structure data analysis code and files, rather than how to conduct specific analyses.

### Organizing analysis code

The analysis stage usually starts with a process we call exploratory data analysis. This is when you are first looking for patterns in your data, creating descriptive graphs and tables, and trying different tests to understand your results. It progresses into final analysis when your team starts to decide which are the “main results”, or those that will make it into a research output. The way you deal with code and code outputs for exploratory and final analysis is different. During the exploratory stage, you will be tempted to write lots of analysis into one big, impressive, start-to-finish script. While this is fine when you are writing your research stream of consciousness into code, it leads to poor practices in the final code such as not clearing the workspace and not loading a fresh dataset before each analysis task.

To avoid mistakes, it’s important to take the time to organize the code that you want to keep, that is, the final analysis code, in an organized manner. The result is a curated set of polished scripts that will be part of a reproducibility package. A well-organized analysis script starts with a completely fresh workspace and, for each output it creates, explicitly loads data before analyzing it. This setup encourages data manipulation to be done earlier in the workflow (that is, in separate cleaning and construction scripts). It also prevents the common problem of having analysis scripts that depend on other analysis scripts being run before them. Such dependencies tend to require manual instructions for all necessary chunks of code to be run in the right order. We encourage you to code each task so it is completely independent of all other code, except for the master script. You can go as far as coding every output in a separate script, but the key is making sure you know which datasets are used for each output, and which code chunks implement each piece of analysis.

There is nothing wrong with code files being short and simple. In fact, analysis scripts should be as simple as possible, so whoever is reading them can focus on the concepts, not the coding. Research questions and statistical decisions should be incorporated explicitly in the code through comments, and their implementation should be easy to detect from the way the code is written. This includes clustering, sampling, and controlling for different variables, to name a few. If you have multiple analysis datasets, each of their names should be descriptive of the sample and unit of observation they contain. As your team comes to a decision about model specification, you can create functions and globals (or objects) in the master script to use across scripts. This is a good way to make sure specifications are consistent throughout the analysis. It also makes your code more dynamic, as it’s easy to update specifications and results through a master file without changing every script.

To create this setup, you will need to make sure that you have an effective data management system, including file naming, organization, and version control. Just as for the analysis datasets, you should name each of the individual analysis files descriptively. Code files such as spatial-diff-in-diff.do, matching-villages.R, and summary-statistics.py are clear indicators of what each file is doing, and allow you to find code quickly. If you intend to numerically order the script files to correspond to exhibits as they appear in a paper or report, leave this to near publication time, as you will constantly re-order them during data analysis.

### Visualizing data

Data visualization is increasingly popular, and is becoming a field in its own right. Although the same principles for coding exploratory and final data analysis apply to visualizations, creating them is usually more difficult than running a regression and exporting its results into a table. We attribute some of the difficulty of creating good data visualization to the difficulty of writing code to create them. The amount of customization necessary to create a nice graph can lead the relevant commands to become quite intricate. Making a visually compelling graph would already be hard enough if you didn’t have to go through many rounds of searching and reading help files to understand a command’s graphical options syntax. Although getting each specific element of a graph to look exactly the way you want can be hard, the solution to such problems is usually a single well-written search away, and we recommend you leave these details as the very last adjustments to make. In our experience, the trickiest part of using plotting commands is getting the data into the right format. Though both Stata and R have plotting functions that graph summary statistics, a good rule of thumb is to ensure that each observation in your dataset corresponds to one data point in your desired visualization. This may seem simple, but often requires the aggregation and reshaping operations discussed earlier in this chapter.

Based on DIME’s accumulated experience creating visualizations for impact evaluations, our team has developed a few resources to facilitate this workflow. First of all, we maintain easily-searchable data visualization libraries for both Stata and R. These libraries feature curated data visualization examples, along with source code and example datasets, so you get a good sense of what your data should look like before you can start writing code to create a visualization. The ietoolkit package also contains two commands to automate common impact evaluation graphs: iegraph plots the values of coefficients for treatment dummies, and iekdensity displays the distribution of an outcome variable across groups and adds the treatment effect as a note.

## Creating reproducible tables and graphs

A great number of outputs will be created during the course of a project. These will include both raw outputs such as tables and graphs and final products such as presentations, papers and reports. During exploratory analysis, your team will consider different approaches to answer research questions and present answers. Though it is best to be transparent about different specifications tried and tests performed, only a few will ultimately be considered “main results”. These will be exported from the statistical software. That is, they will be saved as tables and figures in format that is easier to interact with. For example, saving graphs as images will allow your team to quickly see them, as well as to add them as exhibits to other documents. When the first of these code outputs are being created, agree on where to store them, what software and formats to use, and how to keep track of them. This discussion will save you time and efforts on two fronts: you will spend less time formatting and polishing tables and graphs that will not make their way into final research products; and you will remember the different paths your team has already taken, so you don’t do the same thing twice. This section will take you through key elements to keep in mind when making workflow decisions and outputting results.

### Managing outputs

Decisions about storage of outputs are limited by technical constraints, and dependent on file format. Plain text formats like .tex and .csv and should be managed through version control systems like Git, as discussed in Chapter 2. Binary outputs like Excel files, PDFs, PowerPoints, or Word documents, on the other hand, should be kept in a synced folder. Exporting all raw outputs as plain text files, which can be done through all statistical software, facilitates the identification of changes in results. When you re-run your code from the master script, the outputs will be overwritten, and any changes (for example, in coefficients or number of observations) will be automatically flagged for you or a reviewer to check. Tracking changes to binary files is more cumbersome. They they use more space, which may cause slow down the cloud syncing. There may be exceptions to this general rule depending on the Git client you are using. GitHub Desktop, for example, displays changes in common binary image formats such as PNG files in an accessible manner.

You will need to update your outputs frequently. And if you have tried to recreate a result after a few months, you probably know that it can be hard to remember where the code that created it was saved. File naming conventions and code organization, including easily searchable file names and comments, play a key role in not re-writing scripts again and again. We recommend maintaining one “final” analysis folder and one folder with draft code or exploratory analysis. The latter contains pieces of code that are stored for reference, but not cleaned up to be included in any final outputs. Once an output presents a result in the clearest manner possible, it should be renamed and moved to the “final analysis” folder. It’s typically desirable to have the names of outputs and scripts linked – so, for example, factor-analysis.do creates factor-analysis.eps and so on. Document output creation in the master script that runs your code, so that before the line that runs a particular analysis script there are a few lines of comments listing datasets and functions that are necessary for it to run, as well as all outputs created by that script.

Knowing how your code outputs will be used will help you decide the best format to export them. You can often save figures into different formats, such as .eps, .png, .pdf or .jpg. However, the decision between using Office Suite software such as Word and Power Point versus LaTeX and other plain text formats may influence how you write your code, as this choice often implicates in the use of a particular command. We strongly recommend that you chose software to create final products that can be linked to raw outputs in such a way that they are updated in the paper or presentation every time changes are made to them. We broadly call files that have this feature dynamic documents, and they will be discussed in more detail in the final section of this chapter.

### Exporting analysis outputs

As briefly discussed in the previous section, you do not necessarily have to export each and every table and graph created during exploratory analysis. Most statistical software allow you to review results interactively, and this is often preferred at this stage. Final analysis scripts, on the other hand, must export outputs that are ready to be included in a paper or report. No manual edits, including formatting, should be necessary after exporting final outputs. Manual edits are difficult to reproduce; the less you need them, the more reproducible your output is. You may think that it’s not worth coding a small formatting adjustment, but you will inevitably need to make changes to the output, and automating them will save you time by the end of the process. (However, don’t spend much time formatting tables and graphs until you have come to a decision about which will be used for your final product. ) Polishing final outputs can be a time-consuming process, and you want to do it as few times as possible.

We cannot stress this enough: do not set up a workflow that requires copying and pasting results. Copying results from Excel to Word is error-prone and inefficient. Copying results from a software console is risk-prone, even more inefficient, and totally unnecessary. The amount of work needed in a copy-paste workflow increases rapidly with the number of tables and figures included in a research output, and so do the chances of having the wrong version of a result in a paper or report.

There are numerous commands to export outputs from both R and Stata. Some examples are estout,(Jann 2005, @estout07) outreg2,(Wada 2014 ) and outwrite in Stata; and stargazer, huxtable, and ggplot2’s ggsave in R. They allow for a wide variety of output formats. We recommend using formats that are accessible and, whenever possible, lightweight. Accessible means that it’s easy for other people to open them. In Stata, that would mean always using graph export to save images as .jpg, .png, .pdf, etc., instead of graph save, which creates a .gph file that can only be opened by Stata. Some publications require “lossless” TIFF or EPS files, which are created by specifying the desired extension. Whichever format you decide to use, remember to always specify the file extension explicitly. For tables, there are fewer file format options. Given our recommendation to use dynamic documents, which will be discussed in more detail both in the next section and in Chapter 7, exporting tables to .tex is preferred. Excel .xlsx and .csv are also commonly used, but often require the extra step of copying the tables into the final output. The ietoolkit package includes two commands to export formatted tables, automating the creation of common outputs and saving time for research. iebaltab creates and exports balance tables to Excel or LaTeX. ieddtab does the same for difference-in-differences regressions.

If you need to create a table with a very specific format that is not automated by any command you know, consider writing it manually (Stata’s filewrite and R’s cat(), for example, allow you to do that). This will allow you to write a cleaner script that focuses on the econometrics, and not on complicated commands to create and append intermediate matrices. Keep in mind that final outputs should be self-standing. This means it should be easy to read and understand them with only the information they contain. Make sure labels and notes cover all relevant information included in your code and comments that are not otherwise visible in the output. Examples of information that should be included in labels and notes include sample, unit of observation, unit of measurement, and variable definition.

## Increasing efficiency of analysis with dynamic documents

Dynamic documents are a broad class of tools that enable a streamlined, reproducible workflow. The term “dynamic” can refer to any document-creation technology that allows the inclusion of explicitly encoded linkages to raw output files. This means that, whenever outputs are updated, the next time the document is loaded or compiled, it will automatically include all changes made to all outputs without any additional intervention from the user. This is not possible in tools like Microsoft Office, although there are tools and add-ons that produce similar functionality. In Word, by default, you have to copy and paste each object individually whenever tables, graphs, or other inputs have to be updated. This workflow becomes more complex as the number of inputs grows, increasing the likelihood of making mistakes or missing updates. Dynamic documents prevent this from happening by managing document compilation and inclusion of inputs in a single integrated process, so you can skip the copying and pasting altogether.

### Conducting dynamic exploratory analysis

If all team members working on a dynamic document are comfortable using the same statistical software, built-in dynamic document engines are a good option for exploratory analysis. With these tools, you can write both text (often in Markdown ) and code in the script, and the result will usually be a PDF or HTML file including code, text, and outputs. In our experience, many researchers find the entry cost to learning how to use these tools to be high. These types of dynamic document tools are typically best used by the team members working most closely with code, and can be great for creating exploratory analysis reports as you work on them, or paper appendices including large chunks of code and dynamically created graphs and tables. RMarkdown is the most widely adopted solution in R. Stata offers a built-in package for dynamic documents, dyndoc, and user-written commands such as markstat,(Rodriguez 2017 ) markdoc,(Haghish 2016 ), webdoc,(Jann 2017 ) and texdoc.(Jann 2016 ) The advantage of these tools in comparison with LaTeX is that they create full documents from within your scripts, so running the code and compiling the document is reduced to a single step.

Documents called “notebooks” (such as Jupyter Notebook ) work similarly, as they also use the underlying code that create the document. These tools are usually appropriate for short or informal documents because it tends to be difficult for those who are not familiar with them to edit the content, and they often don’t offer as extensive formatting options as, for example, Word. There are also other simple tools for dynamic documents that do not require direct operation of the underlying code or software, simply access to the updated outputs. An example of this is Dropbox Paper, a free online writing tool that can be linked to files in Dropbox which are automatically updated anytime the file is replaced. These have limited functionality in terms of version control and formatting, and may never include any references to confidential data, but they do offer extensive collaboration features, and can be useful for working on informal outputs. Markdown files on GitHub can also provide similar functionality through the browser, and are version controlled. However, as with other Markdown options, the need to learn a new syntax may discourage take up among team members who don’t work with GitHub more extensively.

Whatever software you are using, what matters is that you make sure to implement a self-updating process for table and figures. We have given a few recommendations as to what we believe to be best practices, but you will need to find out what works for your team. If your team has decided to use Microsoft Office, for example, there are still a few options to avoid problems with copy-pasting. The easiest solution may be for the less code-savvy members of the team to develop the text of the final output pointing to exhibits that are not included inline. If all figures and tables are presented at the end of the file, whoever is developing the code can export them into a Word document using Markdown, so at least this part of the file can be quickly updated when the results change. Finally, statistical programming languages can now often directly export to these formats, such as using the putexcel and putdocx commands in Stata, which can update or respect formatting in Office documents.

### Using LaTeX for dynamic research outputs

Though formatted text software such as Word and PowerPoint are still prevalent, researchers are increasingly choosing to prepare final outputs like documents and presentations using LaTeX. LaTeX is a document preparation and typesetting system with a unique code syntax. While LaTeX has a significant learning curve, its enormous flexibility in terms of operation, collaboration, output formatting, and styling make it our preferred choice for most large technical outputs. In fact, LaTeX operates behind-the-scenes in many other dynamic document tools (discussed below). Therefore, we recommend that you learn LaTeX as soon as you are able to.

The main advantage of using LaTeX is that it updates outputs every time the document is compiled, while still allowing for text to be added and extensively formatted to publication-quality standards. Additionally, because of its popularity in the academic community, social scientists are more familiar with it than other dynamic documents tools, so the cost of entry for a team is often relatively low. Because .tex files are plain text, they can be version-controlled using Git. Creating documents in LaTeX using an integrated writing environment such as TeXstudio, TeXmaker or LyX is great for outputs that focus mainly on text and include figures and tables that may be updated. It is good for adding small chunks of code into an output. Finally, some journals make LaTeX templates available, so papers can be more easily be formatted into their specific layout.

## Looking ahead

This chapter discussed the steps needed to create analysis datasets and outputs from original data. By combining the observed variables of interest for the analysis (measurement variables) with the information in the data map describing the study design (research variables), you created original datasets ready for analysis, as shown in the figure below. Doing so is difficult, creative work, and it is impossible to be reproduced by another person without access to detailed records and explanations of how you interpreted and modified the data. You learned that code must be well-organized and well-documented to allow others to understand how research outputs were created and how those were used to answer the research questions. The final chapter of this book will provide a guide to assembling the raw findings into publishable work, as well as describing methods for making your data, code, documentation, and other research outputs accessible and reusable alongside your primary outputs.

Data analysis tasks and outputs

# Publishing reproducible research outputs

Publication typically involves many iterations of data, code, and code output files, with inputs from multiple collaborators. This process can quickly become unwieldy. It is in nobody’s interest for a skilled and busy researcher to spend days re-numbering figures, tables, or references (and it can take days) when a reasonable amount of up-front effort can automate the task. Similarly, simultaneous collaboration should not involve the repetitive and error-prone task of manually resolving sets of tracked-changes documents with conflicting edits. Furthermore, for most development data projects, completing a research output is not the end of the task. Academic journals increasingly require reproducibility packages containing the data, code, and supporting materials needed to recreate the results. DIME requires reproducibility packages for all published outputs. Replication materials represent an intellectual contribution in their own right, because they enable others to learn from your process and better understand the results you have obtained. If you have organized your analysis process according to the general principles outlined in earlier chapters, publication will not require substantial reorganization of the work you have already done. Hence, publication is the conclusion of the system of transparent, reproducible, and credible research we introduced from the very first chapter of this book.

In this chapter, we suggest tools and workflows for efficiently managing collaboration on research and policy outputs and ensuring reproducible results. The first section discusses how to use dynamic documents to collaborate on writing. The second section covers how to prepare and publish original data, an important research contribution in its own right. The third section provides guidelines for preparing functional and informative reproducibility packages. In all cases, we note that technology is rapidly evolving and that specific tools noted here may not remain cutting-edge, but the core principles involved in publication and transparency will endure.

## Publishing research papers and reports

% collaborating is easier with dynamic documents Development research is increasingly a collaborative effort. This reflects changes in the economics discipline overall: the number of sole-authored research outputs is decreasing, and the majority of recent papers in top journals have three or more authors. As a consequence, documents typically pass back and forth between several writers before they are ready for publication or release. As in all other stages of the research process, effective collaboration requires the adoption of tools and practices that enable version control and simultaneous contributions. This book, for example, was written in LaTeX and managed on GitHub. As we outlined in the previous chapter, dynamic documents are a way to simplify writing workflows: updates to code outputs that appear in these documents, such as tables and figures, can be passed in to the final research output in a single click, rather than copy-and-pasted or otherwise handled individually. Managing the writing process in this way improves organization and reduces error, such that there is no risk of materials being compiled with out-of-date results, or of completed work being lost or redundant.

### Using LaTeX for written documents

As we discussed in Chapter 6, the most widely used software for dynamically managing formal manuscripts and policy outputs is LaTeX. It is also becoming more popular for shorter documents, such as policy briefs, with the proliferation of skills and templates for these kinds of products. LaTeX uses explicit references to the file path of each input (such as tables and figures), which are reloaded from these locations every time the final document is compiled. This is not possible by default in, for example, Microsoft Word. There, you have to copy and paste each object whenever tables, graphs, or other inputs are updated. As time goes on, it becomes increasingly likely that a mistake will be made or something will be missed. In LaTeX, instead of writing in a “what-you-see-is-what-you-get” mode as you do in Word, you write plain text in a .tex file, interlaced with coded instructions formatting the document and linking to exhibits (similar to HTML). LaTeX manages tables and figures dynamically and includes commands for simple markup like font styles, paragraph formatting, section headers and the like. It includes special controls for footnotes and endnotes, mathematical notation, and bibliography preparation. It also allows publishers to apply global styles and templates to already-written material, reformatting entire documents in house styles with only a few keystrokes.

While LaTeX can produce complex formatting, this is rarely needed for academic publishing, as academic manuscripts will usually be reformatted based on the style of the publisher. (By contrast, policy and other self-produced documents may desire extensive typesetting and investments in custom templates and formatting.) In academia at least, it’s rarely worth the investment to go beyond basic LaTeX tools: the title page, sections and subsections, figures and tables, mathematical equations, bolding and italics, footnotes and endnotes, and, last but not least, references and citations. We acknowledge that many of these functionalities including dynamic updating of some outputs can be achieved in Microsoft Word through the use of plugins and careful workflows. If you can maintain such a workflow, that is an acceptable approach to the same problem, but we recommend moving towards adoption of LaTeX when it is possible for you and your team.

One of the most important tools available in LaTeX is the BibTeX citation and bibliography manager. BibTeX keeps all the references you might use in a .bib file, then references them using a simple command typed directly in the document. Specifically, LaTeX inserts references in text using the cite command. Once this is written, LaTeX automatically pulls all the citations into text and creates a complete bibliography based on the citations you used whenever you compile the document. The system allows you to specify exactly how references should be displayed in text (such as superscripts, inline references, etc.) as well as how the bibliography should be styled and in what order (such as Chicago, MLA, Harvard, or other common styles). The same principles that apply to figures and tables are therefore applied here: You can make changes to the references in one place (the .bib file), and then everywhere they are used they are updated correctly with one process. BibTeX is so widely used that it is natively integrated in Google Scholar. Since different publishers have different requirements, it is quite useful to be able to adapt this and other formatting very quickly, including through using publisher-supplied templates where available.

Because it follows a standard code format, LaTeX has one more useful trick: you can convert the raw document into Word or a number of other formats using utilities such as pandoc. Even though conversion to Word is required for a number of academic publishers and can even be preferred for some policy outputs, we still recommend using LaTeX to prepare these when possible. You should export to Word only at the final stage, when submitting materials. You can also use a CSL (Citation Styles Library) file for nearly any journal and have it applied automatically in this process. Therefore, even in the case where you are required to provide `.docx} versions of materials to others, or tracked-changes versions, you can create them effortlessly from a LaTeX document, then use external tools like Word’s compare feature to generate integrated track-changes versions when needed.

### Getting started with LaTeX as a team

Getting used to LaTeX can be challenging, but the control it offers over the writing process is invaluable. Because it is written in a plain text file format, .tex can be version-controlled using Git. This makes it possible to manage contributions and version histories using the same system we recommend for data work. DIME Analytics has created a variety of templates and resources that you can adapt for your own team. Integrated editing and compiling tools like TeXStudio and atom-latex offer the most flexibility to work with LaTeX in teams.

Although ultimately worth it, setting up LaTeX environments locally is not always simple, particularly if you are new to working with plain text code and file management. This is because LaTeX requires that all formatting be done in its special code language, and it is not always informative when you do something wrong. This can be off-putting very quickly for people who simply want to get to writing, and staff not used to programming may not easily acquire the necessary knowledge.

Cloud-based implementations of LaTeX can make it easier for your team to use LaTeX without all members having to invest in new skills or set up matching software environments, and can be particularly useful for first forays into LaTeX writing. One example of this is Overleaf. Most such sites offer a subscription feature with useful extensions and various sharing permissions, and some offer free-to-use versions with basic tools that are sufficient for a broad variety of applications, up to and including writing a complete academic paper with coauthors.

Cloud-based implementations of LaTeX have several advantageous features for teams compared to classic desktop installations. First, since they are completely hosted online, they avoid the inevitable troubleshooting required to set up a LaTeX installation on various personal computers run by the different members of a team. Second, they typically maintain a single, continuously synced, master copy of the document so that different writers do not create conflicted or out-of-sync copies, or need to deal with Git themselves to maintain that sync. Third, they typically allow collaborators to edit documents simultaneously, though different services vary the number of collaborators and documents allowed at each tier. Fourth, some implementations provide a “rich text” editor that behaves pretty similarly to familiar tools like Word, so that collaborators can write text directly into the document without worrying too much about the underlying LaTeX coding. Cloud services also usually offer a convenient selection of templates so it is easy to start up a project and see results right away without needing to know a lot of the code that controls document formatting.

Cloud-based implementations of LaTeX also have disadvantages. There is still some up-front learning required, unless you’re using the rich text editor. Continuous access to the internet is necessary, and updating figures and tables requires a bulk file upload that is tough to automate. Although some services offer ways to track changes and even to integrate a git workflow, doing version control is not as straightforward as using git locally. Finally, they also vary dramatically in their ability to integrate with file systems where you store your code and code outputs, and so you will need to practice an integrated workflow depending what is available to you. Some teams adopt cloud-based tools as a permanent solution, though our recommendation is to eventually shift to local editing and compiling using tools such as TexStudio and code editors like Atom.

## Preparing research data for publication

While we have focused so far on written materials, you must also consider how you will publish the data used in your research. The open science community at large sees data publication both as a citable output and as a necessary transparency measure. Fortunately, it is a conceptually simple task to produce and catalog the required materials. You should be prepared to catalog two separate collections. First, you should catalog the clean data with all variables corresponding directly to fields in the original dataset or data collection instrument (this will not be necessary if you are working with secondary data that was not produced by your team, but you will still need to carefully explain the process of acquiring this data). If you follow the steps outlined in Chapter 5, when you get to the publication stage you will have a cleaned data set and supporting documentation ready.

Second, you should separately catalog the analysis dataset used for the research output you are publishing. This is typically included in the replication package for the research output, and should assume that another researcher is starting work with only the published clean data in hand. The package should also include the data construction scripts that create transformed and derived indicators, project-specific information such as treatment assignment and other indicators generated directly by the research team (another example is constructed record linkages). If you followed the workflow recommended in Chapter 6, by the time you reach publication stage you will already have all necessary files and documentation at hand.

### De-identifying data for publication

Before publishing data, you should carefully perform a final de-identification. The objective of de-identification is to reduce the risk of disclosing confidential information in the published dataset. If you are following the workflow outlined in this book, you should have already removed direct identifiers as a first step after acquiring the data (see the discussion of initial de-identification in Chapter 5). For the final de-identification, you should additionally remove indirect identifiers, and assess the statistical disclosure risk of your data. Unlike direct identifiers, for which a link (or lack thereof) to public information is verifiable, indirect identifiers require an assessment of the likelihood that an individual can be singled out in the data and then linked to public information using combinations of available data. For example, seemingly innocuous variables such as US zip code, gender, and date of birth uniquely identify approximately 87% of the US population. In development data, information such as the size of a household, the ages and marital statuses of the household members, and the types of work or schooling they engage in may be more than enough to identify a person or family from a sufficiently small group.

A number of tools have been developed to help researchers de-identify data. At this stage, the World Bank’s sdcMicro tool, has a useful feature that allows you to assess the uniqueness of the records in your data. It produces simple measures of the identifiability of records from the combination of potentially indirectly identifying variables, and allows you to apply common information masking algorithms, such as binning, top-coding, and jittering data prior to release. You should determine how sensitive your results are to these transformations; it may be the case that masked data cannot be used for your reproducibility package.

There will almost always be a trade-off between accuracy and privacy. For publicly disclosed data, you should favor privacy. Stripping identifying variables from a dataset may not be sufficient to protect respondent privacy, due to the risk of re-identification. One solution is to add noise to data, as the U.S. Census Bureau has proposed. This makes the trade-off between data accuracy and privacy explicit. But there are not, as of yet, established norms for such “differential privacy” approaches: most approaches fundamentally rely on judging “how harmful” information disclosure would be. The fact remains that there is always a balance between information release (and therefore transparency) and privacy protection, and that you should engage with it actively and explicitly. The best thing you can do is make a complete record of the steps that have been taken so that the process can be reviewed, revised, and updated as necessary.

Removing variables results in loss of information, so the de-identification process requires careful assessment of the potential risk to the individual that could be caused by disclosure of their identity or personal information. This will vary widely depending on the types of information you are collecting and the overall vulnerability of the population. In extreme cases, where the population is highly vulnerable and combinations of information are highly specific, you may not be able to publicly release any data at all. You will still be expected to catalog and cite your data, even if you cannot release it publicly. In practice, this may mean publishing only a catalog entry providing information about the contents of the datasets and how future users might request permission to access them (even if you are not the person to grant that permission). In some cases, it may be possible to release the dataset but embargoing specific variables that are required for the analysis but cannot be released publicly. It may be necessary to grant access to the embargoed data for specific purposes, such as a computational reproducibility check required for publication, if done under careful data security protocols and approved by an IRB.

### Publishing research datasets

Publicly documenting all original data acquired as part of a research project is an important contribution in its own right. Cataloging and/or archiving original datasets is a significant contribution in addition to any publication of analysis results. Publicly releasing data allows other researchers to validate the mechanical construction of your results, investigate what other results might be obtained from the same population, and test alternative approaches or answer other questions. This fosters collaboration and may enable researchers to explore variables and questions that you do not have time to focus on otherwise.

The first step toward data publication is choosing the platform where you will publish your data. A variety of options exist; it is important to choose one that allows you to obtain a digital object identifier (DOI) for the location of your data (even if its URL changes), and a formal citation for your data, so you can reference it in other research outputs. Two common platforms for development data are the World Bank’s Development Data Hub and Harvard University’s Dataverse. The World Bank’s Development Data Hub includes a Microdata Catalog and a Geospatial Catalog, where researchers can publish data and documentation for their projects. The Harvard Dataverse publishes both data and code, and its Datahub for Field Experiments in Economics and Public Policy is especially relevant for impact evaluations. Both the World Bank Microdata Catalog and the Harvard Dataverse create data citations for deposited entries. DIME has its own collection of datasets in the Microdata Catalog, where data from our projects is published.

Once you have chosen a platform, you need to determine exactly what data you will publish. As mentioned earlier, there are typically two different types of data releases for a research project: complete (de-identified) original datasets and derivative datasets used for specific research outputs. Whether you can publish the original dataset depends on data ownership and licensing agreements. If the data was acquired through a survey that was contracted by the research team, the data most likely belongs to the research team, and therefore the team has publication rights for both the original and derivative data. If data was acquired from a partner through a licensing agreement, the terms of the license will determine publication rights. These datasets should match the survey instrument or source documentation as closely as possible, and should not include indicators constructed by the research team. Even if you do not have rights to publish the original data, you can typically publish derivative datasets prepared by the research team. These datasets usually contain only the constructed indicators and associated documentation, and should also be included in the replication package.

When publishing data, you will decide how the data may be used and what license you will assign to it. Make sure you understand the rights associated with any data release and communicate them to its future users. Material without a license may never be reused. You should prefer to offer a license that is explicit and details whether and how specific individuals may access the data. Terms of use available in the World Bank Microdata Catalog include, in order of increasing restrictiveness: open access, direct access, and licensed access. Open access data is freely available to anyone, and simply requires attribution. Direct access data is available to registered users who agree to use the data for statistical and scientific research purposes only, to cite the data appropriately, and not to attempt to identify respondents or data providers or link the data to other datasets that could allow for re-identification. Licensed access data is restricted to users who submit a documented application detailing how they will use the data and then sign a formal agreement governing data use. The user must be acting on behalf of an organization, which will be held responsible in the case of any misconduct.

Published data should be released in a widely recognized format. While software-specific datasets are acceptable accompaniments to the code (since those precise materials are probably necessary), you should also consider releasing datasets in plain text formats such as CSV files with accompanying codebooks, since these can be used by any researcher. Additionally, you should also release PDF or code versions of the data collection instrument or survey questionnaire so that readers can understand which data components are collected directly in the field and which are derived. With your analysis dataset, you should also release the code that constructs any derived measures from the clean dataset, so that others can learn from your work and adapt it as they like.

## Publishing a reproducible research package

Major journals now often require that you provide both the data and code required to recreate your results. Some even require being able to reproduce the results themselves before they will approve a paper for publication. If you are producing a policy output, such as an open policy analysis or some other type of material, you may also want to make your materials publicly reproducible. Even if your work is only meant for use inside your organization, having a final set of production materials is still a valuable output. This set of materials, taken together, is often referred to as a reproducibility package. If you have followed the workflows described in this book, preparing the replication package will only require a small amount of extra work. If not, creating this package may take some time. When the replication package is completed, whoever downloads it should be able to understand how your code produces results from your data and be able to reproduce them exactly by executing the included master script.

### Organizing code for reproducibility

Before releasing your code, you should edit it for content and clarity just as if it were written material. The purpose of releasing code is to allow others to understand exactly what you have done in order to obtain your results, and enable them to apply similar methods in future projects. Other researchers should be able to reproduce individual portions of your analysis by making only small adjustments to your code. In either a scripts folder or in the root directory, you should include a master script that allows someone else to run the entire project and re-create all raw code outputs by changing only a single line of code: the one setting the directory path. The code should both be functional and readable, through the use of a clear structure and extensive commenting. Code is often not written this way when it is first prepared, so it is important for you to review the content and organization so that a new reader can figure out what your code should do and how it does it. Making code clean and readable is often where you need to invest time prior to releasing your reproducibility package.

DIME requires all academic outputs to successfully pass a computational reproducibility check before being submitted for publication. We have adopted several practices and requirements to support the production of high-quality reproducibility packages. The materials for these practices are publicly available, so you can use them to check the reproducibility of your own work. This reproducibility check is initiated by submitting the Reproducibility Package Checklist. DIME projects are required to organize code with a master script, to facilitate handovers across team members and make the computational reproducibility check a one-click exercise. Compliance with these and other coding standards at DIME is monitored through quarterly peer code review rounds, which allows research assistants to improve their code and documentation as it is written, rather than revisiting it in a rush near publication time. DIME projects are also expected to use Git and GitHub to document project work and collaboration, and to keep the main branch up-to-date as a working edition.

Before publicly releasing a reproducibility package, it is essential to make sure that the code runs identically on your individual setup compared to a fresh installation of your software. To ensure that your code will run completely on a new computer, you must install any required user-written commands in the master script (for example, in Stata using ssc install or net install and in R adding code that gives users the option to install packages, including selecting a specific version of the package if necessary ). In many cases you can even directly provide the underlying code for any user-installed packages that are needed to ensure forward-compatibility. Make sure system settings like software version and memory settings are defined. The ieboilstart command in ietoolkit defines and applies these settings for a chosen Stata version.

Finally, make sure that code inputs and outputs are clearly identified. A new user should, for example, be able to easily find and quickly recreate any files generated by the code. It should be easy to locate an output in the code, and it should be easy to correspond code to its outputs. Code should be broken down into separate scripts as much as possible to minimize searching through long files. Someone reading the code should fairly easily be able to figure out what state the program will be in at any point without scrolling through hundreds of lines; similarly, they should not have to look in different files or faraway sections of code to make changes to outputs. Each file should be an understandable, independent selection of related processes. Readers should also be able to easily map all the outputs of the code to where they appear in the associated published material, so you must ensure ensure that the raw components of figures or tables are clearly identified. Documentation in the master script is often used to indicate this information. For example, code outputs should clearly correspond by name to an exhibit in the paper, and vice versa. (Supplying a compiling LaTeX document can support this.) Code and code outputs which are not used in the final paper should be removed from the final replication package, but still archived for transparency.

### Releasing a reproducibility package

Once your replication package is prepared for public release, you need to find a place to publish your materials. At the time of writing, there is no consensus on the best solution for publishing code, and there are a variety of archives and storage providers that cater to different needs. The technologies available are likely to change dramatically over the next few years; the specific solutions we mention here highlight some current approaches as well as their strengths and weaknesses.

Features to look for in a platform to release reproducibility packages include: the possibility to store data and documentation as well as code, the creation of a static copy of its content, that cannot be changed or removed, and the assignment of a permanent digital object identifier (DOI) link. Unlike data, code usually has few external constraints to publication. The research team owns the code in almost all cases, and code is unlikely to contain identifying information (though you must verify that it does not). Publishing code also requires assigning a license to it; most code publishers offer permissive licensing options. If you do not provide a license, no one can reuse your code. It is common to only require attribution and citation for code reuse, without putting any barriers or restrictions to accessing the code.

One option for creating and releasing a reproducibility package is GitHub. Making a public GitHub repository is completely free. It can hold any file types, provide a structured, compressed download of your whole project, and allow others to look at alternate versions or histories easily. It is straightforward to simply upload a fixed directory to GitHub, apply a sharing license, and obtain a URL for the whole package. There is a strict size restriction of 100MB per file and a restriction of 100GB on the size of the repository as a whole, so larger projects will need alternative solutions. However, GitHub is not the ideal platform on which to publish reproducibility packages. It is built to version control code, and to facilitate collaboration on it. It is not an archive, meaning that it does not guarantee the permanence of uploaded materials or the access URL, and it does not manage citations or non-code licenses by default. One suggestion is to combine GitHub with the Open Science Framework, as OSF can easily link to and import material from GitHub and apply a permanent URL, DOI, formal citation, general license, and archival services to it.

Other options include the Harvard Dataverse and ResearchGate. Any of these archival services is acceptable – the main requirement is that the system can handle the structured directory that you are submitting, and that it can provide a stable URL for your project and report exactly what, if any, modifications you have made since initial publication. You can even combine more than one tool if you prefer, as long as they clearly reference each other. For example, one could publish code and the corresponding license on GitHub and point to data published on the World Bank Microdata Catalog. Emerging technologies such as the “containerization” approach of CodeOcean offer to store both code and data in one repository, and also provide an online workspace in which others can execute and modify your code without having to download your tools and match your local environment. This is particularly useful over time, as packages and other underlying software may have changed since publication.

In addition to code and data, you may also want to release an author’s copy or preprint of the article itself along with these materials. Check with your publisher before doing so; not all journals will accept material that has been publicly released before its formal publication date, although, in most development research fields, the release of working papers is a fairly common practice. This can be done on a number of preprint websites, many of which are topic-specific. You can also use GitHub or OSF and link to the PDF file directly through your personal website or whatever medium you are sharing the preprint. We recommend against using file sharing services such as Dropbox or Google Drive for this purpose, as their access is more restrictive, and organizations limit access to platforms other than the one officially adopted.

Finally, any reproducibility package should include an overview of its contents and instructions on how to recreate your outputs. This is typically done in the form of a README file. A good README will guide the reader through all the items included in the package. Fortunately, a very good template for such documents is offered by a consortium of social science data editors.

## Looking ahead

This chapter described the culmination of all the efforts in data acquisition, cleaning, processing, and analyzing – the production of materials to share with the world that answer a scientific or policy question in a way that has never been done before. The figure included in this chapter provides an overview of all the outputs created by this stage. Making sure that everything you discovered and created is as broadly available and as easy to use as possible is the last step in producing scientific evidence from original data. This is the purpose of all the rigor, organization, and documentation we encourage and detail at every step of the process: since all your research materials are continuously organized, shareable, secure, documented, and readable, they are both valuable to you and others and easy to provide access to.

# Bibliography

Abowd, John M. 2018. “The U.S. Census Bureau Adopts Differential Privacy.” In Proceedings of the 24th Acm Sigkdd International Conference on Knowledge Discovery & Data Mining, 2867–7. ACM.

Adjognon, Guigonan Serge, Daan van Soest, and Jonas Guthoff. 2019. Reducing Hunger with Payments for Ecosystem Services (Pes): Experimental Evidence from Burkina Faso. The World Bank.

Alix-Garcia, Jennifer M, Katharine RE Sims, Victor Hugo Orozco-Olvera, Laura Costica, Jorge David Fernandez Medina, Sofia Romo-Monroy, and Stefano Pagiola. 2019. Can Environmental Cash Transfers Reduce Deforestation and Improve Social Outcomes? A Regression Discontinuity Analysis of Mexico’s National Program (2011–2014). The World Bank.

Angrist, Joshua D, and Jörn-Steffen Pischke. 2008. Mostly Harmless Econometrics: An Empiricist’s Companion. Princeton University Press.

———. 2010. “The Credibility Revolution in Empirical Economics: How Better Research Design Is Taking the Con Out of Econometrics.” Journal of Economic Perspectives 24 (2): 3–30.

Athey, Susan, and Guido W Imbens. 2017. “The Econometrics of Randomized Experiments.” Handbook of Economic Field Experiments 1: 73–140.

Baldwin, Kate, Shylock Muyengwa, and Eric Mvukiyehe. 2017. Reforming Village-Level Governance via Horizontal Pressure: Evidence from an Experiment in Zimbabwe. The World Bank.

Baldwin, Kate, and Eric Mvukiyehe. 2015. “Elections and Collective Action: Evidence from Changes in Traditional Institutions in Liberia.” World Politics 67 (4): 690–725.

Banerjee, Abhijit, Eliana La Ferrara, and Victor Orozco. 2019. “Entertainment, Education, and Attitudes Toward Domestic Violence.” In AEA Papers and Proceedings, 109:133–37.

Bedoya, Guadalupe, Aidan Coville, Johannes Haushofer, Mohammad Razaq Isaqzadeh, and Jeremy Shapiro. 2019. No Household Left Behind: Afghanistan Targeting the Ultra Poor Impact Evaluation. The World Bank.

Begg, Colin, Mildred Cho, Susan Eastwood, Richard Horton, David Moher, Ingram Olkin, Roy Pitkin, et al. 1996. “Improving the Quality of Reporting of Randomized Controlled Trials: The CONSORT Statement.” JAMA 276 (8): 637–39.

Benhassine, Najy, David McKenzie, Victor Pouliquen, and Massimiliano Santini. 2018. “Does Inducing Informal Firms to Formalize Make Sense? Experimental Evidence from Benin.” Journal of Public Economics 157: 1–14.

Benschop, Thijs, Cathrine Machingauta, and Matthew Welch. 2019. “Statistical Disclosure Control: A Practice Guide.”

Bertrand, Marianne, Bruno Crépon, Alicia Marguerie, and Patrick Premand. 2017. Contemporaneous and Post-Program Impacts of a Public Works Program: Evidence from côte d’Ivoire. World Bank.

Bierer, Barbara E, Mark Barnes, and Holly Fernandez Lynch. 2017. “Revised ‘Common Rule’ Shapes Protections for Research Participants.”

Bjärkefur, Kristoffer, Luı́za Cardoso de Andrade, and Benjamin Daniels. 2020. “Iefieldkit: Commands for Primary Data Collection and Cleaning.” The Stata Journal 20 (4): 892–915.

Calderon, Gabriela, Leonardo Iacovone, and Laura Juarez. 2017. “Opportunity Versus Necessity: Understanding the Heterogeneity of Female Micro-Entrepreneurs.” The World Bank Economic Review 30 (Supplement_1): S86–S96.

Camerer, Colin F, Anna Dreber, Eskil Forsell, Teck-Hua Ho, Jürgen Huber, Magnus Johannesson, Michael Kirchler, et al. 2016. “Evaluating Replicability of Laboratory Experiments in Economics.” Science 351 (6280): 1433–6.

Carril, Alvaro. 2017. “Dealing with Misfits in Random Treatment Assignment.” The Stata Journal 17 (3): 652–67.

Chang, Andrew C, and Phillip Li. 2015. “Is Economics Research Replicable? Sixty Published Papers from Thirteen Journals Say ’Usually Not’.” Available at SSRN 2669564.

Christensen, Garret, and Edward Miguel. 2018. “Transparency, Reproducibility, and the Credibility of Economics Research.” Journal of Economic Literature 56 (3): 920–80.

Coville, Aidan, Vincenzo Di Maro, Felipe Alexander Dunsch, and Siegfried Zottel. 2019. The Nollywood Nudge: An Entertaining Approach to Saving. The World Bank.

Cunningham, Scott. 2018. “Causal Inference: The Mixtape.” Manuscript.

Cusolito, Ana Paula, Ernest Dautovic, and David McKenzie. 2018. Can Government Intervention Make Firms More Investment-Ready? A Randomized Experiment in the Western Balkans. The World Bank.

Daniels, Benjamin. 2019. “OUTWRITE: Stata Module to Consolidate Multiple Regressions and Export the Results to a. Xlsx,. Xls,. Csv, or. Tex File.”

Daniels, Benjamin, Amy Dolinger, Guadalupe Bedoya, Khama Rogo, Ana Goicoechea, Jorge Coarasa, Francis Wafula, Njeri Mwaura, Redemptar Kimeu, and Jishnu Das. 2017. “Use of Standardised Patients to Assess Quality of Healthcare in Nairobi, Kenya: A Pilot, Cross-Sectional Study with International Comparisons.” BMJ Global Health 2 (2): e000333.

De Andrade, Gustavo Henrique, Miriam Bruhn, and David McKenzie. 2013. A Helping Hand or the Long Arm of the Law? Experimental Evidence on What Governments Can Do to Formalize Firms. The World Bank.

Duflo, Esther, Abhijit Banerjee, Amy Finkelstein, Lawrence F Katz, Benjamin A Olken, and Anja Sautmann. 2020. “In Praise of Moderation: Suggestions for the Scope and Use of Pre-Analysis Plans for RCTs in Economics.” National Bureau of Economic Research.

Duflo, Esther, Rachel Glennerster, and Michael Kremer. 2007. “Using Randomization in Development Economics Research: A Toolkit.” Handbook of Development Economics 4: 3895–3962.

Duvendack, Maren, Richard Palmer-Jones, and W Robert Reed. 2017. “What Is Meant by ‘Replication’ and Why Does It Encounter Resistance in Economics?” American Economic Review 107 (5): 46–51.

Fernandes, Ana M, Russell Hillberry, and Alejandra Mendoza Alcántara. 2015. Trade Effects of Customs Reform: Evidence from Albania. The World Bank.

Fernandes, Ana M, Russell Hillberry, and Alejandra Mendoza Alcantara. 2017. An Evaluation of Border Management Reforms in a Technical Agency. The World Bank.

Gelman, Andrew, and Eric Loken. 2013. “The Garden of Forking Paths: Why Multiple Comparisons Can Be a Problem, Even When There Is No ‘Fishing Expedition’ or ‘P-Hacking’ and the Research Hypothesis Was Posited Ahead of Time.” Department of Statistics, Columbia University.

Gibson, Mike, and Anja Sautmann. 2020. “Introduction to Randomized Evaluations.” https://www.povertyactionlab.org/resource/introduction-randomized-evaluations.

Glewwe, Paul, and Margaret E Grosh. 2000. Designing Household Survey Questionnaires for Developing Countries: Lessons from 15 Years of the Living Standards Measurement Study. World Bank.

Goldstein, Markus, Kenneth Houngbedji, Florence Kondylis, Michael O’Sullivan, and Harris Selod. 2015. Formalizing Rural Land Rights in West Africa: Early Evidence from a Randomized Impact Evaluation in Benin. The World Bank.

Haghish, E. F. 2016. “Markdoc: Literate Programming in Stata.” Stata Journal 16 (4): 964–988(25). http://www.stata-journal.com/article.html?article=pr0064.

Hamermesh, Daniel S. 2007. “Replication in Economics.” Canadian Journal of Economics/Revue Canadienne d’économique 40 (3): 715–33.

Healy, Kieran. 2018. Data Visualization: A Practical Introduction. Princeton University Press.

Hlavac, Marek. 2015. “Stargazer: Beautiful LATEX, HTML and ASCII Tables from R Statistical Output.”

Hoces de la Guardia, Fernando, Sean Grant, and Edward Miguel. 2018. “A Framework for Open Policy Analysis.” Science and Public Policy.

Ioannidis, John PA. 2005. “Why Most Published Research Findings Are False.” PLoS Medicine 2 (8): e124.

Ioannidis, John PA, Tom D Stanley, and Hristos Doucouliagos. 2017. “The Power of Bias in Economics Research.” The Economic Journal.

Jann, B. 2016. “Creating Latex Documents from Within Stata Using Texdoc.” Stata Journal 16 (2): 245–263(19). http://www.stata-journal.com/article.html?article=pr0062.

———. 2017. “Creating Html or Markdown Documents from Within Stata Using Webdoc.” Stata Journal 17 (1): 3–38(36). http://www.stata-journal.com/article.html?article=pr0065.

Jann, Benn. 2005. “Making Regression Tables from Stored Estimates.” Stata Journal 5 (3): 288–308(21). http://www.stata-journal.com/article.html?article=st0085.

———. 2007. “Making Regression Tables Simplified.” Stata Journal 7 (2): 227–244(18). http://www.stata-journal.com/article.html?article=st0085_1.

Jones, Maria Ruth, Florence Kondylis, John Ashton Loeser, and Jeremy Magruder. 2019. Factor Market Failures and the Adoption of Irrigation in Rwanda. The World Bank.

Keating, Joseph, Andrea Locatelli, Andemariam Gebremichael, Tewolde Ghebremeskel, Jacob Mufunda, Selam Mihreteab, Daniel Berhane, and Pedro Carneiro. 2011. “Evaluating Indoor Residual Spray for Reducing Malaria Infection Prevalence in Eritrea: Results from a Community Randomized Control Trial.” Acta Tropica 119 (2-3): 107–13.

Kerr, Norbert L. 1998. “HARKing: Hypothesizing After the Results Are Known.” Personality and Social Psychology Review 2 (3): 196–217.

Kondylis, Florence, Arianna Legovini, Kate Vyborny, Astrid Maria Theresia Zwager, and Luiza Cardoso De Andrade. 2020. “Demand for Safe Spaces: Avoiding Harassment and Stigma.” World Bank Policy Research Working Paper, no. 9269.

Kondylis, Florence, Valerie Mueller, Glenn Sheriff, and Siyao Zhu. 2016. “Do Female Instructors Reduce Gender Bias in Diffusion of Sustainable Land Management Techniques? Experimental Evidence from Mozambique.” World Development 78: 436–49.

Kondylis, Florence, Valerie Mueller, and Siyao Zhu. 2015. “Measuring Agricultural Knowledge and Adoption.” Agricultural Economics 46 (3): 449–62.

Kondylis, Florence, and Mattea Stein. 2018. The Speed of Justice. The World Bank.

Kopka, Helmut, and Patrick W Daly. 1995. “A Guide to LATEX.” IEEE Multimedia 2: 473–80.

Kuld, Lukas, and John O’Hagan. 2017. “The Trend of Increasing Co-Authorship in Economics: New Evidence.”

Legovini, Arianna, Guigonan Serge Adjognon, Guadalupe Bedoya Arguelles, Theophile Bougna Lonla, Kayleigh Bierman Campbell, Paul J. Christian, Aidan Coville, et al. 2019. “Science for Impact: Better Evidence for Better Decisions -– the DIME Experience.” World Bank Group. http://documents.worldbank.org/curated/en/942491550779087507/Science-for-Impact-Better-Evidence-for-Better-Decisions-The-Dime-Experience.

Legovini, Arianna, Vincenzo Di Maro, and Caio Piza. 2015. Impact Evaluation Helps Deliver Development Projects. The World Bank.

McCullough, Bruce D, Kerry Anne McGeary, and Teresa D Harrison. 2008. “Do Economics Journal Archives Promote Replicable Research?” Canadian Journal of Economics/Revue Canadienne d’économique 41 (4): 1406–20.

McGovern, Mark E. 2012. “A Practical Introduction to Stata.” PGDA Working Papers 9412. Program on the Global Demography of Aging. https://ideas.repec.org/p/gdm/wpaper/9412.html.

Nosek, Brian A, George Alter, George C Banks, Denny Borsboom, Sara D Bowman, Steven J Breckler, Stuart Buck, et al. 2015. “Promoting an Open Research Culture.” Science 348 (6242): 1422–5.

Nosek, Brian A, Charles R Ebersole, Alexander C DeHaven, and David T Mellor. 2018. “The Preregistration Revolution.” Proceedings of the National Academy of Sciences 115 (11): 2600–2606.

Olken, Benjamin A. 2015. “Promises and Perils of Pre-Analysis Plans.” Journal of Economic Perspectives 29 (3): 61–80.

Orozco, Valerie, Christophe Bontemps, Elise Maigne, Virginie Piguet, Annie Hofstetter, Anne Lacroix, Fabrice Levert, Jean-Marc Rousselle, and others. 2018. “How to Make a Pie? Reproducible Research for Empirical Economics & Econometrics.” Toulouse School of Economics Working Paper 933.

Ozier, Owen. 2019. Replication Redux: The Reproducibility Crisis and the Case of Deworming. The World Bank.

Özler, Berk, Lia CH Fernald, Patricia Kariger, Christin McConnell, Michelle Neuman, and Eduardo Fraga. 2016. Combining Preschool Teacher Training with Parenting Education: A Cluster-Randomized Controlled Trial. The World Bank.

Pradhan, Menno, Sally A Brinkman, Amanda Beatty, Amelia Maika, Elan Satriawan, Joppe de Ree, and Amer Hasan. 2013. “Evaluating a Community-Based Early Childhood Education and Development Program in Indonesia: Study Protocol for a Pragmatic Cluster Randomized Controlled Trial with Supplementary Matched Control Group.” Trials 14 (1): 259.

Prennushi, Giovanna, and Abhishek Gupta. 2014. Women’s Empowerment and Socio-Economic Outcomes: Impacts of the Andhra Pradesh Rural Poverty Reduction Program. The World Bank.

Rodriguez, G. 2017. “Literate Data Analysis with Stata and Markdown.” Stata Journal 17 (3): 600–618(19). http://www.stata-journal.com/article.html?article=pr0067.

Simmons, Joseph P, Leif D Nelson, and Uri Simonsohn. 2011. “False-Positive Psychology: Undisclosed Flexibility in Data Collection and Analysis Allows Presenting Anything as Significant.” Psychological Science 22 (11): 1359–66.

Simonsohn, Uri, Leif D Nelson, and Joseph P Simmons. 2014. “P-Curve: A Key to the File-Drawer.” Journal of Experimental Psychology: General 143 (2): 534.

Simonsohn, Uri, Joseph P Simmons, and Leif D Nelson. 2015. “Specification Curve: Descriptive and Inferential Statistics on All Reasonable Specifications.” Available at SSRN 2694998.

StataCorp, LLC. 2019. “Stata Statistical Software: Release 16. College Station, TX.”

Stodden, Victoria, Peixuan Guo, and Zhaokun Ma. 2013. “Toward Reproducible Computational Research: An Empirical Analysis of Data and Code Policy Adoption by Journals.” PLoS One 8 (6): e67111.

Swanson, Nicholas, Garret Christensen, Rebecca Littman, David Birke, Edward Miguel, Elizabeth Levy Paluck, and Zenan Wang. 2020. “Research Transparency Is on the Rise in Economics.” In AEA Papers and Proceedings, 110:61–65.

Sweeney, Latanya. 2000. “Simple Demographics Often Identify People Uniquely.” Working paper. Carnegie Mellon University, Data Privacy. http://dataprivacylab.org/projects/identifiability/.

Vilhuber, Lars. 2020. “Implementing Increased Transparency and Reproducibility in Economics.” Zenodo. https://doi.org/10.5281/zenodo.3911311.

Vilhuber, Lars, James Turrito, and Keesler Welch. 2020. “Report by the AEA Data Editor.” In AEA Papers and Proceedings, 110:764–75.

Wada, Roy. 2014. “OUTREG2: Stata Module to Arrange Regression Outputs into an Illustrative Table.”

Wafula, Francis, Amy Dolinger, Benjamin Daniels, Njeri Mwaura, Guadalupe Bedoya, Khama Rogo, Ana Goicoechea, Jishnu Das, and Bernard Olayo. 2017. “Examining the Quality of Medicines at Kenyan Healthcare Facilities: A Validation of an Alternative Post-Market Surveillance Model That Uses Standardized Patients.” Drugs – Real World Outcomes 4 (1): 53–63.

White, Matthew. 2016. “BCSTATS: Stata Module to Analyze Back Check (Field Audit) Data and Compare It to the Original Survey Data.”

Wicherts, Jelte M, Coosje LS Veldkamp, Hilde EM Augusteijn, Marjan Bakker, Robbie Van Aert, and Marcel ALM Van Assen. 2016. “Degrees of Freedom in Planning, Running, Analyzing, and Reporting Psychological Studies: A Checklist to Avoid P-Hacking.” Frontiers in Psychology 7: 1832.

Wickham, Hadley. 2016. Ggplot2: Elegant Graphics for Data Analysis. Springer-Verlag New York. https://ggplot2.tidyverse.org.

Wickham, Hadley, and Garrett Grolemund. 2017. R for Data Science: Import, Tidy, Transform, Visualize, and Model Data. 1st ed. O’Reilly Media, Inc.

Yishay, Ariel Ben, Maria Jones, Florence Kondylis, and Ahmed Mushfiq. 2016. Are Gender Differences in Performance Innate or Socially Mediated? The World Bank.

Swanson et al. (2020)

Vilhuber (2020)

McCullough, McGeary, and Harrison (2008)

https://blogs.worldbank.org/impactevaluations/more-replication-economics

See Baldwin and Mvukiyehe (2015) for an example.

Camerer et al. (2016)

Process standardization: Agreement within a research team about how all tasks of a specific type will be approached.

Hamermesh (2007)

Ozier (2019)

Chang and Li (2015)

StataCorp, LLC (2019)

See DIME Analytics Coding Standards: https://github.com/worldbank/dime-standards

https://www.worldbank.org/en/research/dime

Legovini, Di Maro, and Piza (2015)

Legovini et al. (2019)

Angrist and Pischke (2010), Ioannidis (2005)

Ioannidis, Stanley, and Doucouliagos (2017)

Simmons, Nelson, and Simonsohn (2011)

Wicherts et al. (2016)

Vilhuber, Turrito, and Welch (2020)

More details on study registrations and links to additional resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Study_Registration

Nosek et al. (2018)

More details on how to pre-register your study and links to other resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Pre-Registration

Kerr (1998)

We recommend this checklist: https://blogs.worldbank.org/impactevaluations/a-pre-analysis-plan-checklist

Gelman and Loken (2013)

More details on how to prepare a pre-analysis plans and links to additional resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Pre-Analysis_Plan

See Cusolito, Dautovic, and McKenzie (2018) for an example.

Olken (2015)

https://blogs.worldbank.org/impactevaluations/pre-analysis-plans-and-registered-reports-what-new-opinion-piece-does-and-doesnt

See Bedoya et al. (2019) for an example.

Duflo et al. (2020)

More details on registered reports and links to additional resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Registered_Reports

https://blogs.worldbank.org/impactevaluations/registered-reports-piloting-pre-results-review-process-journal-development-economics

Simonsohn, Nelson, and Simmons (2014)

See Coville et al. (2019) for an example.

More details on research documentation and links to additional resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Research_Documentation

Duvendack, Palmer-Jones, and Reed (2017)

Archival repository: A third-party service for information storage that guarantees the permanent availability of current and prior versions of materials.

https://osf.io

https://github.com

More details on how to use Git and GitHub and links to all DIME Analytics resources on best practices and how to get started can be found on the DIME Wiki: https://dimewiki.worldbank.org/Getting_started_with_GitHub

See Yishay et al. (2016) for an example.

Original data: A new dataset, as obtained and corrected, that becomes the functional basis for research work.

Vilhuber, Turrito, and Welch (2020)

For example, https://data.usaid.gov

Details on how to document this type of material can be found at https://doi.org/10.5281/zenodo.4319999.

https://microdata.worldbank.org

https:/datacatalog.worldbank.org

Digital object identifier (DOI): A permanent reference for electronic information that persistently updates to a new URL or other locations if the information is relocated.

Christensen and Miguel (2018)

More details and links to additional resources on how to make your research reproducible and prepare a reproducibility package can be found on the DIME Wiki: https://dimewiki.worldbank.org/Reproducible_Research. More details can also be found under Pillar 3 in the DIME Research Standards: https://github.com/worldbank/dime-standards.

More details and links to best practices on topics related to data publication, such as de-identification and how to license published data, can be found on the DIME Wiki: https://dimewiki.worldbank.org/Publishing_Data. More details can also be found under Pillar 5 in the DIME Research Standards: https://github.com/worldbank/dime-standards

Stodden, Guo, and Ma (2013)

The DIME Analytics reproducibility checklist can be found in Pillar 3 of the DIME Research Standards at https://github.com/worldbank/dime-standards.

Nosek et al. (2015)

Computational reproducibility: The ability of another individual to reuse the same code and data and obtain the exact same results as yours.

More details and links to additional resources on how to make your research reproducible and prepare a reproducibility package can be found on the DIME Wiki: https://dimewiki.worldbank.org/Reproducible_Research. More details can also be found under Pillar 3 in the DIME Research Standards: https://github.com/worldbank/dime-standards.

https://blogs.worldbank.org/impactevaluations/what-development-economists-talk-about-when-they-talk-about-reproducibility

Simonsohn, Simmons, and Nelson (2015)

https://blogs.worldbank.org/opendata/making-analytics-reusable

Read more details about back up strategies and other aspects of data storage on the DIME Wiki: https://dimewiki.worldbank.org/Data_Storage.

More naming conventions and links to more resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Naming_Conventions.

Git: A distributed version control system for collaborating on and tracking changes to code as it is written.

Read more about how to install and use ieboilstart and how it can help you harmonize settings across users as much as possible in Stata on the DIME Wiki: https://dimewiki.worldbank.org/ieboilstart.

https://www.rstudio.com

More details on the benefits of external code editors and links to popular code editors can be found on the DIME Wiki: https://dimewiki.worldbank.org/Code_Editors.

Read more about how to install and use iefolder, as well as find links to resources explaining the best practices this command build upon on the DIME Wiki: https://dimewiki.worldbank.org/iefolder.

More details on DIME’s suggested data work folder structure and explanations of the best practices it is based on can be found on the DIME Wiki: https://dimewiki.worldbank.org/DataWork_Folder.

Git only tracks files, so empty folders – which most folders are in the beginning of a project – are ignored if placeholder files are not used, leading to only parts of the folder structure being shared across the team. Read more about how to install and use iegitaddmd and how it can help you track empty folder in Git on the DIME Wiki: https://dimewiki.worldbank.org/Iegitaddmd.

Comments: Code components that have no function to the computer, but describe in plain language for humans to read what the code is supposed to do.

More details and description of each section of our template master do-file can be found on the DIME Wiki: https://dimewiki.worldbank.org/Master_Do-files.

Personally-identifying information: any piece or set of information that can be used to identify an individual research subject. Read more about what extra consideration you must take into account when working with PII data on the DIME Wiki: https://dimewiki.worldbank.org/Protecting_Human_Research_Subjects.

More details on statistical disclosure and links to best practices related to data publication, can be found on the DIME Wiki: https://dimewiki.worldbank.org/Publishing_Data.

See Baldwin, Muyengwa, and Mvukiyehe (2017) for an example.

Bierer, Barnes, and Lynch (2017)

https://gdpr-info.eu

Read more about what extra consideration you must take into account when working with human subjects on the DIME Wiki: https://dimewiki.worldbank.org/Protecting_Human_Research_Subjects

More details on research ethics as well as links to tools and other resources related can be found on the DIME Wiki: https://dimewiki.worldbank.org/Research_Ethics. More details can also be found under Pillar 1 in the DIME Research Standards: https://github.com/worldbank/dime-standards

Institutional Review Board (IRB): An institution formally responsible for ensuring that research meets ethical standards.

More details and best practices for how to submit a project for an IRB approval can be found on the DIME Wiki: https://dimewiki.worldbank.org/IRB_Approval.

More details on best practices when obtaining informed consent and links to additional resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Informed_Consent.

Read more about data security and the options you have to protect your data either on the DIME Wiki: https://dimewiki.worldbank.org/Data_Security, or under Pillar 4 in the DIME Research Standards https://github.com/worldbank/dime-standards.

Read our step-by-step guide for how to get started with password managers under Pillar 4 in the DIME Research Standards: https://github.com/worldbank/dime-standards.

Virtual Private Network (VPN): Allows you to securely connect to a network you trust over an insecure network. With the VPN you can securely communicate with other devices on the trusted network and make your traffic to the internet inaccessible to the host of the insecure network.

Encryption: Methods which ensure that files are unreadable even if laptops are stolen, databases are hacked, or any other type of unauthorized access is obtained. Read more about these methods on the DIME Wiki: https://dimewiki.worldbank.org/Encryption.

Read our step-by-step guide for how to get started with Veracrypt under Pillar 4 in the DIME Research Standards: https://github.com/worldbank/dime-standards.

More details and best practices related to de-identification as well as tools that can help you assess disclosure risks can be found on the DIME Wiki: https://dimewiki.worldbank.org/De-identification.

Read more details about end-of-life plans for data and other aspects of data storage on the DIME Wiki: https://dimewiki.worldbank.org/Data_Storage.

See Kondylis and Stein (2018) for an example of a project using an innovative combination of administrative and survey data.

More details on DIME’s data map template and links to related topics with examples can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_Map.

More details on DIME’s data linkage table template and an example can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_Linkage_Table.

More details on the concept of unit of observations can be found on the DIME Wiki: https://dimewiki.worldbank.org/Unit_of_Observation.

More details on DIME’s master dataset template and an example can be found on the DIME Wiki: https://dimewiki.worldbank.org/Master_Data_Set.

More details on DIME’s data flow chart template and an example can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_Flow_Chart.

Project ID: The main ID used in your project to identify observations. You should never have multiple project IDs for the same unit of observation. The project ID must uniquely and fully identify all observations in the project. See https://dimewiki.worldbank.org/ID_Variable_Properties#Project_ID for more details.

See Fernandes, Hillberry, and Mendoza Alcantara (2017) for an example.

See Benhassine et al. (2018) for an example.

Treatment: The general word for the evaluated intervention or event. This includes things like being offered a training, a cash transfer from a program, or experiencing a natural disaster, among many others.

Counterfactual: A statistical description of what would have happened to specific individuals in an alternative scenario, for example, a different treatment assignment outcome.

Average treatment effect (ATE): The expected average change in outcome that untreated units would have experienced had they been treated.

Read more about how to install and use iebaltab and how it simplifies balance tables in Stata on the DIME Wiki: https://dimewiki.worldbank.org/iebaltab.

More details on RCTs and links to even more extensive resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Randomized_Control_Trials.

Duflo, Glennerster, and Kremer (2007), Gibson and Sautmann (2020)

More details on quasi-experimental research designs and links to even more extensive resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Quasi-Experimental_Methods

More details on RD designs and links to even more extensive resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Regression_Discontinuity.

See Alix-Garcia et al. (2019) for an example.

More details on IV designs and links to even more extensive resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Instrumental_Variables.

See Calderon, Iacovone, and Juarez (2017) for an example.

More details on matching methods and links to even more extensive resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Matching.

See Prennushi and Gupta (2014) for an example.

See Pradhan et al. (2013) for an example.

See Kondylis et al. (2016) for an example.

See Bertrand et al. (2017) for an example.

See Goldstein et al. (2015) for an example.

Randomization is often used interchangeably to mean random treatment assignment. In this book however, randomization will only be used to describe the process of generating a sequence of unrelated numbers, i.e. a random process. Randomization will never be used to mean the process of assigning units in treatment and control groups, that will always be called random treatment assignment, or a derivative thereof.

More details on sampling and important consideration related to sample size, as well as links to even more extensive resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Sample_Size_and_Power_Calculations.

See De Andrade, Bruhn, and McKenzie (2013) for an example.

Orozco et al. (2018)

Pseudo-random number generator: An algorithm that creates a long, fixed sequence of numbers which exhibits no statistical relationships between the position or value of any set of those numbers.

More details on randomization in Stata and the three important steps that needs to be followed to make it reproducible can be found on the DIME Wiki: https://dimewiki.worldbank.org/Randomization_in_Stata.

At the time of writing, we recommend using version 13.1 for backward compatibility; the algorithm used to create this list of random numbers was changed after Stata 14 but the improvements do not matter in practice.

Read more about how to install and use ieboilstart and how this command can help you harmonize settings such as version across users on the DIME Wiki: https://dimewiki.worldbank.org/ieboilstart.

More details and description of each section of our template master do-file can be found on the DIME Wiki: https://dimewiki.worldbank.org/Master_Do-files.

You can draw a uniformly distributed six-digit seed randomly by visiting https://bit.ly/stata-random. (This link is a just shortcut to request such a random number on https://www.random.org.) There are many more seeds possible but this is a large enough set for most purposes.

Athey and Imbens (2017)

More details on the concepts of unit of sampling and unit treatment assignment can be found on the DIME Wiki: go to https://dimewiki.worldbank.org/Unit_of_Observation

More details on clustered sampling and links to additional resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Multi-stage_(Cluster)_Sampling.

See Keating et al. (2011) for an example.

More details on stratified sampling and links to additional resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Stratified_Random_Sample.

https://blogs.worldbank.org/impactevaluations/when-should-you-cluster-standard-errors-new-wisdom-econometrics-oracle

https://blogs.worldbank.org/impactevaluations/tools-of-the-trade-doing-stratified-randomization-with-uneven-numbers-in-some-strata

Carril (2017)

More details on sampling and links to additional resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Sampling.

More details on how to perform power calculations can be found on the DIME Wiki: https://dimewiki.worldbank.org/Sample_Size_and_Power_Calculations.

More details on minimum detectable effect and links to additional resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Minimum_Detectable_Effect.

More details on randomization inference and links to additional resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Randomization_Inference.

More details and best practices related to data ownership can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_Ownership.

More details and best practices related to data ownership can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_Ownership.

Derivatives of data can be indicators, aggregates, visualizations, etc. created from the original data.

More details and best practices for how to submit a project for an IRB approval can be found on the DIME Wiki: https://dimewiki.worldbank.org/IRB_Approval.

More details on data licensing agreements can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_License_Agreement.

https://microdata.worldbank.org

Glewwe and Grosh (2000)

More details and links to CAPI resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Computer-Assisted_Personal_Interviews_(CAPI).

More details and links to questionnaire design resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Questionnaire_Design.

More details and links to questionnaire programming resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Questionnaire_Programming.

More details and links to questionnaire design resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Questionnaire_Design.

More details and links to more resources about theories of change can be found at the DIME Wiki: https://dimewiki.worldbank.org/Theory_of_Change.

More details on causal research designs can be found on the DIME Wiki: https://dimewiki.worldbank.org/Experimental_Methods and https://dimewiki.worldbank.org/Quasi-Experimental_Methods.

More details on how to prepare a pre-analysis plans and links to additional resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Pre-Analysis_Plan.

Links to resources with extensive survey libraries with modules that can be used as starting points can be found on the DIME Wiki: https://dimewiki.worldbank.org/Literature_Review_for_Questionnaire.

Begg et al. (1996)

More details on how to plan, prepare for, and implement a comprehensive survey pilot, and links to complementary resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Survey_Pilot.

More details on selecting appropriate respondents for a survey pilot can be found on the DIME Wiki: https://dimewiki.worldbank.org/Survey_Pilot_Participants.

A checklist for how to prepare for a survey pilot can be found on the DIME Wiki: https://dimewiki.worldbank.org/Checklist:_Preparing_for_a_Survey_Pilot..

A checklist for content-focused pilots can be found on the DIME Wiki: https://dimewiki.worldbank.org/Checklist:_Content-focused_Pilot.

A checklist for survey protocols that should be tested during a survey pilot can be found on the DIME Wiki: https://dimewiki.worldbank.org/Checklist:_Piloting_Survey_Protocols.

At the time of publishing this book, SurveyCTO was the most commonly used survey software at DIME. Best practices for SurveyCTO code (that almost always applies to other survey software as well) can be found on the DIME Wiki: https://dimewiki.worldbank.org/SurveyCTO_Coding_Practices.

Coded response options: Responses to questions which require respondents to select from a list of choices, corresponding to underlying numerical response codes.

Open-ended questions: Responses to questions which do not impose any structure on the response, typically recorded as free-flowing text.

Likert scale: an ordered selection of choices indicating the respondent’s level of agreement or disagreement with a proposed statement.

See Wafula et al. (2017) for an example.

More details on naming conventions can be found on the DIME Wiki: https://dimewiki.worldbank.org/Naming_Conventions#Variable_Names.

Read more about how to install and use ietestform and the reasoning for all the tests it performs on the DIME Wiki: https://dimewiki.worldbank.org/ietestform.

Bjärkefur, Andrade, and Daniels (2020)

A checklist with best practices important to remember during a data-focused pilot can be found on the DIME Wiki: https://dimewiki.worldbank.org/Checklist:_Data-focused_Pilot.

For more details on how to design an enumerator manual and a template for enumerator manuals see the DIME Wiki: https://dimewiki.worldbank.org/Enumerator_Training#Enumerator_manual.

For more details and examples of common survey protocols see the DIME Wiki: https://dimewiki.worldbank.org/Survey_Protocols

More deatails and best practices related to enumerator trainings can be found on the DIME Wiki: https://dimewiki.worldbank.org/Enumerator_Training.

DIME Analytics developed standard guidelines for introducing field staff to the survey software DIME uses most commonly, SurveyCTO: https://osf.io/n7ctd/.

More details on enumerator assessment metrics can be found on the DIME Wiki: https://dimewiki.worldbank.org/Enumerator_Training#Assessing_Enumerators.

More details on how to develop a data quality assurance plan can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_Quality_Assurance_Plan.

More details on monitoring data quality can be found on the DIME Wiki: https://dimewiki.worldbank.org/Monitoring_Data_Quality.

More details on HFCs and what types of checks should be included can be found on the DIME Wiki: https://dimewiki.worldbank.org/High_Frequency_Checks.

https://github.com/PovertyAction/high-frequency-checks.

See Kondylis, Mueller, and Zhu (2015) for an example.

More details on how to design and implement back-checks can be found on the DIME Wiki: https://dimewiki.worldbank.org/Back_Checks.

White (2016)

More details on audio audits and important considerations when using them can be found on the DIME Wiki: https://dimewiki.worldbank.org/Monitoring_Data_Quality#Random_audio_audits.

More details about what makes data PII and links to more resources on the extra consideration that must be taken when working with PII data can be found on the DIME Wiki: https://dimewiki.worldbank.org/Personally_Identifiable_Information_(PII).

Read more about data security and the options you have to protect your data either on the DIME Wiki: https://dimewiki.worldbank.org/Data_Security, or under Pillar 4 in the DIME Research Standards https://github.com/worldbank/dime-standards.

More details on what encryption is and how it should be used to protect your data can be found on the DIME Wiki: https://dimewiki.worldbank.org/Encryption.

Read our step-by-step guide for how to get started with password managers under Pillar 4 in the DIME Research Standards: https://github.com/worldbank/dime-standards.

More details on what encryption-in-transit is and when it should be used to protect your data can be found on the DIME Wiki: https://dimewiki.worldbank.org/Encryption#Encryption_in_Transit.

More details on what encryption-at-rest is and when it should be used to protect your data can be found on the DIME Wiki: https://dimewiki.worldbank.org/Encryption#Encryption_at_Rest.

More details on what symmetric encryption is and when it should be used can be found on the DIME Wiki: https://dimewiki.worldbank.org/Encryption#Symmetric_Encryption.

More details on what asymmetric encryption is and when it should be used can be found on the DIME Wiki: https://dimewiki.worldbank.org/Encryption#Asymmetric_Encryption.

Data table: data that is structured into rows and columns. Also called tabular datasets or rectangular data. Examples of non-rectangular data are written text, NoSQL and graph databases, or files such as images.

Unit of observation: the unit described by the data. In datasets, it is ideally what each row represents. More details on the concept of unit of observations can be found on the DIME Wiki: https://dimewiki.worldbank.org/Unit_of_Observation.

More details on the properties required for variables that uniquely identifies each observation can be found on the DIME Wiki: https://dimewiki.worldbank.org/ID_Variable_Properties.

More details on DIME’s data linkage table template and an example can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_Linkage_Table.

More details on DIME’s master dataset template and an example can be found on the DIME Wiki: https://dimewiki.worldbank.org/Master_Data_Set.

We use the expression raw data to refer to the “data in the state it was originally received by the research team”. In other sources, you will also see it used to refer to the “corrected and compiled dataset created from received information, reflecting only that information”, which we call clean data. This applies to data acquired from partners as well as original data collected by the research team.

More details on what makes an ID variable a suitable Project ID variable can be found on the DIME Wiki: https://dimewiki.worldbank.org/ID_Variable_Properties#Project_ID.

Such operations are commonly called `merges" in Stata, and     "joins" in R'stidyversedialect.     We will use the termmerge` in this book.

Read more about how to install and use ieduplicates and how the command can help you efficiently deal with duplicates on the DIME Wiki: https://dimewiki.worldbank.org/ieduplicates.

Variable: the collection of all data points that measure the same attribute for each observation.

Wide data: a data table where a single variable is divided into multiple columns, for example one for each individual in a household.

Reshape: transform a data table in such a way that the unit of observation represented by a row changes.

https://github.com/PovertyAction/high-frequency-checks

More details on how to deal with duplicates during surveys and how to track completion can be found on the DIME Wiki: https://dimewiki.worldbank.org/Duplicates_and_Survey_Logs

Read more about how to install and use ieduplicates and how the command can help you efficiently deal with duplicates on the DIME Wiki: https://dimewiki.worldbank.org/ieduplicates.

See Özler et al. (2016) for an example.

More details about real-time data quality assurance and links to additional resources can be found on the DIME Wiki: https://dimewiki.worldbank.org/Monitoring_Data_Quality.

Read more about what extra consideration you must take into account when working with human subjects on the DIME Wiki: https://dimewiki.worldbank.org/Protecting_Human_Research_Subjects.

See Banerjee, Ferrara, and Orozco (2019) for an example.

More details on research ethics as well as links to tools and other resources related can be found on the DIME Wiki: https://dimewiki.worldbank.org/Research_Ethics. It can also be found under Pillar 1 in the DIME Research Standards: https://github.com/worldbank/dime-standards.

Protecting Human Research Participants (https://phrptraining.com) and the CITI Program (https://citiprogram.org) are common options.

More details and best practices related to de-identification as well as tools that can help you assess disclosure risks can be found on the DIME Wiki: https://dimewiki.worldbank.org/De-identification.

https://github.com/J-PAL/PII-Scan and https://github.com/PovertyAction/PII_detection.

Benschop, Machingauta, and Welch (2019)

Read more about how to install and use iecodebook and how the command can help in de-identification and other cleaning tasks on the DIME Wiki: https://dimewiki.worldbank.org/iecodebook

Data construction: The process of creating complex or abstract measures from raw information that is directly observed or collected.

More details on value labels in Stata and best practices on how to work with them can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_Cleaning#Value_Labels

More details on survey codes and how they relate to best practices when working with missing values in Stata can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_Cleaning#Survey_Codes_and_Missing_Values

More details on variable labels in Stata and best practices on how to work with them can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_Cleaning#Variable_Labels

Read more about how to install and use iecodebook and how the command can help making cleaning tasks more efficient on the DIME Wiki: https://dimewiki.worldbank.org/iecodebook

https://www.tidyverse.org/

See Fernandes, Hillberry, and Alcántara (2015) for an example.

More details on how to best document your data and links to additional resources on this topic can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_Documentation

Wickham and Grolemund (2017)

See chapter 5 for discussions on how to tidy data, monitor data quality and document corrections.

Data construction: The process of transforming cleaned data into analysis data by creating the derived indicators that will be analyzed.

See Adjognon, Soest, and Guthoff (2019) for an example.

More details on the concepts of unit of observations and unit of analysis can be found on the DIME Wiki: https://dimewiki.worldbank.org/Unit_of_Observation

More details on DIME’s data flow chart template and an example can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_Flow_Charts

More details on DIME’s data linkage table template and an example can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_Linkage_Table

For more details on how to deal with outliers see the DIME Wiki: https://dimewiki.worldbank.org/Variable_Construction\#Dealing_with_outliers

Read more about how to install and use iecodebook and how the command can help appending data more efficiently on the DIME Wiki: https://dimewiki.worldbank.org/iecodebook

See Daniels et al. (2017) for an example.

See Jones et al. (2019) for an example.

Angrist and Pischke (2008)

Cunningham (2018)

Healy (2018),wilke2019fundamentals

https://worldbank.github.io/Stata-IE-Visual-Library

https://worldbank.github.io/r-econ-visual-library/

More tools and links to other resources for creating good data visualizations can be found on the DIME Wiki: https://dimewiki.worldbank.org/Data_visualization

Read more about how to install and use iegraph and how the command can be used to easily create graphs for two very common impact evaluation regressions on the DIME Wiki: https://dimewiki.worldbank.org/Iegraph

Exporting results: The creation of publication-ready representations of results.

For a more detailed discussion on this, including different ways to export tables from Stata, see https://blogs.worldbank.org/impactevaluations/nice-and-fast-tables-stata

Daniels (2019)

Hlavac (2015)

Wickham (2016)

Read more about how to install and use iebaltab and how it simplifies balance tables in Stata on the DIME Wiki: https://dimewiki.worldbank.org/iebaltab.

Read more about how to install and use ieddtab and how it simplifies generating tables for difference-in-differences regressions in Stata on the DIME Wiki: https://dimewiki.worldbank.org/ieddtab.

A checklist with best practices important to remember to generate informative and easy to read tables can be found on the DIME Wiki: https://dimewiki.worldbank.org/Checklist:_Submit_Table.

Dynamic documents: File types that include direct references to exported materials and update them in the output automatically.

https://www.markdownguide.org/

https://rmarkdown.rstudio.com

https://www.stata.com/manuals/rptdyndoc.pdf

https://jupyter.org

See more details at https://www.stata.com/manuals/rptputexcel.pdf and https://www.stata.com/stata-news/news32-3/spotlight-putdocx/.

See https://github.com/worldbank/DIME-LaTeX-Templates.

Kuld and O’Hagan (2017)

https://github.com/worldbank/dime-data-handbook

Kopka and Daly (1995)

https://pandoc.org

https://github.com/citation-style-language/styles

https://github.com/worldbank/DIME-LaTeX-Templates

https://www.texstudio.org

https://atom.io/packages/atom-latex

https://www.overleaf.com/

For an example, see the replication package for Kondylis et al. (2020) in https://github.com/worldbank/rio-safe-space.

Disclosure risk: the likelihood that a released data record can be associated with an individual or organization.

Sweeney (2000)

Benschop, Machingauta, and Welch (2019)

Abowd (2018)

More details and links to best practices on topics related to data publication, such as de-identification and how to license your published data, can be found on the DIME Wiki: https://dimewiki.worldbank.org/Publishing_Data. More details can also be found under Pillar 5 in the DIME Research Standards: https://github.com/worldbank/dime-standards.

https://www.doi.org

https://datacatalog.worldbank.org

https://microdata.worldbank.org

More details on how to submit to the World Bank Microdata Catalog and links to DIME’s submissions there can be found on the DIME Wiki: https://dimewiki.worldbank.org/Microdata_Catalog

https://dataverse.harvard.edu and https://dataverse.harvard.edu/dataverse/DFEEP

https://microdata.worldbank.org/catalog/dime

https://microdata.worldbank.org/index.php/terms-of-use

Vilhuber, Turrito, and Welch (2020)

Hoces de la Guardia, Grant, and Miguel (2018)

Such as https://github.com/worldbank/sdgatlas2018, https://blogs.worldbank.org/opendata/how-we-mass-produced-reproducible-human-capital-project-country-briefs, or https://blogs.worldbank.org/impactevaluations/what-development-economists-talk-about-when-they-talk-about-reproducibility

https://github.com/worldbank/dime-standards

The renv package helps you maintain reproducibility by tracking versions of packages used: https://rstudio.github.io/renv/articles/renv.html

Read more about how to install and use ieboilstart and how this command can help you harmonize settings such as version across users on the DIME Wiki: https://dimewiki.worldbank.org/ieboilstart.

More details and links to additional resources on how to make your research reproducible and prepare a reproducibility package can be found on the DIME Wiki: https://dimewiki.worldbank.org/Reproducible_Research. More details can also be found under Pillar 3 in the DIME Research Standards: https://github.com/worldbank/dime-standards

https://osf.io

https://dataverse.harvard.edu

https://www.researchgate.net

https://codeocean.com

https://doi.org/10.5281/zenodo.4319999